## Slide 1
V. Kekelidze,
NICA
Volga
river
127-th session of the Scientific Council,
20 – 21 February, 2020, Dubna
Progress of implementation of the 7-year Plan (2017−2023)
in the NICA project & proposal to update the Plan
Notes: Good afternoon! First of all I would like to express my gratitude to Prof. Livai and organizers for the invitation and opportunity to give a talk at the Wigner Colloquium

## Slide 2
essential upgrade of existing accelerator complex;
construction of Collider to provide collisions of
ions from p to Au and polarized p и d;
construction of 3 detectors: Baryonic Matter @ Nuclotron (BM@N), Multi Purpose Detector (MPD) and Spin Physics Detector (SPD).
Main goals: to obtain comprehensive information on
hot and dense baryonic matter:
- phase transition peculiarity;
- whether there is a critical end-point?
nucleon spin structure:
- how the spin of proton / neutron is composed?
Notes: NICA is a Nuclotron … The main targets of the project are: ..
That has required a development of accelerator facility and construction of

## Slide 3
NICA Complex:
Accelerators, Detectors, Infrastructure
Notes: Few words on the NICA …

## Slide 4
Objects
Accelerator block:
Nuclotron
Nuclotron & channels
Injector complex
Injection complex
Booster
Booster
Collider
Collider
Notes: This is a view of major NICA facilities. The Nuclotron – supercoducting synchrotron with circumference of 250 meters was put in operation 24 years ago. The beams from Nuclotron are extracted to the experimental hall, where the first experiment of NICA program BM@N is located. The plan is to put in operation a booster in 2019, and collider - in 2020 simultaneously with the MPD.

## Slide 5
Type сю | SC synchrotron
particles | p, d, nuclei
max. kinetic energy, GeV/u | 10.71 ( p); 5.35 ( d) 3.8 (Au)
max. mag. rigidity, Tm | 38.5
circumference, m | 251.52
vacuum, Torr | 10-9
intensity, Au /pulse | 1 109
Nuclotron
The Collider
45 T*m, 11 GeV/u for Au79+
Ring circumference, m | 503,04
Number of bunches | 22
r.m.s. bunch length, m | 0,6
b, m | 0,35
Energy in c.m., Gev/u | 4-11
r.m.s. Dp/p, 10-3 | 1,6
IBS growth time, s | 1800
Luminosity, cm-2 s-1 | 1x1027
Design parameters, Stage II
Stage I:
without ECS
reduced number of RF
reduced luminosity
 | value
ion species | A/Z < 3
max. energy, MeV/u | 600
magnetic rigidity, T m | 1.6 – 25.0
circumference, m | 210.96
vacuum, Tor | 10-11
intensity, Au /p | 1.5 109
Booster
Notes: The Nuclotron, synchrotron based on the SC magnets developed at JINR, was put in operation in 1993. In was essentially modernized in 2010-2015. It will provide acceleration of gold ions up to kinetic energy 4,4 GeV/u, and protons up to 12 GeV.

## Slide 6
The technological line for production, tests and
certification of SC magnets for NICA and FAIR
was put in operation on November 28, 2016

## Slide 7
Magnet production (к. 217)
all Booster magnets are produced and tested
production of
Collider magnets
is in progress
Notes: The technological line for magnet assembly and test has been put in operation. In total almost 450 magnets will be fabricated for NICA and FAIR /SIS100 accelerators. The booster magnet fabrication is going well.
All yokes are already produced and delivered.

## Slide 8
Reference period
Nuclotron
injection
Power supplies
RF station
extraction
E-cooling system
Booster: assembly since 2018
Booster
Nuclotron

## Slide 9
ECS - mounted & tested (Budker institute)
beam diagnostics - 90%
control systems - 95%
ACS of beam pipe vacuum pumping - 40%
all 40 dipoles
and
24 quadrupole doublets
mounted in the tunnel;
Control and monitoring systems:
Booster systems

## Slide 10
Power supply and energy evacuation systems
Power Supply
equivalent load
switches
Energy evacuation keys
busbar trunking
readiness:
basic IPS -98%
busbar trunking system - 80%
control system - 95%
commissioning
10-12.2019

## Slide 11
Booster commissioning schedule
Booster assembly |  | 2018 |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  | 
 |  | V | VI | VII | VIII | IX | X | XI | XII | I | II |  | III | IV | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | VI | VI
“Cold” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | bypasses and ends |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | reference magnets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | “Warm” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | E-cooling |  |  |  | commissioned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | injection section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | beam extraction section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | RF system |  |  |  |  |  | Tested |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | vacuum system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | power supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | cryogenic system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | thermometry system |  |  |  |  |  |  | Tested |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
technological commissioning
Commissioning with beam

## Slide 12
Official start of the Booster commissioning
23 December 2019

## Slide 13
MPD
SPD
Collider systems installation
Start of installation:
magnets August 2020
channel equipment - July 2020
RF systems - summer 2020
ECS - summer 2021
Notes: The lattice design and prototyping of most collider elements are completed. The ring circumference is twice as one of the Nuclotron. For the gold beam a Luminosity at the energy above 10 GeV per nucleon will be 10 to the 27

## Slide 14
Collider magnets
Dipoles assembly and tests 35%
Quadrupoles 10%
Final focus systems 5%
mounting & commissioning
07.2020 - 07.2021
 | dipoles | lenses
number | 80+8* | 70+12**
Мах. field / gradient | 1.8 T | 23.1 T/m
weignt | 1670 kg | 240 kg

## Slide 15
Nuclotron- Collider transport channels
(Sigma-Phi)
15
Magnetic element | Number | Effective length, m | Max. magnetic field (gradient), T (T/m)
Long dipole | 21 | 2 | 1.5
Short dipole | 6 | 1.2 | 1.5
Quadrupole Q10 | 22 | 0.353 | 31
Quadrupole Q15 | 6 | 0.519 | 31
Steerer | 33 | 0.466 | 0.114
magnets – readiness 95%
delivery 02.2020
Vaccum chamber and diagnostics
- readiness 70%
delivery 06.2020
Power supplies- readiness 10%
delivery 08.2020
mounting & commissioning
- 08.2020 > 02.2021

## Slide 16
Accelerator commissioning schedule
works /contracts in progress
magnet assembly & tests
technological run
commissioning with the beam
Completion of mounting December2021

## Slide 17
Objects
Detectors:
Baryonic Matter @ Nuclotron
BM@N
Multi Purpose Detector
MPD
Spin Physics Detector
SPD TDR
Notes: This is a view of major NICA facilities. The Nuclotron – supercoducting synchrotron with circumference of 250 meters was put in operation 24 years ago. The beams from Nuclotron are extracted to the experimental hall, where the first experiment of NICA program BM@N is located. The plan is to put in operation a booster in 2019, and collider - in 2020 simultaneously with the MPD.

## Slide 18
University of Plovdiv, Bulgaria;
Institute of High Energy Physics, China;
Shanghai Institute of Nuclear and Applied Physics, CFS, China;
Tsinghua University, Beijing, China;
Nuclear Physics Institute CAS, Czech Republic;
Tubingen University, Germany;
Tel Aviv University, Israel;
Joint Institute for Nuclear Research;
Almaty Institute of Physics & Technology, Kazakhstan;
Institute of Applied Physics, Chisinev, Moldova;
Warsaw University of Technology, Poland;
Baryonic Matter at Nuclotron
(BM@N) Collaboration:
University of Wroclaw, Poland;
Institute of Nuclear Research RAS, Moscow, Russia;
NRC Kurchatov Institute, Moscow, Russia;
Institute of Theoretical & Experimental Physics, NRC KI, Moscow, Russia;
Moscow Engineer and Physics Institute, Russia;
Skobeltsin Institute of Nuclear Physics, MSU, Russia;
Moscow Institute of Physics and Technics, Moscow, Russia;
Massachusetts Institute of Technology, Cambridge, USA.
11 Countries, 21 Institutions, 245 participants

## Slide 19
Mobily computing farm for BM@N
Baryonic Matter at Nuclotron (BM@N)

## Slide 21
First result of BM@N experiment: Λ hyperon yield in C+C, Al, Cu, Pb interactions
Results presented at SQM 2019 and QM 2019 conferences

## Slide 22
year | 2017 | 2018 | 2021 | 2022 +
beam | C | Ar,Kr, C(SRC) | Kr,Xe | Up to Au
beam, Hz | 0.5M | 0.5M | 0.5M | 2-5M
trigger, Hz | 5k | 10k | 10k | 20k→50k
central tracker | 6 ½ pl.GEM | 6 ½ pl.GEM +3 pl. FwdSi | 7 pl. GEM + 3 pl. FwdSi | 7 pl. GEM + 3 pl. FwdSi + 4 stations STS
status | Tech run | Tech & physics runs | Phys run, Stage I | Phys run, Stage II
Baryonic Matter at Nuclotron (BM@N)

## Slide 23
Baku State University, NNRC, Azerbaijan;
University of Plovdiv, Bulgaria;
University Tecnica Federico Santa Maria, Valparaiso, Chili;
Tsinghua University, Beijing, China;
USTC, Hefei, China;
Huizhou University, Huizhou, China;
Institute of Nuclear and Applied Physics, CAS, Shanghai, China;
Central China Normal University, China;
Shandong University, Shandong, China;
Consortium MEXNICA, Mexico;
Institute of Applied Physics, Chisinev, Moldova;
WUT, Warsaw, Poland; NCN, Otwock – Swierk, Poland;
UW, Wroclaw, Poland; Jan Kochanowski University, Kielce, Poland;
INR RAS, Moscow, Russia;
MEPhI, Moscow, Russia;
PNPI, Gatchina, Russia;
INP MSU, Moscow, Russia;
KI NRS, Moscow, Russia;
SPSU - Dept. of NP, Russia;
St. Petersburg, Russia;
SPSU – Dept. of HEP, St. Petersburg, Russia;
North Ossetia State University, Vladikavkaz, Russia;
IHEP, Beijing, China;
University of South China, China;
Palacky University, Olomouc, Czech Republic;
NPI CAS, Rez, Czech Republic;
Tbilisi State University, Tbilisi, Georgia;
Tubingen University, Tubingen, Germany; Tel Aviv University, Tel Aviv, Israel;
Joint Institute for Nuclear Research;
IPT, Almaty, Kazakhstan;
FHCal
MPD Collaboration:
11 Countries, 38 Institutes, 505 participants
spokesperson – A. Kisiel WUT, Poland

## Slide 24
Stage I: TPC, TOF, ECAL, FHCal, FFD
Multi-Purpose Detector (MPD)
URQMD
charged
b<11 fm
dN/dh
ECal
h
TPC
FFD
FHCal
TOF
acceptance
11 A GeV
4 A GeV
Stage I: put in operation in 2021
Notes: The MPD will be put in operation at two stages. At the first one the barrel part will be equipped with major tracking detector TPC, TOF end ECAL. FHC and FD will be operational as well.
At the second stage the detector will be supplemented with IT and end cap subdetectors.

## Slide 25
Multi-Purpose Detector (MPD)
URQMD
charged
b<11 fm
dN/dh
ECal
h
TPC
FFD
FHCal
TOF
acceptance
CPC
Stage II
Stage II ( 2023): + ITS + EndCap (CPC / Straw, TOF, ECAL)
Stage I: TPC, TOF, ECAL, FHCal, FFD
Stage I: put in operation in 2021
11 A GeV
4 A GeV
Notes: The MPD will be put in operation at two stages. At the first one the barrel part will be equipped with major tracking detector TPC, TOF end ECAL. FHC and FD will be operational as well.
At the second stage the detector will be supplemented with IT and end cap subdetectors.

## Slide 26
Control
Duar
cryostat
SC coil
Trim
Coils
SC solenoid:
yoke
B0=0.5 T
Nominal current: 1790 A
Stored energy: 14.6 MJ
Yoke: all parts in Dubna,
control assembly tolerance~ 0,5 mm
The cryostat with SC coil:
- Ready for cold tests
Produced inASG (Genova) и Vitkovice HM
weight ~ 900 t
mounting - Mar.‘20
Notes: The major part of MPD is SC solenoiodal magnet. It is a challenging project due to very high requirement for the magnetic field homogeneity – better that a permill.
After long negotiations a contract is signed with the ASG sc company – the one which produced a big solenoid for CMS. The ASG is responsible for production of coils, cryostat control system etc. In addition the company takes responsibility for the overall supervision and final characteristics.

## Slide 27
FEC64SAM:
4500 SAMPA V4
– delivered from CERN
TPC – the basic tracker
length | 340 сm
radius 4 | 140 сm
Radius 1 | 27 сm
gas | 0,9Ar+0,1CH4
drift velocity | 5.45 см/mks;
drift time | < 30 mks;
N of R/O cham. | 12 + 12
channels | 95 232
Max rate | ~ 7 kHz
Assembly in the clean room
28 modules
280 prop. cham-s
13 440 channels
R/O cards with NINO & HPTC
- are produced
R= 170 cm
20% modules assembled & tested
Time of flight sytem(TOF)

## Slide 28
43000 modules «shashlyk» type(Pb+Sc)
IHEP
p0 gg
~ 100 t
Projective
geometry
s(E) ~ 5% @ 1 GeV;
s(t) ~ 500 ps
Beijing
Blocks f modules
JINR, IHEP, Tensor + .. - 25%
China - 75%
Production plans:
r/o: WLS fibers +MAPD;
L ~35 cм (~ 14 X0);
Segmentation (4x4 cm2).
Supporting structure
- sagitta ~ 5 мм
- material budg. (R)0,13 X0
ECal ~ 100 t
Carbon fiber
Contract signed АО «ЦНИИСМ»
Electromagnetic calorimetry (ECal) system
MOST
allocated
6 М $

## Slide 29
First Physics with MPD
Preparation of the report on expected physics results on the first run of MPD
Initial running plan for the NICA Complex (beam types, collision energies)
Status of the readiness of the MPD detector subsystems
Calibration and computing readiness
Selection of physics observables with largest discovery potential for the initial data sample
Schedule for preparation of first scientific publications from MPD data

## Slide 30
COLLABORATION AGREEMENT with:
National Autonomous University of Mexico,
  Institute fir Nuclear Science;
Benemerita Autonomous University Puebla;
Research & Advanced Studies Center;
University of Colima;
Autonomous University of Sinaloa.
Agreement was signed with 5 Mexico Universities
11 October 2019

## Slide 31
NICA days in Warsaw, 21-21 October, 2019
21 October 2019 г. Memorandum was signed by 5 Polish insoftitutions participation in the MPD:
Jan Kochanowski University;
National Centre for Nuclear Research (NCBJ), Otwock;
University of Wroclaw, Wroclaw;
Warsaw University of Technology, Warsaw;
University of Warsaw.

## Slide 32
Helmholtz-Wintergespräche, Moscow, 7 February 2020
GSI coordinates German institutions participation
in the NICA Project
GSI-JINR Agreement
Got Green Light
and parties exchanged
signed documents
contribution ~ 20 М Евро

## Slide 33
Objects
Infrastructure:
Collider building (#17)
Engineering
Area for applied research
applied research area
NICA center
NICA Center
Computing
Notes: This is a view of major NICA facilities. The Nuclotron – supercoducting synchrotron with circumference of 250 meters was put in operation 24 years ago. The beams from Nuclotron are extracted to the experimental hall, where the first experiment of NICA program BM@N is located. The plan is to put in operation a booster in 2019, and collider - in 2020 simultaneously with the MPD.

## Slide 34
BM@N
Collider building (№ 17) civil construction
MPD
SPD
Construction completion– December 2020
August 2019
tunnel – preparation for equipment installation
MPD
MPD
Staging in object commissioning:
MPD - March ’20
Collider – July ‘20;
Supplement to the Agreement
with the General Contractor №5:
Draft is prepared; negotiation stage
Plan to sign in March 2020
Notes: The civil construction of the collider complex is going on in accordance with the plans. the MPD hall will be ready by the summer of 2018, and the entire complex will be completed in 2019.

## Slide 35
BM@N
Power substations 6 kV
MPD
SPD
August 2019
5 for collider: 11 МW
1 for CCS: 11 МW
1 for bld. 205: 8 МW
№15
Notes: The civil construction of the collider complex is going on in accordance with the plans. the MPD hall will be ready by the summer of 2018, and the entire complex will be completed in 2019.

## Slide 36: Cryogenics
Compressor
station 4,4 MW
1000 l/h He liquifier
Cryogenic-compressor station
40 м3 резервуар д/жидкого гелия
500 kg/h nitrogen recondenser RA-0.5
Two recondensers RA05
- are produced
3 satellite
refrigerators
- to be mounted
Completion in 2020
Power in cold will be
more that doubled
from 4 kW to 10 kW at 4.5K

## Slide 37
NICA Center: general designer ООО ПИ «Арена»
Plan:
State Expertise in 2020

## Slide 38: NICA Computing and networks
Data storage:
2017: 1 PB RAW /year
- plan: 10 PB RAW /year
Fast disk memory
of the super computer
«Говорун»
LIT

## Slide 39
LHEP off-line cluster
- запput in operation on 19 September 2019
3000 cores,
upgraded up to 5000;
3,5+3,5 PB disk memorty

## Slide 40
Project schedule
and funding issues
Notes: Few words on the NICA …

## Slide 41
Agreement between
the RF Government
and JINR
signed on June 2-nd 2016
2022
The NICA Project is being implemented in accordance with
the JINR 7-year plans in 2010-2016 and
in 2017- 2023: 237,9 M$
The RF Government Decree
updated in
the National Project “Science”
with the allocation of the necessary funding (+ 5,6 BRub)
the beginning of international scientific research
at a scientific facility of the "mega-science" class:
NICA Complex
allocation of
initial funding (8,8 B Rub)

## Slide 42
17.1.1 | Mounting of the accelerator complex including SC Booster synchrotron and collider | 20.12.21 | Act of completion sent to the MES
17.1.2 | Construction of the experimental set-ups (MPD, BM@N, SPD ) | 01.06.24 | Act of completion sent to the MES
17.1.3 | Construction of the engineering infrastructure | 01.10.22 | Act of completion sent to the MES
17.1.4 | Construction of computer complex | 01.10.21 | Act of completion sent to the MES
17.1.5 | Construction of infrastructure for applied research | 01.12.21 | Act of completion sent to the MES
17.1 | Start of the scientific researches | 25.12.22 | Report sent to the MES
Updated JINR – RF Agreement
(completion dates and report forms)

## Slide 43
Project office
Machines
Project management and expertise structure
Project Leader
Civil construction
Detectors
BM@N
MPD
SPD
Computing
& network integration
Engineering
infrastructure
Supervisory Board
JINR and RF
Coordination Committee
Project Directorate
RRB
COLLABORATIONS
Chief Engineer
Cost & Schedule Review Committee
PROJECTS
IB Boards
DACs
MAC
JINR SC
PFO
Legal off.
Procure-t
Accoun-ting off.
services
PAC
JINR CP
stockholders
expertise
management
Applied research
infrastructure
SB
EC
User
Committee

## Slide 44
The TDR’s of the Accelerator complex
and both detectors BM@N and MPD have been completed in 2012
Three international committees were created to expertise the project:
Machine Advisory Committee
Detector Advisory Committee for MPD
Detector Advisory Committee for BM@N
It was decided to implement the project in two stages:
Stage I (Basic Configuration) - allowing to start BM@N and MPD experiments at reasonable conditions (beam species and luminosity);
Stage II – to reach the design parameters of collider in luminosity,
and detectors in acceptances and resolutions.
The Project Stage I cost was estimated
as 17 500 M Rub in 2013 prices (~ 550 M$)
= 28 158,9 M Rub (~ 456,1 M$) in current prices
approved by the JINR PC & SB in March 2019
The committee recommendations initiated a significant modernization of the project to achieve the required competitiveness.

## Slide 45
№ | objects | completion | CB | Spent + commitments
1 | Accelerator complex including Booster and Collider | 20/12/22 | 144,9 | 80,0
2 | Detectors (BM@N, MPD, SPD) | 01/06/24 | 91,1 | 70,1
3 | Engineering infrastructure | 01/10/22 | 187,8 | 184,2
4 | Computing | 01/10/21 | 18,4 | 11,2
5 | Infrastructure for applied researches | 01/12/21 | 13,9 | 2,0
 | total |  | 456,1 | 347,5
M $
Key financial table with some redistribution between 5 blocks
for the implementation of the project Complex NICA Stage I
approved by the SB (Dec. 2019)

## Slide 46
The project cost (Stage 1) has been updated twice,
each time approved by the SB:
M $
2013 initial version (in 2013 prices) ~ 550
2019 (Feb) update due to change of currency rate
within the same project value 456,1
2019 (Dec) reallocation of object costs to free up
too tight limits on the infrastructure 456,1
2013
New Project
of bld. 17
State
Expertise
2015
Gen. Contractor
~ 3 800 M Rub
Contract
Signed
Gen. Contractor
~ 7 000 M Rub
Updated Contract
to be Signed
Project
of bld. 17
State
Expertise
2019
2020
2016
JINR - RF
Agreement
Signed
project development under the supervision of MAC and DAC
has led to the essential expansion of the civil construction

## Slide 47
Progress in 2014 – 2019 and plans (EVM diagram)
256 332,1 k$
deadline
initial plan
current plan
plan
procurement
work done

## Slide 48
Conclusions
Construction plans for key blocks of the NICA project,
indicated in the JINR 7-year plan and in the JINR-RF Agreement,
have been updated in the National project "Science"
Work on the project is carried out in accordance with the updated plans; one of the key milestone - the Booster commissioning,
will be implemented in 2020
The NICA project has been widely recognized
by the international scientific community
and has attracted participants from all over the world
To achieve the required competitiveness, the NICA project
has been substantially modernized since its approval
It is proposed to adopt and approve NICA project implementation
plans specified in the national project “Science”

## Slide 49
“When it seems to you that the goal is unattainable, do not change the goal - change your plan of action.”
Confucius.
Thank you