## Slide 1
A.Sidorin for the AD team
PP PAC, JINR, Dubna, 3-4 February 2020
Progress towards realization of the Nuclotron-NICA project
A.Sidorin, on behalf of the team

## Slide 2
Status of the Booster assembly and commissioning
- HILAc-Booster transport line
- Cryo-magnetic system
- Plans of the commissioning works
Contents
Preparations for the Collider assembly

## Slide 3
Booster 3D view
E-cooling system
Measurement period
Nuclotron
Injection system
Power supply
Accelerating station
Extraction system
Booster
BNBTL

## Slide 4
HILAc-Booster Beam Transport Line
Mounting was finished in July
transport with minimal ion losses
debunching
matching
Separation and adsorption of neighbor charge states of ions.
Provide different schemes of the beam injection into the Booster.

## Slide 5
HILAc-Booster transport line
October:
preparation for commissioning
December:
commissioned

## Slide 6
The booster tunnel cross section
Booster
Booster Cryo-magnetic system

## Slide 7
First dipole magnet was installed in SFT yoke in September 2018
Booster Cryo-magnetic system

## Slide 8
Time-schedule
Booster
Booster (25 Tm)
up to 578 MeV/u
Apr-May 2019 –
technological run
Oct-Nov 2019
- commissioning with the beam
S.Kostromin, PP PAC 20.01.2019

## Slide 9
Regular period
Quadrupole doublet
Dipole module
Dipole module
Beam chamber
Booster Cryo-magnetic system
Lenses
Pick-up
Corrector

## Slide 10
Booster Cryo-magnetic system
Pick-up stations were purchased in FMB (Berlin):
term of delivery – October 2018,
first serial pick-up was transferred to Dubna in May 2019
During cryogenic tests at a few lenses were measured
displacement of optical axis (up to 0.5 mm) after cycle of cooling and heating
The reason: displacement of the winding inside the yoke
All 24 blocks were reassembled with more strong fixation of the windings
and passed through the cryogenic tests again
Now all the magnets are at the ring

## Slide 11
First warm gap
Electrostatic septum
Injection channel from HILAC
Kicker
Quadrant I
Quadrant IV
Bypass
Booster injection system

## Slide 12
Vacuum test of electrostatic septum
• Cryosystems/HiVac companies
Booster injection septum

## Slide 13
Electrostatic kicker
• BEVATECH/PINK companies
Booster injection kicker

## Slide 14
RF tanks
Second warm gap
Pump stations
Booster acceleration stations + Measurement period

## Slide 15
Testing of accelerating stations
• Budker Institute of Nuclear Physics
Booster acceleration stations

## Slide 16
Booster acceleration stations

## Slide 17
Booster acceleration stations

## Slide 18
Elements of Power supply system

## Slide 19
Room in the basement
Elements of Power supply system

## Slide 20
Third warm gap
Extraction channel to Nuclotron
Quadrant II
Quadrant III
Kicker
Septum 1,2
Pickup
Bypass
Booster Extraction system
Booster fast extraction system
The kicker and septum will be delivered from BINP at the end of February

## Slide 21
Booster fast extraction system
Assembly of the bypass

## Slide 22
22
4-th warm gap
Booster electron cooling system

## Slide 23
Booster electron cooling system
Budker Institute of Nuclear Physics

## Slide 24
Control rack of correctors
Measuring rack of BPM and thermometry
Control rack of vacuum system
Booster Control and diagnostic systems

## Slide 25
Booster vacuum system

## Slide 26
Booster commissioning
23 December official start of the booster commissioning:
Tuning of power supply and test of energy evacuation system
on equivalent load
Quadrant by quadrant test of vacuum system
(In parallel: assembly of measurement period)
Cooling of cryo-magnetic system, test of thermometry
and quench detectors
Test of cryo-magnetic system with current
(In parallel: Completion of the beam pipe assembly)
- Test with ion beam (May - June 2020)

## Slide 27
Booster commissioning

## Slide 28
Booster-Nuclotron transport line
under contract with BINP
Channel delivery
September 2020
beam transport with minimal ion losses
Separation of neighbor charge states.
Stable operation of the Booster and Nuclotron together
depends on compressor power

## Slide 29
This summer (depending on building completion):
Mounting dipole magnets of the Collider first arc section
Assembly of the Nuclotron-Collider beam transport line
Mounting of RF-1 stations
Plans for the collider assembly

## Slide 30
Collider barrier bucket
Tested at BINP, transported to JINR in January 2020

## Slide 31
According to request of the Machine Advisory Committee
Interim report on NICA project progress (under edition by I. Meshkov)
prepared in January 2020
http://nucloweb.jinr.ru/nica/MAC/20Jan16_Rpt_to_MAC.pdf

## Slide 32
Thank your for attention