## Slide 1: NICA Booster: status of mounting preparation
NICA Machine Advisory Committee,
meeting at Joint Institute for Nuclear Research, Dubna, Russia
June, 7-8, 2018
A. Galimov

## Slide 2
Scheme of the booster
Assemblies | Q-ty, pcs
Dipoles | 40
Quadrupole doublets | 24
Kit for assembling magnet joints | 45
Bypass for coolant liquid | 2
Warm sections | 4
Section with reference magnet (L, R) | 2
Feed box (L, R) | 2
Vacuum stations (insulation volume) | 26
Vacuum stations (cold beam pipe) | 24

## Slide 3
Booster assembling (time-schedule)
Booster assembling |  | 2018 |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  | 
 |  | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI
“Cold” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Bypasses and ends |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Reference magnets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
“Warm” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | E-cooling |  |  |  | - commissioning |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Injection section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Beam extraction section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Accelerating station |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Systems assembling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Vacuum system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Power supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Cryogenic system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Thermometry system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Technological commissioning
Commissioning
with beam

## Slide 4
approved documentation (schemes, layouts, instructions, flow charts, etc.) geodetic network - ready; bridge cranes of build - ready; energy supply (380/220V, 50Hz); water system (cooling equipment); movable clean zones for beam pipe and vacuum stations assembling; instruments (helium leak testers, movable pumping stations, laser tracker tools and etc.); interior of Booster tunnel and b.1 completion (floor, walls, light and etc.); compressed air system 6 bar (suppling equipment); storing places of complete products; places for preparing units and element; places for staff; tailored logistics | Status in hand ready; ready; in hand in hand in hand ready in hand in hand in hand in hand in hand in hand
Documentations and engineer systems

## Slide 5
The booster tunnel cross section

## Slide 6
Required equipment and instruments
Laser tracker
Mobile clean zone
Leak detectors

## Slide 7
The typical joint (dipole-dipole assembling)
Dipole unit
Bellows hoses
Bus-bars
Dipole unit
Supports
Beam pipe

## Slide 8
Dipole-dipole joint
Thermal shield
Vacuum chamber

## Slide 9
Regular periods
Quadrupoles unit
Dipole unit
Dipole unit

## Slide 10: Arrangement of Booster dipole magnets
The arrangement of Booster dipole magnets in tunnel is done. The best way for bending magnets ranking is to use the pair of magnets with short and long effective length (total amount of this pairs is 20 pcs.).
The closed orbit distortion for bending magnets ranking on injection current 625 A is about 0.45 mm and for extraction current 9745 A and the same ranking this distortion is about 1.6 mm, see figure (right) below.

## Slide 11
Regular period
Assembly workflow (part 1)
Alignment of yoke inside vacuum chamber (2w × 2h × 64m = 256pm (16days)
Transfer magnet on position (3w × 0,5h × 64m = 96pm (4days)
Mounting magnet in tunnel (2w × 0,5h × 64m = 64pm (4days)
Magnet 1
Assembling of He and N2 lines M1-M2 (2w × 1h × 60m = 120pm (8days)
Assembling of He and N2 headers M2-M3
Soldering of bus-bars M1-M2 (1w × 4h × 60m = 240pm (30 days)
Soldering of bus-bars M1-M2
Alignment in position (2w × 2h × 64m = 256pm (16days)
Magnet 2
Magnet 3
1
2
3
4
5
6

## Slide 12
Quadrant
Regular period 1
Regular period 2
Regular period 3
Regular period 4
Regular period 5
END1
END2
Mounting insert between the beam pipes (2w × 2h × 60joints = 240pm (8days)
Mounting turbo-pump stations (2w × 4h × 8 stations= 32pm (8days)
Transfer unit on position and mounting
Transfer unit on position and mounting
Assembling of He and N2 headers END1-1-2-3-4-5-END2
Soldering bus-bars END1-1-2-3-4-5-END2
Helium leakages tests of manifolds connections (2w × 1h × 60joints = 120pm (4days)
Assembly workflow (part 2)
7
8
9

## Slide 13
Quadrant
Regular period 1
Regular period 2
Regular period 3
Regular period 4
Regular period 5
END1
END2
Helium leakages tests of beam pipe connections (2w × 16h × 12 time= 384pm (24days)
Thermal shield and nitrogen manifolds assembly (2w × 2h × 60 time= 240pm (24days)
Electrical tests (2w × 2h × 4 time= 16pm (1days)
Vacuum shell assembly (2w × 3h × 60 joints = 300pm (19 days)
Pump and helium leakages tests (2w × 24h × 4 quadrants = 196pm (16 days)
Electrical tests under vacuum (2w × 1h × 4 quadrants = 8pm)
Pumping of beam pipe (2w × 56h × booster = 112pm (5 days))
Mounting insulation volume vacuum system (2w × 8h × 26 stations = 416pm (26 days)
Assembly workflow (part 3)
10
11
12
13
14
15
16
17
Notes: probability

## Slide 14
Step of workflow | Magnet mounting, vacuum chamber and nitrogen shield assembling | Leakage test, beam pipe and He manifold flange assembling | Alignment | Soldering and voltage test | Сrane operator
1 | 128 |  | 128 |  | 
2 | 64 |  |  |  | 32
3 | 64 |  |  |  | 
4 |  | 120 |  |  | 
5 |  |  |  | 240 | 
6 | 128 |  | 128 |  | 
7 |  | 120 |  |  | 
8 |  | 240 |  |  | 
9 |  | 32 |  |  | 
10 |  | 384 |  |  | 
11 | 240 |  |  |  | 
12 |  |  |  | 16 | 
13 | 300 |  |  |  | 
14 |  | 416 |  |  | 
15 |  | 196 |  |  | 
16 |  |  |  | 8 | 
17 |  | 112 |  |  | 
SUM (≈3100) | 924 | 1620 | 256 | 264 | 32
Man powers for regular periods

## Slide 15
Bypass unit of I and III warm sections
Quadrupole unit
Quadrupole unit
Cold-warm section
Cold-warm section
Transfer tube
15
All-metal gate
All-metal gate

## Slide 16
Cold-warm section assembling
All-metal gate
Pick-up station
Helium channels
Quadrupole doublet magnet
Beam pipe
Nitrogen channels
Vacuum chamber

## Slide 17
Power supply, reference magnet and acceleration station area
Booster
Reference magnets
Power supply
device

## Slide 18
Section with reference magnet
Feedbox “R”
Feedbox “L”
Cryogenic feeder “L”
Cryogenic feeder “R”
Booster “2”
Accelerating stations
Reference magnet
Reference magnet
Platform

## Slide 19
Bypass 1,2 (6w × 80h = 224pm (10days)
Irregular periods assembly workflow
10
Booster assembling |  | 2018 |  |  |  |  |  |  | 
 |  | V | VI | VII | VIII | IX | X | XI | XII
“Cold” sections |  |  |  |  |  |  |  |  | 
 | Quadrant 1 |  |  |  |  |  |  |  | 
 | Quadrant 2 |  |  |  |  |  |  |  | 
 | Quadrant 3 |  |  |  |  |  |  |  | 
 | Quadrant 4 |  |  |  |  |  |  |  | 
 | Bypasses |  |  |  |  |  |  |  | 
 | Reference magnets |  |  |  |  |  |  |  | 
Reference magnets and feed boxes (6w × 96h = 328 pm (14 days)
Pump and helium leakages tests (2w × 60h = 120pm (5 days)
Technological commissioning (10 days)
18
19
20
21
Notes: probability

## Slide 20
Step of workflow | Magnet mounting, vacuum chamber and nitrogen shield assembling | Leakage test, beam pipe and He manifold flange assembling | Alignment | Soldering and voltage test | Сrane operator
1-17 | 924 | 1620 | 256 | 264 | 32
18 | 160 | 32 |  | 16 | 16
19 | 224 | 48 |  | 32 | 24
20 |  | 120 |  |  | 
SUM ≈3800 mp | 1308 | 1820 | 256 | 312 | 72
Managers, engineers and workers (4 months or 120 days or 960 hours, 8h/day) |  |  |  |  | 
Technicians (7+6) | 1,4 (2+1) | 1,8 (2+2) | 1+1 | 1+1 | 1+1
Engineers (1+1) | 1+1 |  |  |  | 
Managers | 1 |  |  |  | 
Man powers for booster cold part assembling
Notes: contain

## Slide 21
Thank you for attention