## Slide 1
BEAM TRANSFER CHANNELS,
INJECTION AND EXTRACTION SYSTEMS –
STATUS OF CONSTRUCTION
Tuzikov A.
on behalf of JINR team

## Slide 2
NICA beam transfers
Beam transfer from HILAC to Booster
HILAC-Booster transport channel;
Booster injection system.
Beam transfer from Booster to Nuclotron
Booster fast extraction system;
Booster-Nuclotron transport channel;
Nuclotron high energy beam injection system.
Beam transfer from Nuclotron to Collider
Nuclotron fast extraction system;
Nuclotron-Collider transport channel;
Collider injection system.
Beam dump from Collider
Collider beam dump system.
NICA MAC 2018

## Slide 3
Beam transfer from HILAC to Booster
Goals
Accumulation of required intensity of ions in Booster by means of several methods of beam injection.
Commissioning: March 2019
Beam parameters
Ions | Au31+
Energy, MeV/u | 3.2
Magnetic rigidity, T m | 1.6
Electric rigidity, MV | 40
Ion number | 2∙109
HILac
Booster
NICA MAC 2018

## Slide 4
The beam transport with minimal ion losses.
The beam debunching.
The beam matching.
Separation and adsorption of neighbor charge states of ions.
Providing different schemes of the beam injection into the Booster.
Main goals
HILAC-Booster beam transport channel
Beam transport in the median plane of the Booster.
The debuncher in non-dispersive region of the beam transport channel.
Features
NICA MAC 2018

## Slide 5
Composition
HILAC-Booster beam transport channel
NICA MAC 2018

## Slide 6
HILAC-Booster beam transport channel
Beam dynamics
Separation
Beam envelopes
Horizontal and vertical acceptances of the channel are equal to 39 and 31 π·mm·mrad correspondingly.
Reducing from 5·10-3 to 1·10-3 by means of the beam debunching.
NICA MAC 2018

## Slide 7
Parameters of main elements
HILAC-Booster beam transport channel
Quadrupoles
Effective length, m | 0.29 / 0.21
Max gradient, T/m | 10 / 19
Gap (diameter), mm | 95 / 71
Dipoles
Effective length, m | 0.65
Max field, T | 1
Gap, mm | 45
Steerers
Effective length, m | 0.25
Max field, T | 0.05
Gap, mm | 125 × 110
NICA MAC 2018

## Slide 8
Parameters of main elements
HILAC-Booster beam transport channel
Debuncher
Designed and fabricated by Bevatech team
Inner length, m | 0.49
Frequency, MHz | 100.625
Max effective voltage, kV | 260
NICA MAC 2018
Status of channel equipment
Power supplies are being assembled.
Beam diagnostics is purchased partially. Full set of beam diagnostics will not be purchased until the channel commissioning.
First part of vacuum equipment is ordered. Full set of vacuum equipment will be purchased in the nearest future.
Design of stands is near completion.

## Slide 9
IP1
ESS
IP2
IP3
The beam injection with minimal ion losses.
The beam injection by the following methods: single-turn injection, multiturn injection, multiple injection.
Goals
Booster injection system
Accumulation of ions in horizontal phase plane.
Closed orbit bump (for multi-turn and multiple injections).
Rapid change of fields in the system elements (for more compact filling of the horizontal phase plane in case of multi-turn and multiple injections).
Features
NICA MAC 2018

## Slide 10
Parameters of elements
 | Length, m | Gap, mm | X1, mm | X2, mm | Max voltage, kV
IK1 | 0.5 | 100 | -50 | +50 | 40
IK2 | 0.8 | 93 | -36 | +57 | 50
IK3 | 0.5 | 100 | -50 | +50 | 60
IES | 1.9 | 35 | [+38; +195] | [+73; +230] | 125
Booster injection system
Electrostatic septum ESS
NICA MAC 2018
Under fabrication
Delivery this autumn

## Slide 11
Electric injection kickers IP1, IP3
Booster injection system
NICA MAC 2018
Electric injection kicker IP2
IP2 is under fabrication and will be delivered this autumn.
Power supplies of IP2 is out of start-up configuration.
IP3 manufacturing is being ordered.
IP1 will be manufactured and installed on 2019.
Main power supply of IP3 has been manufactured.
Power supply of IP1 and additional power supply of IP3 is out of start-up configuration.

## Slide 12
Goals
Transfer of the beam with parameters which can be altered in wide ranges due to 1) use of different schemes of beam injection into Booster and 2) use of an electron cooling system.
Ion stripping to a maximum charge state.
Commissioning: November 2019
Ions: before stripping station after stripping station | Au31+ Au79+
Maximum magnetic rigidity of ions, T m: before stripping station after stripping station | 25 10
Ion number | 1.5∙109
Beam Parameters
Beam transfer from Booster to Nuclotron
Booster
Nuclotron
NICA MAC 2018

## Slide 13
Booster fast extraction system
NICA MAC 2018
Beam extraction

## Slide 14
Length, m | 1.5
Max magnetic field, T | 0.18
Bending angle, mrad | 10
Pulse duration, μs: rise plateau | 0.5 0.5
Booster fast extraction system
Kicker
NICA MAC 2018
Kicker and power supplies are under fabrication by BINP.

## Slide 15
Septa (two sections)
Booster fast extraction system
Length, m | 0.4; 1.4
Max magnetic field, T | 0.544; 1.3
Bending angle, mrad | 22.2; 185
Pulse shape | semisinusoidal
Pulse duration, μs | 80; 1200
NICA MAC 2018
Septa and power supplies are under fabrication by BINP.

## Slide 16
Booster fast extraction system
Closed orbit bump subsystem
NICA MAC 2018
Power supplies and current leads will be purchased this summer.
PS number / dipole magnets | Nominal beam deflection angle in dipole doublet, mrad | Nominal current, A | Max current, A
1 / 2М5А-2М5B | 1.55 | 49 | 150
2 / 2М6А-2М6B | 3.6 | 115 | 150
3 / 3М2А-3M2B | 3.48 | 111 | 150
4 / 3М3A-3M3B | 1.79 | 57 | 150

## Slide 17
Goals
The beam transport with minimal ion losses.
Separation of neighbor charge states. Estimates of ion stripping at energy of 580 MeV/u: 100% Au31+ → 80% Au79+, ~20% Au78+. Due to high intensity of Au78+ ions they have to be extracted from the channel to an absorber.
Booster-Nuclotron beam transport channel
View from above
Side view
NICA MAC 2018

## Slide 18
Booster-Nuclotron beam transport channel
3D model
NICA MAC 2018
Composition

## Slide 19
Booster-Nuclotron beam transport channel
Beam dynamics
NICA MAC 2018

## Slide 20
Booster-Nuclotron beam transport channel
Parameters of magnetic elements
Magnetic element | Type | Effective length, m | Max. magnetic field (gradient), T (T/m)
BM1 – BM5 | sector dipole | 1.95 | 1.58
SEPT_2 | septum | 1.4 | 1.3
Q1 – Q4 | quadrupole | 0.4 | 14
Q5 – Q8 | quadrupole | 0.4 | 20
Corr1 – Corr3 | steerer | 0.1 | 0.15
NICA MAC 2018
Being designed by BINP team

## Slide 21
Nuclotron high energy beam injection system
Composition
NICA MAC 2018

## Slide 22
Lambertson magnet
NICA MAC 2018
Length, m | 1.5
Max magnetic field, T | 1
Septum thickness, mm | 7
Power supply | DC
Lambertson magnet is based on existing spare yoke for slow extraction system of Nuclotron.
Yoke modification is in progress.
Manufacturing of superconducting coils and the cryostat, purchase of power supplies is not started yet.
Nuclotron high energy beam injection system

## Slide 23
Kicker
NICA MAC 2018
Nuclotron high energy beam injection system
Length, m | 2
Max magnetic field, T | 0.1
Max current, kA | 15
Aperture, mm×mm | 86 × 44
Pulse duration, μs: rise plateau fall | free ≥ 0.5 ≤ 0.5
Development of design of a cold kicker is in progress.
Warm prototype for mechanical tests has been manufactured.
Conceptual design of power supplies is under development.

## Slide 24
Beam transfer from Nuclotron to Collider
Goals
Accumulation of required intensity of ions (with help of barrier bucket system and beam cooling systems of Collider).
Commissioning: June 2020
Ions | Au79+
Energy of ions, GeV/u | 1 ÷ 4.5
Magnetic rigidity of ions, T m | 14 ÷ 45
Ion number | 1∙109
Beam Parameters
NICA MAC 2018

## Slide 25
Nuclotron fast extraction system
NICA MAC 2018
Beam extraction
The beam shift to the septum by means of RF system: = 8.5·10-3.
The kick in horizontal plane: angle 8 mrad.
The beam deflection in vertical direction: angle 83 mrad.

## Slide 26
Nuclotron fast extraction system
Kicker
Length, m | 3
Max magnetic field, T | 0.13
Max current, kA | 20
Pulse duration, μs: rise plateau fall | ≤ 0.55 ≥ 0.2 free
NICA MAC 2018
Concept of the kicker and its power supplies has been developed.
Kicker prototype has been manufactured and tested.

## Slide 27
Nuclotron fast extraction system
Lambertson magnet (two sections)
Length, m | 1.5; 1.5
Max magnetic field, T | 1; 1.5
Septum thickness, mm | 5; 10
Power supply system | cyclic, serial to dipole magnets
NICA MAC 2018
Lambertson magnets are based on existing spare yokes for slow extraction system of Nuclotron.
Concept has been developed only.

## Slide 28
Goals
Nuclotron-Collider beam transport channel
The beam transport with minimal ion losses.
The beam matching with lattice functions of the Collider rings (except vertical dispersion).
NICA MAC 2018

## Slide 29
Layout
Nuclotron-Collider beam transport channel
NICA MAC 2018
Composition

## Slide 30
Beam dynamics (North Branch)
Nuclotron-Collider beam transport channel
NICA MAC 2018
Horizontal and vertical acceptances of the north branch of the channel are equal to 13 and 10 π·mm·mrad correspondingly.

## Slide 31
Beam dynamics (South Branch)
Nuclotron-Collider beam transport channel
NICA MAC 2018
Horizontal and vertical acceptances of the south branch of the channel are equal to 13 and 10 π·mm·mrad correspondingly.

## Slide 32
Parameters of pulsed magnet elements
Nuclotron-Collider beam transport channel
Magnetic element | Number | Effective length, m | Max. magnetic field (gradient), T (T/m)
Long dipole | 21 | 2 | 1.5
Short dipole | 6 | 1.2 | 1.5
Quadrupole Q10 | 22 | 0.353 | 31
Quadrupole Q15 | 6 | 0.519 | 31
Steerer | 33 | 0.466 | 0.114
Designed by SigmaPhi
NICA MAC 2018

## Slide 33
Collider injection system
NICA MAC 2018
Beam injection

## Slide 34
Septum
34
NICA MAC 2018
Collider injection system
Length, m | 2.5
Max magnetic field, T | 1
Aperture, mm×mm | 45×45
Septum thickness, mm | 3
Pulse shape | semisinusoidal
Pulse duration, μs | ~ 10
Technical design development is in progress.
Concept of power supply has been developed.

## Slide 35
Collider injection system
Kicker
NICA MAC 2018
Length, m | 4.5
Max magnetic field, T | 0.1
Pulse duration, ns: rise plateau fall | 200 200 200
After-kick amplitude, plateau level | ≤1.5%
After-kick duration, ns | ≤160
Concept of the kicker and its power supplies is under development.
Effects of after-kicks to the stack are estimated. Concept of measures against after-kicks has been developed.

## Slide 36
Beam dump directions
Collider beam dump system
NICA MAC 2018

## Slide 37
Beam dump from upper ring
Collider beam dump system
NICA MAC 2018

## Slide 38
Beam dump from lower ring
Collider beam dump system
NICA MAC 2018

## Slide 39
Beam dump from upper ring
Collider beam dump system
NICA MAC 2018
Beam dump from lower ring

## Slide 40
Kickers
Collider beam dump system
NICA MAC 2018
Septa
Lambertson magnet
Absorbers

## Slide 41
THANK YOU FOR ATTENTION