## Slide 1
Progress towards realization of the Nuclotron-NICA project

## Slide 2
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Booster (25 Tm)
1(2-3) single-turn injection,
storage of (2  4)×109 ions,
acceleration up to 100 MeV/u,
electron cooling, acceleration
up to 600 MeV/u
Linac HILac
KRION
IP-1
IP-2
Stripping (80%) 197Au31+ => 197Au79+
KRION
Linac HILAc
Booster (25 Tm)
1(2-3) single-turn injection,
storage of (2  4)×109 ions,
acceleration up to 100 MeV/u,
electron cooling, acceleration
up to 600 MeV/u
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Slow resonance extraction
Collider
L ≥ 1027 см-2с-1
2015-2018
work in progress
assembly
commissioned / existing
Facility components – status

## Slide 3
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Booster (25 Tm)
1(2-3) single-turn injection,
storage of (2  4)×109 ions,
acceleration up to 100 MeV/u,
electron cooling, acceleration
up to 600 MeV/u
Linac HILac
KRION
IP-1
IP-2
Stripping (80%) 197Au31+ => 197Au79+
KRION
Linac HILac
Booster (25 Tm)
1(2-3) single-turn injection,
storage of (2  4)×109 ions,
acceleration up to 100 MeV/u,
electron cooling, acceleration
up to 578 MeV/u
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Slow resonance extraction
Collider
L ≥ 1027 см-2с-1
2019
Facility components – status
work in progress
assembly
commissioned / existing

## Slide 4
Linac HILac
KRION
KRION
Linac HILAc
Booster (25 Tm)
up to 578 MeV/u
Nuclotron (45 Tm)
up to 4.5 GeV/u
Injection - chain
for heavy ions
Heavy ion source KRION ESIS type project up to 1.5·109 Au31+ particles per cycle (achived 5·108 Au31+ )
at repetition frequency up to 10 Hz
Overall commissioning
3.2 MeV/u, Au31+, 10.2016

## Slide 5
Linac HILac
KRION
KRION
Linac HILAc
Booster (25 Tm)
up to 578 MeV/u
Nuclotron (45 Tm)
up to 4.5 GeV/u
Injection - chain
for heavy ions
17.01.19
Booster - Nuclotron
channel contracted to BINP
commissioning at end of 2019
HiLac – Booster
channel
mounting started

## Slide 6
Linac LU-20
Ion sources
Nuclotron (45 Tm)
up to 4.5 GeV/u
Linac LU-20
Ion sources
Injection - chain
for light ions
New fore-injector for LU-20 with buncher + Source of Polarized Ions
 | Polarized deutrons | Polarized protons
Obtained beam current in 2017 (source) | 2 mA | 0.4 mA
Project beam current (source) | 5-6 mA | 5-6 mA
Obtained beam intensity in 2017 (Nuclotron) | 2.2x109 ppc | 1.8x108 ppc
Project beam intensity (Nuclotron) | 1-2x1010 ppc | 1-2x1010 ppc
3 runs in 2016-2017 (#52-54) with d↑, 1 run (#54) with stable p↑ beam
JINR, INR, ITEP, MEPHI,
Resonator is fabricated in Sneshinsk
1.8 E8
Polarized protons

## Slide 7
Time-schedule
Booster
Booster (25 Tm)
up to 578 MeV/u
Apr-May 2019 –
technological run
Oct-Nov 2019
- commissioning with the beam

## Slide 8
Booster dipoles
Leff. @ 9745 A
σrms = 2.3*10^(-4)
Leff. @ 625 A
σrms = 4*10^(-4)
Booster quadrupoles
Testing results

## Slide 9
Booster
Booster (25 Tm)
up to 578 MeV/u
17.01.19
20 dipoles’ units delivered to the tunnel

## Slide 10
Routine operation of SPI and new fore-injector
Polarized deuterons acceleration: Intensity up to 2*109 per cycle
8E8
Nuclotron: polarized deuterons and protons
12C+6 beam extraction (3,5 Gev/u) RUN #55 (05.02.18-05.04.18)
12C+6 5*108 Tspill = 4s, kdc= 99,5%
Nuclotron: slow extraction
Acceleration of 197Au79+ up to 4.5 GeV/u
Injection system for 197Au79+ from Booster at 578 MeV/u
Slow extraction system for 197Au79+ at 1  4.5 GeV/u
Nuclotron: tasks
for 2020

## Slide 11
Nuclotron (45 Tm)
up to
4.5 GeV/u max.
Lambertson magnets are based on existing spare yokes for slow extraction system of Nuclotron
Concept has been developed
Nuclotron high energy beam injection system
11
Design of a cold kickers is in progress
Warm prototype for mechanical tests has been manufactured
Nuclotron fast extraction system

## Slide 12
Magnetic element | Number | Effective length, m | Max. magnetic field (gradient), T (T/m)
Long dipole | 21 | 2 | 1.5
Short dipole | 6 | 1.2 | 1.5
Quadrupole Q10 | 22 | 0.353 | 31
Quadrupole Q15 | 6 | 0.519 | 31
Steerer | 33 | 0.466 | 0.114
Magnets of the Nuclotron-Collider channel are in development by SigmaPhi.
Nuclotron-Collider beam transport channel

## Slide 13
NICA Collider
Nuclotron magnets’ technology
Racetrack of 503.04 m circumference
2 Interaction points
0.32 m vertical beam separation
double-aperture sc-magnets with 1.8 T max field
45 T·m magnetic rigidity
ion kinetic energy range from 1 GeV/u to 4.5 GeV/u for Au79+
vacuum: 10−9 Pa;
Average luminosity 1027 cm−2·s−1 for gold ion collisions at √sNN = 9 GeV.

## Slide 14
Collider
+ RF-2 systems in the project version
+ RF-3 systems in the project version
+ S-cooling (transverse)
+ E-cooling
1. Injector chain: KRION => Booster => BTL BN => Nuclotron
2. BTL Nuclotron => Collider
3. Collider equipped with
RF-1 (barrier voltage system) for ion storage
RF-2 in a reduced version: 2 cavities per ring instead 4 (50 kV RF amplitude instead 100 kV)
1 channel of S-cooling per ring (cooling of longitudinal deg. of freedom)
Result: 22 bunches of the length   2 m per collider ring that = 5e25 cm-2s-1.
NICA Stage II-a (basic configuration):
NICA Stage II-b (full configuration):
Result: 22 bunches of the length  = -star = 0.6 m per collider ring that = 1e27 cm-2s-1.

## Slide 15
Time-schedule
Collider
IP-1
IP-2
Collider
L ≥ 1027 см-2с-1

## Slide 16
Collider magnets’ system
Assembly and testing
Parameter | Dipole | Lens
Number of magnets | 80+8* | 78+12**
Max. magnetic field (gradient) | 1.8 T | 23.1 T/m
Effective magnetic length | 1.94 m | 0.47 m
Beam pipe aperture (h/v) | 120 mm / 70 mm | 
Distance between beams | 320 mm | 
Overall weight | 1670 kg | 240 kg
*- beams vertical elevation dipoles
**- final focus quadrupoles
178 structural sc-magnets to assemble and test

## Slide 17
SC-magnets to assembly and testing

## Slide 18
NICA Collider magnets testing
26 dipoles’ yokes delivered to JINR
5 dipoles’ successfully passed cryogenic tests
testing results

## Slide 19
RF-system
3D model of RF3 station
RF system for basic configuration is under construction at BINP – 2020
RF system for project configuration is under development at BINP – 2021
RF1 station: preparation for the tests

## Slide 20
Electron Cooling System of NICA Collider, Ions 197 Au79+
HV Electron Cooler for NICA Collider
Design and construction at BINP
Installation at NICA in 2021
together with 4 RF2 and 16 RF3 stations
Parameter | Value
Electron energy, MeV Energy instability, E/E | 0.2 – 2.5  110-4
Electron beam current, A | 0.1 – 1.0
Cooling section length, m | 6.0
Solenoid magnetic field, T Field inhomogeneity, B/B | 0.05 – 0.2  110-5

## Slide 21
Septum
Length, m | 2.5
Max magnetic field, T | 1
Aperture, mm×mm | 45×45
Septum thickness, mm | 3
Pulse shape | semisinusoidal
Pulse duration, μs | ~ 10
Technical design development is in progress.
Concept of power supply has been developed.
Injection-system

## Slide 22
Beam dump system – under designing
Kickers
Lambertson magnet
Septa
Beam-dump system

## Slide 23
24 of Dec 2018 final annual JINR-BINP-ITEP meeting took part at LHEP
Joint work on the NICA collider physics continued

## Slide 24
Thank you

## Slide 25
12C BM@N SRC
40Ar 84Kr BM@N
Run 55: February – April 2018
the first run with startup configuration of BM@N
experiment BM@N SRC
0,5
1,0
1,5
2,0
2,5
3,0
Kr26+
30/03/2018
s
03.04