## Slide 1: Status of the Factory of Super Heavy Elements and the Quality control system for construction of the DC-280 cyclotron
Igor Kalagin
Dubna 2018
FLEROV LABORATORY of NUCLEAR REACTIONS
JOINT INSTITUTE FOR NUCLEAR RESEARCH

## Slide 2: Superheavy Elements (SHE) Factory – the Goals
Experiments at the extremely low (σ<100 fb) cross sections:
Synthesis of new SHE in reactions with 50Ti, 54Cr ...;
Synthesis of new isotopes of SHE;
Study of decay properties of SHE;
Experiments requiring high statistics:
Nuclear spectroscopy of SHE;
Study of chemical properties of SHE.

## Slide 3: SHE Factory
High-current cyclotron DC-280
New facilities:
New gas-filled separator
Preseparator
SHELS
Etc.
SHE Factory Building
Notes: The project of the SHE factory includes three principal components: i) high current accelerator, ii) new experimental hall and iii) a number of the next generation facilities.

## Slide 4
DC-280 cyclotron for stand-alone SHE factory
DC280 (expected) E=4÷8 MeV/A |  | 
Ion | Ion energy [MeV/A] | Output intensity
7Li | 4 | 1×1014
18O | 8 | 1×1014
40Ar | 5 | 6×1013
48Ca | 5 | 0,6-1,2×1014
54Cr | 5 | 2×1013
58Fe | 5 | 1×1013
124Sn | 5 | 2×1012
136Xe | 5 | 1×1014
238U | 7 | 5×1010

## Slide 5
Ion sources | DECRIS-PM - 14 GHz Superconducting ECR (developing stage)
Injection energy | Up to 80 keV/Z
A/Z range | 4÷7
Energy | 4÷8 MeV/n
Magnetic field level | 0.6÷1.3 T
K factor | 280
Gap between plugs | 400 mm
Valley/hill gap | 500/208 mm/mm
Magnet weight | 1000 t
Magnet power | 300 kW
Dee voltage | 2x130 kV
RF power consumption | 2x30 kW
Flat-top dee voltage | 2x14 kV
DC-280
Main Parameters

## Slide 6
DC-280 cyclotron
Autonomous Launching and Tuning Works (LT Works)

## Slide 7
Main RF-resonator
Magnet yoke
HV platform N1
(Umax=70 kV)
Electrostatic deflector
(Bender)
Separating magnet
DECRIS-PM
ECR-source
(Umax=20 kV)
Magnet coils
Ion beam extraction
Flat –top resonator
Vacuum pump
Accelerating tube
Configuration of the DC-280

## Slide 8: Beam injection system
The HV platform (December 2017)
The DECRIS-PM ion source on the platform
Area of the electrostatic deflector (Bender)
Communications under the platform

## Slide 9
Radial trimming coils
Azimuthal trimming coils
Number of radial trimming coils | 11
Number of azimuthal trimming coils | 8
Magnet trimming coils
Checking of magnetic field direction between trimming coils was carried out during Launching and Tuning Works

## Slide 10
RF system
3Frf
Frf
Plating (antidee)
Frf=7.32÷10.38 MHz
Fft=21.96÷31.14 MHz
Platings inside the vacuum chamber
Installation of dee (Feb. 2018)
RF resonator (June 2018)
Plating assembling
RF generators

## Slide 11
Beam extraction system
Electrostatic deflector
Focusing magnetic channel
Extraction radius of Rext=1.79 m
Electrostatic deflector
L=1.8 m, E=90 кВ/сm
Magnetic channel
L=0.9 m, G=4.6÷8.4 T/m
Assembling of the deflector

## Slide 12
Radial current probe, flat-top resonator, extraction channels
Flat-top resonator
Beam transport channels

## Slide 13
Water cooling system
Control and power supply systems
Power supplies of injection
Power supplies of cyclotron

## Slide 14
DC-280 control room

## Slide 15
Plan of the 1-st floor of the SHE Factory
GFS-2
DC-280

## Slide 16: New FLNR gas-filled separator (contracted)
Reaction | Transmission
244Pu(48Ca,3n)289114 | 60 %
244Pu(58Fe,4n)298120 | 75 %
Technical Design
Report No 412923

## Slide 17
Arrangement of GFS-2 at the beam line No3
Installation of magnets: June 2018
Commissioning: Sept. – Oct. 2018
Obtaining licenses and permits : Nov. 2018

## Slide 18
Quality control system for construction of the DC-280 cyclotron
The DC-280 cyclotron was constructed in compliance with the Quality Assurance System under standard GOST R ISO 9001
Project structure management
Types of official documents, procedures for their preparation, processing, storage, and classification
Stages of the DC-280 project implementation
The Quality Assurance System defines:

## Slide 19
The project structure management

## Slide 20
The structure of the DC-280 documentation catalogue

## Slide 21
The DC-280 documentation catalogue

## Slide 22
Calculations, mathematical modelling, analysis of potential engineering proposals, prototyping, configuration of cyclotron complex, and equipment spacing layout
Engineering specifications for the manufacture of products and systems, quality assurance and product acceptance requirements
Test programme, test protocols, product and system passports
Manufacturer provides
on-site quality assurance: post-process quality check monitoring by the Department of Technical Monitoring (DTM); DTM certificates processing; and current on-line process quality control
Acceptance inspection of manufactured products and systems by FLNR representatives
Incoming inspection of products prior to their installation at FLNR
FLNR staff members carry out
testing of products and allied equipment in conditions that correspond to the real ones under which current facilities operate can be done, if necessary.
Installation of products and systems at FLNR
Programmes of Autonomous Launching and Tuning Works (LTWs) for assembled systems, including test programmes of the installed equipment
Autonomous LTWs without ion acceleration. Complex LTW programme for the DC-280
Project documentation sent to the Federal Medical and Biological Agency of Russia (FMBA)
FMBA expert conclusion certificate for the DC-280 cyclotron and permission for complex LTWs
Complex LTWs for the DC-280 cyclotron with the acceleration of testing ions. FMBA dosimetry measurements, sanitary and epidemiological studies
DC-280 cyclotron complex operability certificate
FMBA sanitary and epidemiological conclusion for the approval of works at the DC-280
Act of commissioning of the DC-280 cyclotron
Stages of the DC-280 project implementation
June 2018
September 2018
November 2018

## Slide 23
Protocols, acts, passports, certificates of DC-280 equipment

## Slide 24
Autonomous LTWs of all the DC-280 cyclotron systems are being carried out. The GFS-2 separator is being assembled. Documents for obtaining the FMBA permission on Complex LTWs with acceleration of testing ions are being prepared.
All products and systems for the SHE Factory were designed and manufactured in compliance with the Quality Assurance System.
Conclusion

## Slide 25
THANKS FOR YOUR ATTENTION!