Brief annotation of the project

Project DERICA (**D**ubna **E**lectron **R**adioactive **I**on **C**ollider f**A**cility, <http://aculina.jinr.ru/derica.php>) is now been considered as one of important variant of the JINR infrastructure development perspective within the next seven-year plan. The research program of the project focused on the study of radioactive nuclei is at the forefront of low energy nuclear physics. Aunique feature of the project is the possibility of investigation of the electron interaction with poorly studied radioactive nuclei in collider experiments to determine the fundamental properties of nuclear matter, namely, the electromagnetic form factors of exotic nuclei. Obviously, that a number of most important and long-term R&D works should be started ASAP to provide the realization of the project during the next seven years period.

The key facility in the project is the high-intensity linear particle accelerator of heavy ions LINAC-100 with the energy of about 100 and 140 MeV/nucleon for the uranium and calcium ions, respectively. The development of the initial part of the accelerator (“front-end”) is the most important and time-consuming task demanding a lot of research and development (R&D) works. The task consists of several stages and assumes the development of a set of the innovation technologies:

- development of the high-intensity ECR source of heavy ions;

- design of normal conducting LINAC sections with the RFQ focusing and drift-tubes LINACs intended to operate in a continuous (CW) mode;

- development of superconducting accelerating resonators;

- design of gas strippers to increase charge states of the accelerated ions;

- development of the RF power supplies based on solid-state amplifiersfor the resonatorfeeding.

 Development of a prototype of the initial section of the high-intensity heavy-ionLINAC is a realistic task for JINR. This confidence is based on the availability of necessary technologies in-house, existing cooperation with the leading Russian institutes (NRC KI–ITEP, NRNU MEPHI, INR RAS, VNIITF, NIIEFA), and collaboration with researchers abroad (GSI, MSU, INFN, GANIL, TRIUMF, PTI NASB). In the future, the further development of this project implies the construction of the LINAC-100 accelerator with the energy of heavy-ion beams about 100 AMeV (and higher) with record intensities (I(for U) ~ 1 emA). This high-current accelerator integrated with the downstream equipment for RIB production (the fragment separator, ion gas catcher, MR-TOF spectrometer, storage ring system, etc.) will allow one to carry out unique world-level experiments with radioactive beams.

Introduction

 Both, the key point and starting point on the way towards the DERICA project realization is development of the normal conducting accelerating resonators designed to operate in continuous mode. The resonators with the radiofrequency quadrupole focusing (RFQ) and several H-type resonators are needed to construct the initial part (so-called front-end) of the LINAC-100. Whereas the technologies for design and construction of the resonators operating in pulsed mode have been recovered in Russia, in particular due to the efforts of the JINR staff, the works done in Russia on the CW-resonators (Continuous Wave) are only theoretical and computational ones. It is extremely important to start designing, manufacturing and testing the prototypes of such resonators, to determine their limiting parameters, operating conditions, andstarttheir serial production as soon as possible.

The topics of priority works and preliminary schedule are as follows:

1. Design and construction of the prototype of the new JINR basicfacility in the framework of the DERICA project, aimed at fundamental radioactive ion beam research. First of all, these are:

(a) Design and manufacturing of the CW RFQ prototype (1-3 sections) for prospective high-intensity heavy-ion linear accelerator (with the project beam current above 1 emA).(b) Development of the ion beam formation system fora plasma border of theECR ion source and the ion beam matching system for beams generated by the ECR source with CW RFQ (LEBT - low energy beam transport).

(c) Development and construction of a test-standconsisting of the prototype section of the advanced CW RFQ and the 14 GHz ECR ion source. Commissioning of the equipment with the use of the 14N2+ ions (for the currents of 3 emA and higher).

2. Design of the high-current superconducting ECR heavy-ionsource with the 28 GHzfrequency (ions up to uranium). Construction of the technology demonstrator.
3. Development and construction of the LEBT (low energy beam transport)to match the beam generated by prospective 28 GHz ECR with CW RFQ acceptance.

4. Development of the superconducting part of the LINAC-100, including of ionstrippersections and charge state separators.

5. Conceptual design report (CDR) for the whole mega-science level project DERICA.

3.4. Status of works

Development of the accelerating complex for DERICA project requires addressing a set of key scientific, engineering and technological issues. The important requirement for the subsystem’s development is ensuring their reliability and stability for operation load ~ 6000 hours/year. Concerning the ion source, it is required to develop the setup (i) working in the continuous mode, (ii) providing the maximum achievable charge state of the accelerated ions (up to uranium), and (iii) delivering the highest ion beam intensity for user experiments. For the most of the experiments, the primary beam intensity should be higher than 10 pµA. Today, the heavy ion source based on electron-cyclotron resonance (ECR) is the most appropriate choice. The world record intensity values for the heavy-ion beams achieved by the best ECR ion sources are shown in the Table 1.

Table 1. Parameters of heavy-ion beams provided by ECR sources at IMP (SECRAL) and LBNL (VENUS). World-record values of intensities are emphasized by bold italics [2].

|  |  |  |  |
| --- | --- | --- | --- |
| Ion, Beam | A/Z | IMP,eμA | VENUS, eμA |
| 16O6+ | 2.67 | ***6100*** | 4750 |
| 40Ar12+ | 3.3 | ***1420*** | 1060 |
| 40Ar16+ | 2.5 | ***620*** | 523 |
| 40Ar18+ | 2.2 | ***15*** | 4 |
| 40Ca11+ | 3.63 | 710 | ***854*** |
| 40Ca14+ | 2.86 | 270 | ***285*** |
| 86Kr18+ | 4.78 | ***1020*** | 770 |
| 86Kr28+ | 3.07 | ***146*** | 100 |
| Xe26+ | 5.03 | ***1100*** |  |
| Xe30+ | 4.4 | 320 | ***330*** |
| Xe42+ | 3.1 | ***15*** | 6 |
| 209Bi31+ | 6.74 | ***680*** | 300 |
| 209Bi50+ | 4.18 | 10 | ***27*** |
| 238U33+ | 7.2 | 202 | ***440*** |

Thus, it is possible to formulate the first task for R&D.It is necessity to develop the source for generation of highly charged ions beams (from boron to uranium) with the intensities close to the record ones (shown in Table 1 by bold italics), or even exceeding them. The next conclusion from Table 1 is that the front-end of the accelerator complex should be designed to accelerate ions with the mass-to-charge ratio A/Z ≤ 7.5. The workboth directions, the development of the ion source and the initial part of the accelerator complex,should be carried out in conjunction. It is necessary to develop the ion source based on the most modern technologies that should guarantee not only high-intensity beams from the source with the highest attainable charge states, but also the development of the LEBT delivering the beams with minimal phase volumes to RFQ. The parameters of the produced beam determine the construction of the beam-matching system with the accelerating structure, as well as the parameters of the accelerating channel in the initial normal conducting part of the accelerator. At present, there is excellent expertise in this field in the Russian Federation (FLNR JINR - ECR sources, NRC KI – ITEP – beam-forming systems and RFQs). With joint efforts of the above teams the expected timescale for the required developments is 3-5 years.

Within the R&D works on the front-end of the normal conducting accelerator, one should first develop the manufacturing technology of accelerating structures (RFQ and DTL) designed to operate in CW mode. Whereas the technology for the pulsed normal conducting accelerating structures has been restored in the Russian Federation within the NICA project], the technology for normal conducting CW-RFQ and CW-DTL still requires development. This includes the manufacturing technology of the resonator based on vacuum brazing from individual elements made of oxygen-free copper.It couldprovide the key parameters required for the setup operation: the residual pressure not higher than 10-8 Torr, the specified resonant frequency, the specified distribution of the RF field along the accelerator axis, the specified accuracy of electrode alignment, power input on the required level in continuous mode. To attain these aims, it is necessary to start work on the development of the prototype of the normal conducting part of the accelerator, namely the initial sections of RFQ, using the most recent recommendations and achievements of the global accelerator community [1-7]. It should be noted that the first part of the work, namely, the development for the accelerating structures with given electrodynamicsparameters is generally solved by the world accelerator community and only adaptation of this expertise in the Russian Federation is required. However, the long-term performance of these structures under beam was achieved so-far only for small intensities of the CW beams. Thus, the search and implementation of new solutions are foreseen within this project.

Another key problem that should be resolved within this project is thegeneral lack of high-frequency superconducting technology in Russia at present. However, this problem has already begun to be solved in the framework of joint program implemented by JINR, NRNU MEPhI, and several scientific centers atRepublicof Belarus. It is assumed that by the end of this year, the first prototype of the coaxial resonator will be manufactured and its tests will start.

1. A.M. Bazanov, et al., COMMISSIONING OF NEW LIGHT ION RFQ LINAC AND FIRST NUCLOTRON RUN WITH NEW INJECTOR, Proceedings of the 8th International Particle Accelerator Conference, Copenhagen, Denmark, from 14–19 May, 2017, pp.2366-2368.

2. P. Ostroumov, Overview of Worldwide High Intensity Heavy Ion Linacs, Proceedings of the 29th Linear Accelerator Conference, Beijing, China, 16–21 September 2018.

3. P.N. Ostroumov, et al., ACCELERATOR PHYSICS ADVANCES AT FRIB, Proceedings of the 9th International Particle Accelerator Conference, Vancouver, Canada, April 29–May 4, 2018, pp.2950-2952.

4. T. Yoshimoto†, et al., ION BEAM STUDIES IN THE FRIB FRONT-END, Proceedings of the
9th International Particle Accelerator Conference, pp.1094–1096.

5. E. Fagotti, et al., IFMIF/EVEDA RFQ PRELIMINARY BEAM CHARACTERIZATION, Proceedings of the 29th Linear Accelerator Conference, Beijing, China, 16–21 September 2018, pp.834-837.

6. E. Pozdeyev, et al., FIRST ACCELERATION AT FRIB, Proceedings of the 29th Linear Accelerator Conference, Beijing, China, 16–21 September 2018, pp.615–619.

7. M. Sugimoto, et al., PROGRESS REPORT ON LIPAC, Proceedings of the 29th Linear Accelerator Conference, Beijing, China, 16–21 September 2018, pp.308-313.

3.5. Description of the proposed project (no more than 5 pages).

The purpose of the work is the development of technical base for the construction of the heavy-ion accelerator designed for energy about 100 AMeV, LINAC-100, which is the beam driver for the DERICA facility. At the first stage, it is suggested to develop and construct the ECR ion source using superconducting magnets and operating at frequency 28 GHz, as well several sections of the prototype RFQ, for the R&D works on continuous-mode operation. Along with the solution of these key tasks, the test stand of the accelerator front-end will be developed including the high-voltage platform with the installed test ECR source, the ion beam-forming system, the beam transport and matching with the RFQ acceptance. The test-stand will be equipped with a diagnostic system for the ion beam, which will also be developed and constructed in the course of the project.

The following results of the works are expected:

1. Basing on beam dynamics simulations the accelerating LINAC-100 channel from the ion source to theLINAC-100 outputwill be developed. The RF operation frequency range of the accelerator resonators will be defined, theenergy of shift from one frequency to another will be selected, and the quantity, design and installation points of theion stripperswill bechosen.

2. Thetechnicaldocumentationforthe 28 GHzECRsourcewith the superconducting magnets will be developed.

3. Thetechnicaldocumentationwill be developed and several first sections of RFQ of the initial part of the LINAC-100 accelerator will be manufactured.

4. The test-stand for testingunder beamwill be constructedto verify the physical, technological and design solutions for the beam-forming system, the beam transport channel, and low-energy beam matching with the RFQ acceptance, the RFQ design.

5. Deeper specification of the scientific program, feasibility studies and following CDR development for the whole DERICA project is expected.

The general trends of the accelerator technique development in the world are:

1. The ion sources are used based on the electron-cyclotron resonance (ECR) operating with superconducting magnets ],];
2. Development of systems with the radiofrequency quadrupole focusing (RFQ) ] functioning in the continuous mode. These systems are used for bunching and acceleration of a beam in the initial part of the accelerating complex up to energies of several MeV, provide possibility of low-energy (down to several tens of keV) injection of ion beam and allowfor high (close to 100%) beam transmission efficiency. Today in the world, the technology of creation of CW-RFQ is still under development There are already examples of the operating CW-RFQ but so far working with beams of negligibly small intensity ];
3. For the energy range of 3-50 MeV the phasing out the use of the classical Alvarez accelerator is observed. Instead systems based on the IH-type resonators with the radio-frequency (RF) transverse focusing, or systems consisting of acceleration sections based on the IH-type resonators and focusing elements ,] are more often used. As well, the separate short IH-type resonators (CH, a quarter - and half-waveresonators, spoke resonators, etc.) with the focusing solenoids and quadrupole lenses placed between the resonators are used;
4. At intermediate and high energies the superconducting resonators are used in accordance with the modular design principle for accelerators: the superconducting resonators are divided into few groups of identical resonators. Such approach significantly simplifies and decrease the cost of the manufacturing process;
5. The superconducting sections arestarted using at as low as possible energies. Whereas in the SNS accelerator the superconducting sections operate starting from the energy of 186 MeV, in the linear particle accelerator of the MYRRHA sub-critical facility it is planned to use them starting from 5.5 MeV. This allows to significantly simplify and, as a result, to lower the cost of the accelerator RF power supply system and also to reduce the cost of its operation. In the Legnaro National laboratory (LNL-INFN, Italy) with participation of staffs of the National Research Center “Kurchatov Institute” – ITEP the first-ever superconducting accelerator with the radiofrequency quadrupole focusing ], has been put into operation. However such cardinal solution does not look reasonable in view of technical difficulties which complicate achievement of the demanded beam transmission efficiency for an intensive beam;
6. Solid-state powerful RF power supply. Reliability and life-time of the RF power supply of this type are much higher, than those for the traditional vacuum power RF tubes of comparable power ], ].

To develop and construct accelerator LINAC-100a number of challenges must be addressed, main of them are:

1. Optimization of the accelerator general layout, including bends, strippers and separators, securing the variation of parameters for the acceleration of ions with the different charge-to-mass ratio keeping the particle loss in the superconducting part at a level of not more than 10-4 m-1. It is also necessary to optimize the stripper position in order to reduce the number of needed superconducting resonators and, respectively, decrease the LINAC-100 cost. The work will be carried out by the working staff of NRNU MEPhI, National Research Center “Kurchatov Institute” - ITEP, GSI (Germany) with participation of specialists from LNL-INFN (Italy). Specialists of JINR determine the initial and final parameters of ion beams received with the ECR source which are necessary for experimental works at the output of the accelerator.
2. Generation and forming of ion beams with the highest charge state and intensity not less than 10 pµA with the normalized emittance not higher than 1-2 π mm mrad at the level 98% of the intensity. To solve this problem it is necessary to developand construct the ECR source with the superconducting magnet system operating at the frequency of 28 GHz. This work is carried out by group of specialists from FLNR JINR. The aim of the work is, at least, to provide generation of the beam of uranium ions in charge state not less than 33+ having intensity not less than 10 pµA,compatible with the world-best achieved results, intending to improve these parameters further.
3. System shaping the beam with emittance not worse than 1–2 π mm mrad has to be developed for this source. This work can be started along with development of the ECR source prototype with the use of the KOBRA-3D software package. The work will be carried out in cooperation with experts from FLNR JINR and National Research Center “Kurchatov Institute” – ITEPbeing familiar with the KOBRA-3D software package and having experience in R&D work on forming systems for the ionbeams with plasma border ];
4. Creation of a test stand, equipped with the required diagnostic tools, for checking the ECR source, the low-energy channel of the beam transport, and the RFQ resonators "in-beam". The work will be performed in collaboration by the experts of FLNR JINR, National Research Center “Kurchatov Institute” – ITEP and INR RAS. FLNR JINR is responsible for the construction of the HV platform and a test ion source, and alsoFLNR JINR, together with ITEP, will develops elements of the beam-transportation channel. The working staff of ITEP participates in thedevelopment of elements of the diagnostic system, in particular, the beam transformerfor a continuous beam, the emittance measuring instrument, where they have extensive experience, including joint works with JINR ], ], ]. INR RAS develops the detector for the bunch shape measurements (Bunch Shape Monitor) [14].
5. Development of the low-energy beam transport for six-dimension matchingwith the RFQ. The magnetic separator, the focusing lenses (solenoids or quadrupoles) and RF buncher for the longitudinal matching of the beam will be in the composition of the channel [15]. The development of the channel will be performed by group of experts from FLNR JINR (magnetic elements), National Research Center “Kurchatov Institute”- ITEP (HF buncher). Manufacturing of the channel elements is supposed to be carried out with involvement of the enterprises of Rosatom – NIIEFA (St.-Petersburg) and VNIITF (Snezhinsk);
6. Development of themanufacturing techniques and setup of the RFQ resonators, maintenance of stability of their parameters during the work in the CW mode. For doing this, several sections of RFQ will be developed and tested. At the first stage, the manufacturing techniques of these sections will be developed, providing a working vacuum pressure not worse than 10-8 Torr, adjustment of electrodes, and achievement of the required electrodynamicsparameters of resonators. At the second stage, RFQ will be installed on the test stand for matching of the emittance of the ion beam with acceptance of RFQ, testing of correctness of the chosen parameters for the resonators providing stability of work of RFQ under beam, measurement of the beam parameters at the RFQ exit.Development of sections will be carried out by group of specialists from National Research Center “Kurchatov Institute” – ITEP, in collaboration with experts from NRNU MEPhI, INR RAS (Troitsk), GSI (Germany) and LNL-INFN (Italy);
7. Development of the RF generators operating in the CW mode. In Russian Federation, NIITFA of Rosatom State Atomis Energy Corporation and “Triada-TV”company (Novosibirsk) are engaged in development of the solid-state generators. When the RFQ resonators are ready, the agreement should be signed with one of these companies for delivery of the corresponding modules. The work will be fulfilled under the control of the National Research Center “Kurchatov Institute” – ITEP;
8. Development of the ion beam acceleration channel on the basis of simulated beam dynamics for defining and optimization of amount of the superconducting resonators needed for the acceleration of a broad range of ions. Simulation of the beam dynamics in the superconducting part of the accelerator will be carried out by group of specialists from NRNU MEPhI, development of resonators is performed in collaboration of specialists from NRNU MEPhI, JINR, number of institutes of Republic of Belarus, with involvement of specialists from GSI (Germany), LNL-INFN (Italy), TRIUMF (Canada);
9. A study of electrodynamics parameters and mechanical loads in the superconducting resonators in the transition processes. This work will be carried out when the superconducting resonators are ready. The work is already performed by the joint team of experts from NRNU MEPhI, JINR, number of institutes of Republic of Belarus with involvement of experts from GSI (Germany), LNL-INFN (Italy), TRIUMF (Canada) and financed from other sources.

It is supposed that the work will take at least three years.

**During the first year,** the development of the channel of the LINAC-100 accelerator from the ion source to the exit from the superconducting part of the accelerator will be complete. The stripper positions and the general structure of the separators placed after strippers will be defined. The chain of frequencies of the resonators will be defined, energies of the operating frequencies shift and also the place of transition from normal conducting part of the accelerator to the superconducting one will be fixed. The works on simulation of the electrodynamics parameters of the RFQ resonators as well as the thermal calculations of these resonators will be performed. Basing on these results, the design documentation (DD) on production of the RFQ resonator prototype will be provided. The technical specification on the 28 GHz ECR source with superconducting magnets will be provided. The technical project of the test stand will be developed. DD on the basic elements of the beam diagnostic system will be prepared. The design documentation on the buncher for the longitudinal matching of the beam will be developed.

**During the second year,** the DD on different parts will be prepared and delivered for manufacturing; architectural supervision of their production will be overseen, with acceptance as the products are ready. The works on preparation of the place for the test stand will be performed and the parts will be mounted as they are ready. Basing on the numerical simulations of the beam-forming system for the test source, DD will be developed and the manufacturing will be started.

**During the third year,** the works on production of the first test resonator will be completed. The testing and tuning of the resonator together with putting it under operation at the working HF power level will be fulfilled. According to the results of testing the resonator DD will be corrected and manufacturing of the corrected modifications will be started. The test stand will be assembled and the testing ECR source with the developed beam-forming system will be installed. The beam diagnostic system will be mounted and tested. The works on ion beam source measurement and optimization will be carried out. The channel of the ion beam transportation to the place of its input to RFQ will be mounted. The works on tuning of the channel to match the beam emittance to the RFQ acceptance will be carried out. Input of a beam to RFQ will be carried out.

**For three years**, the works on the feasibility of the DERICA project [16] with involvement of experts from NPI (Novosibirsk), IAP RAS (. St. Petersburg), NRNU MEPhI, National Research Center “Kurchatov Institute” -ITEP (Moscow), GSI (Germany), MSU (USA), Nihon Univ. (Japan) will be conducted with corresponding development of the conceptual and technical design of the project. Deeper specification of the scientific program is foreseen too.

References

1. T. Nakagawa, Review of highly charged heavy ion production with electron cyclotron resonance ion source Review of Scientific Instruments 85, 02A935 (2014); doi: 10.1063/1.4842315.

2. a) H. W. Zhao, et al. Superconducting ECR ion source: From 24-28 GHz SECRAL to 45 GHz fourth generation ECR. Review of Scientific Instruments 89, 052301 (2018); doi: 10.1063/1.5017479;

b) T. Nagatomo, et al. NEW 28-GHz SUPERCONDUCTING ELECTRON CYCLOTRON RESONANCE ION SOURCE FOR SYNTHESIZING SUPER-HEAVY ELEMENTS WITH Z>118. 23th Int. Workshop on ECR Ion Sources, JACoW Publishing, doi:10.18429/JACoW-ECRIS2018-TUA3.

3. Капчинский И.М., Тепляков В.А. Линейный ускоритель ионов с пространственно-однородной жесткой фокусировкой. — Приборы и техника эксперимента, 1970, № 2, с. 19-22.

4. OstroumovP.N. ADVANCES IN CW ION LINACS, proceedings of 6th International Particle Accelerator Conference IPAC2015, Richmond, VA, USA, 2015, pp.4085-4090.

5. Barth W., Forck P., Ratzinger U. et al. Commissioning of IH-RFQ and IH-DTL for the GSI high-Current linac. — In: Proc. LINAC’00, 2000, p. 229—231.

6. Kolomiets A.A., Koshelev V.A., Plastun A.S., et al. Novel DTL section for ITEP-TWAC heavy ion injector. — In: Proc. RuPAC’12, 2012, p. 469—471.

7. Pisent A., Bisoffi G., Cavenago M., et al. Results on the beam commissioning of the superconducting-RFQ of the new LNL injector — In: Proc. LINAC’06, 2006, p. 227—231.

8. Sechi F., Bujatti M. Solid State Microwave High-Power Amplifiers. Artech House Inc., 2009. ISBN-13: 978-1-59693-319-4.

9. Smirnov A., Krasnov A., Rezanov I., et al. The layout of 352 MHz 400 kW RF power amplifier.— In: Proc. NAPAC’13, 2013, p. 937—939.

10. S. Barabin, A. Kozlov, T. Kulevoy, et al., PEPPER-POT EMITTANCE MEASUREMENTS Proceeding of 26th Russian Particle Accelerator Conference RUPAC2018, Protvino, Russia, 1-5 October 2018, Protvino, Russia, pp. 443-445.

11. S. Barabin, A. Kozlov, T. Kulevoy, et al., EMITTANCE MEASUREMENT ON KRION-6T ION SOURCE BY PEPPERPOT METHOD, Proceeding of 26th Russian Particle Accelerator Conference RUPAC2018, Protvino, Russia, 1-5 October 2018, Protvino, Russia, pp.207-210.

12. S. Barabin, A. Kozlov, T. Kulevoy, et al., EMITTANCE MEASUREMENTS OF POLARIZED ION BEAMS USING A PEPPER-POT EMITTANCE METER, Proceeding of 26th Russian Particle Accelerator Conference RUPAC2018, Protvino, Russia, 1-5 October 2018, Protvino, Russia, pp.440-442.

13. T. Kulevoy, G. Kropachen, A. Balabin, et al., FRONT-END SIMULATION FOR TWAC INJECTOR I4, Rev. of Sci. Instr. 79, 2008, 02B722.

14. a) A. Feschenko. Technique and Instrumentation For Bunch Shape Measurements.
Proceedings of RUPAC2012, Saint-Petersburg, Russia, pp. 181-185;

b) A.Feschenko, S.Gavrilov. Methods for Bunch Shape Monitor Phase Resolution Improvement, Proc. of LINAC2016, East Lansing, MI, USA, 25-30 September 2016, pp. 408-410.

15. A.I. Balabin and G.N. Kropachev, 6D-High Current Beam Matching at RFQ Entrance, Proceeding of the 4th European Particle Accelerator Conference, EPAC94, 27 June - 1 July, London 1994, pp.1180-1182.

16. L.V. Grigorenko, B.Yu. Sharkov, A.S. Fomichev et al., Scientific program ofDERICA – prospective accelerator and storage ring facility for radioactive ion beam research, Usp. Fiz. Nauk, 2019 (in press); <http://aculina.jinr.ru/derica.php>

3.6. Staff estimation.

The total number of experts involved into the project now is expected to be 17 persons per year (i.e. equivalent of full working time).

Personally, employment of each institute is presented in the Table 2.

Table 2. Estimation of the involved staffinto the main works of the project.

|  |  |  |  |
| --- | --- | --- | --- |
| Name of works | Institute | Employees / employment (%) | Equivalent of full employment (persons/year) |
| Construction of the test stand consisting of ECRion source andLINACfront-end; design oftheECR ion source with 28 GHz frequency; conceptual design report forDERICA project | JINRNIIEFABINPIAP RANNRC KI – ITEPMEPhI | 12 / 252 / 258 / 251 / 302 / 251 / 20 | 26/4=6.5 |
| Design and manufacturing of the CW RFQ prototype and ion beam formation system for a plasma border of the ECR ion source (low energy beam transport line) | JINRNIIEFAINP RANVNIITFVNIIEFNRC KI – ITEP | 2 / 252 / 254 / 254 / 252 / 258 / 25 | 22/4=5.5 |
| Design and manufacturing of the superconductive part of LINAC (prototypes including CW resonators, ion strippers etc.)  | JINRINP RANMEPhINRC KI – ITEPPTI NASB | 2 / 252 / 257 / 251 / 254 / 25 | 16/4=4.0 |
| Specification of the scientific program per each stage of the DERICA project  | JINRBINPKINIIYaF MSU | 5 / 101 / 102 / 102 / 10 | 10/10=1 |
|  | In total: 17 |

Form 24

Project: **«Prototype development of the front-end of heavy ions high current linear accelerator aimed on fundamental research with high intensive radioactive beams»**

Supplement for the physical program of the project **«Development of the FLNR accelerator complex and experimental setups (DRIBs-III)»**on the years 2019/2021.
Theme: 03-0-1129-2017/21

**List of participants and institutes**

**Russia:**

JINR (Dubna)

А.А. Bezbakh, S.L. Bogomolov, A.V. Butenko, А.A. Efremov, L.V. Grigorenko,

A.V. Gorshkov,I.V. Kalagin, G. Kaminski, A.V. Karpov, S.A. Krupko, I.N. Meshkov,

S.I. Sidorchuk, S.V. Stepantsov, E.M. Syresin, A.M. Rodin, G.M. Ter-Akopian, A.S. Fomichev,

V. Chudoba, P.G. Sharov, B.Yu. Sharkov, B.V. Antonenko, G.G. Adamian, S.N. Ershov,

R.V. Jolos, А.P. Severuhin

NRC «KI» - ITEP (Moscow)

T.V. Kulevoy, G.N. Kropachev, A.L. Sitnikov, A.I. Semennikov, A.V. Kozlov, D.N. Seleznev, D.A. Liakin, A.Yu. Orlov, S.V. Barabin, V.G. Kuz’michev, R.P. Kuybida

NRNU MEPhI (Moscow)

S.M. Polozov, A.V. Samoshin, V.S. Diubkov, T.A. Lozeeva, Yu.Yu. Lozeev,

A.S. Tsaregorodtsev,M.V. Lalayan, M.A. Gusarova, S.M. Matsievskiy

INP RAN (Moscow)

A.V. Feschenko, V.V. Paramonov, Yu.V. Senichev, А.S. Belov, S.А. Gavrilov

NRC «KI» (Moscow)

А.А. Korsheninnikov, E.Yu. Nikolskii

NIIEFA (St. Petersburg)

S.E. Sytchevskiy, Е.А. Lamzin, V.P. Kukhtin

IAP RAN (St. Petersburg)

M.I. Yavor

**VNIIEF (Sarov)**

N.V. Zavialov, А.V. Telnov

VNIITF (Snezhinsk)

I.V. Mamaev, B.A. Sidorov, M.Yu. Namenko, M.S. Pisarev

NIIYaFMSU (Moscow)

D.O. Eremenko

IAPRAN (Nizniy Novgorod)

S.V. Golubev

BINP (Novosibirsk)

P.Yu. Shatunov, Yu.M. Shatunov, V.V. Parkhomchuk, А.S. Kasaev, А.А. Krasnov, I.A. Koop, Yu.A. Rogovskiy, D.B. Shvarts

**Belorussia:**

PTI NASB (Minsk)

V.I. Zaleski, I.L. Pobol, A.I. Pokrovskiy

**Germany:**

GSI (Darmstadt)

W. Barth, S. Yaramyshev, H. Weik, C. Sheidenberger, H. Simon, Yu. Litvinov, U. Razinger

**France:**

CEA (Saclay)

P. Vedrinne

**Italy:**

LNL-INFN (Legnaro)

A. Facco, B. Giovanni, A. Pisent

**Canada:**

TRIUMF (Vancouver)

V.L. Zvyagintsev

**South Korea:**

Univ. of Korea (Sejong)

H.K. Park, E.S. Kim, C.S. Park

**China:**

IMP (Lanzhou)

H. Zhao, L. Sun

**Japan:**

Nihon Univ. (Chiba)

T. Katayama

Project leaders: L.V. Grigorenko (FLNR JINR)

 T.V. Kulevoy (NRC “KI” - ITEP)

Deputy project leaders: A.S. Fomichev (FLNR JINR)

 A.A. Efremov (FLNR JINR)

 S.M. Polozov (NRNU MEPhI)

Submitted to Science Organization Department: April 29, 2019

Reported on Scientific and Technical Council: April 17, 2019

Discussed within a round table format on the international meeting “Technicalmeetingonconceptualdesignofprospectivehigh-currentheavy-ioncw-LINACforRIBresearchatJINR” Dubna, February 8, 2019; <http://aculina.jinr.ru/derica.php>

Form 25

Project approval list

**«Prototype development of the front-end of heavy ions high current linear accelerator aimed on fundamental research with high intensive radioactive beams»**

and its supplement for the physical program of the project

**«Development of the FLNR accelerator complex and experimental setups (DRIBs-III)»**on the years 2019/2021.

Theme: 03-0-1129-2017/21

Theme leaders: G.G. Gulbekian, S.N. Dmitriev, M.G. Itkis

Project leaders: L.V. Grigorenko, T.V. Kulevoy

APROVED BY JINR DIRECOTR \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

AGREED BY:

JINR VICE-DIRECTOR \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

CHIEF SCIENTIFIC SECRETARY \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

JINR CHIEF ENGINEER \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

HEAD OF SOD \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

FLNR DIRECTOR \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

FLNR CHIEF ENGINEER \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

PROJECT LEADER \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

 \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

PAC FOR NUCLEAR PHYSICS \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

 \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ «\_\_\_\_»\_\_\_\_\_\_\_\_2019

Form 26

Schedule and necessary resources for realization of the project:

**«Prototype development of the front-end of heavy ions high current linear accelerator aimed on fundamental research with high intensive radioactive beams»**

Supplement for the physical program of the project:

**«Development of the FLNR accelerator complex and experimental setups (DRIBs-III)»**

on the years 2019/2021

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of works / Years | 2019 | 2020 | 2021 | Total (kUSD) |
| Design and manufacturing of the RFQ prototype (first section) | 250 | 400 | 330 | 980 |
| Design and manufacturing of the beam transport system (CW-resonators, ion strippers, etc.)  | 150 | 300 | 220 | 670 |
| Design and manufacturing of the ion beam formation system for a plasma border of the ECR ion source | 60 | 80 | 100 | 240 |
| Design of the superconducting ECRion source 28 GHzand elements of formation system for a high current beam. | 100 | 340 | 540 | 980 |
| Design and manufacturing ofthe test setup consisting of ECR 14 GHz ion source and prospective LINAC front-end (LEBT, cw‑RFQetc.). Equipment test using the ions14N2+, I~30 emA. | 40 | 160 | 160 | 360 |
| DERICA CDR. Phase 1–project of the high current linear accelerator (E\_Ca ~ 140 AMeV and E\_U ~ 100 AMeV) with the downstream equipment (fragment separator, gas-cell, MR-TOFspectrometer etc.) for fundamental research with radioactive beams. Specification of scientific program for each project stage.  | 50 | 120 | 100 | 270 |
| In total | 650 | 1400 | 1450 | 3500 |

Project leader: L.V. Grigorenko (FLNR JINR)

Form 29

Estimated project costs for

**«Prototype development of the front-end of heavy ions high current linear accelerator aimed on fundamental research with high intensive radioactive beams»**

and for supplement of the physical program

**«Development of the FLNR accelerator complex and experimental setups (DRIBs-III)»**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Cost items / Years | 2019 | 2020 | 2021 | Total (kUSD) |
| R & D | 300 | 350 | 350 | 1000 |
| FLNR production and process department | 20 | 60 | 80 | 160 |
| FLNR design department  | 25 | 55 | 70 | 150 |
| Equipment and materials, including:*RFQsections (3 units.)**Beam monitor system**Vacuum system**HV platform* *Components of ECRion source**RF generator, power supply,* *communications etc.* | 300 | 850 | 900 | 2050 |
| International cooperation: a) visit into non-JINR-member countriesb) visit into JINR-member countries | 25205 | 554510 | 605010 | 140 |
|  |
| In total | 650 | 1400 | 1450 | 3500 |

FLNR Director S.N. Dmitriev

Project leader L.V. Grigorenko

FLNR leading economist T.V. Mamonova