## Slide 1
Status of the NICA project development

## Slide 2
Injection complex: KRION, HILAc, LU20
Synchrotron Booster
BT Line Booster – Nuclotron
Nuclotron upgraded
BM@N Detector setup
NICA Stage I (BM@N):
NICA Stage II-a (basic configuration):
+
Collider equipped with
RF-1
RF-2: 2 cavities per ring Instead 4 (50 kV RF amplitude instead 100 kV)
1 channel of S-cooling per ring (long. cooling)
NICA Stage II-b (full configuration):
+ RF-2 systems in project version
+ RF-3 systems in project version
+ S-cooling in project version
+ E-cooling
MPD:
+ inner tracker systems
+ forward trackers
NICA Stage III (polarized beams and spin physics)
22 bunches   2 m per ring L=5e25 cm-2s-1
22 bunches   0.6 m per ring L=1e27 cm-2s-1
Jan 2022

## Slide 3
Time-schedule
Booster commissioning
to BM@N
NICA stage 2a
Jan
2022

## Slide 4
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Linac HILac
KRION
IP-1
IP-2
Stripping (80%) 197Au31+ => 197Au79+
KRION
Linac HILac
Booster (25 Tm)
1(2-3) single-turn injection,
storage of (2  4)×109 ions,
acceleration up to 100 MeV/u,
electron cooling, acceleration
up to 578 MeV/u
Nuclotron (45 Tm)
injection of one bunch
of  2×109 ions,
acceleration up to
1 - 4.5 GeV/u max.
Linac LU-20
Ion sources
Fixed Target Area
Slow resonance extraction
Collider
L ≥ 1027 см-2с-1
2019
Facility components’ – status
work in progress
assembly
commissioned / existing

## Slide 5
HILAc-Booster transport channel
Mounting should be finished this month
transport with minimal ion losses
debunching
matching
Separation and adsorption of neighbor charge states of ions.
Provide different schemes of the beam injection into the Booster.

## Slide 6
Booster injection system
IP1
ESS
IP2
IP3
ESS + IP2 delivery June 2019 CryoSystems
IP3 delivery
July 2019
Bevatech + Pink
IP1 – ordering in
Aug 2019
injection with minimal ion losses
single-turn injection, multiturn injection, multiple injection.

## Slide 7
Booster
90% sc-magnets passed tests
50% of magnets delivered to ring tunnel
accelerator infrastructure under mounting
technological run
Sept 2019
run with beam up to the end of 2019

## Slide 8
Booster fast extraction system
kicker
septum
commissioning
final tuning
kicker + septum + stripper + power supplies …. delivery from BINP Sep 2019

## Slide 9
Booster-Nuclotron transport channel
under contract with BINP
Channel delivery
March 2020
…April 2020 start mounting
beam transport with minimal ion losses
Separation of neighbor charge states.

## Slide 10
Nuclotron high energy beam injection system
Lambertson magnet
10
Length, m | 1.5
Max magnetic field, T | 1
Septum thickness, mm | 7
Power supply | DC
Lambertson magnet is based on existing spare yoke for slow extraction system of Nuclotron.
Yoke modification has to be finished.
Kicker
Length, m | 2
Max magnetic field, T | 0.1
Max current, kA | 15
Aperture, mm×mm | 86 × 44
Pulse duration, μs: rise plateau fall | free ≥ 0.5 ≤ 0.5
Development of design of a cold kicker is finishing.
Warm prototype for mechanical tests has been manufactured.

## Slide 11
Goals
Accumulation of required intensity of ions (with help of barrier bucket system and beam cooling systems of Collider).
under contract with SigmaPhi
Delivery to JINR – until end 2019
July 2020 – start mounting
Commissioning - end 2021
Nuclotron-Collider beam transfer channel
88 magnets
30 power supply racks
45 diagnostic devices
200 beam pipes and bellows
55 vacuum pumps
12 vacuum gates
6 for-vacuum pumps
20 vacuum-meters
8 control racks

## Slide 12
Collider building construction
ring equipment mounting (12 months)
Apr 2019

## Slide 13
satellite refrigerators RSG–2000/4.5
of the collider
40 m3 liquid helium tank
1300 kg/h nitrogen liquefier OA–1.3
draining and oil-purification units MO–800
1000 l/h helium liquefier OG–1000
2x6600 Nm3/h helium screw compressors
3x10740 Nm3/h nitrogen turbo compressors
500 kg/h nitrogen re-condenser RA–0.5 of the collider
500 kg/h nitrogen re-condenser RA–0.5 of the Nuclotron and booster
satellite refrigerator
RSG–2000/4.5
of the booster
Delivered Delivery in 2019 Delivery in 2020
Cryogenics

## Slide 14
serial production and testing of sc-magnets started (15 dipoles tested)
RF1- delivery from BINP 2019
RF2- delivery from BINP 2020
RF2, RF3 – delivery from BINP 2021
E-Cooler – delivery from BINP 2021
Collider

## Slide 15
Ring-9 –
quads lengths adjusted to power all magnets in series
Lattice
Linear optics
Beam Vertical separation magnets
MPD+Ecool solenoids
RF-system
Corrector magnets:
Closed Orbit
Chromaticity
X-Y-coupling
Octupoles
Collider
MAC-2018

## Slide 16
Quads currents and eff length
Lattice
Linear optics
Collider
MAC-2018

## Slide 17
Set of collider’s quads for production
5 design type
Collider
MAC-2018

## Slide 18
Collider
Optics optimized May 2019

## Slide 19
Collider
Take all technical solutions
Tendering and production
Plan and perform mounting
foresee and include in the ring structure (cryostat system) all “objects”, witch should be used in further machine operation
Systems under active development:
injection & beam dump
stochastic cooling
beam feedback
collimation system
instrumentation
power supplies
timing system
control system
Thank you for your attention!