## Slide 1
Organizational structure of the NICA project
V. Kekelidze
“Anyone who wants truth is already terribly strong.”
F. Dostoevsky
XI Session of the NICA MAC, May 27-30, 2020

## Slide 2
Project
office
Machines
Project management and expertise structure
Project Leader
Civil construction
Computing
networking
Engineering
Infrastr.
Supervisory Board
Coordination Committee
Project Directorate
RRB
COLLABORATIONS
PROJECTS
IB Boards
DACs
MAC
JINR SC
Plan & finance division
Legal office
Procurement
Accounting office
services
PAC
JINR CP
stockholders
expertise
management
Applied research
infrastruct.
SB
EC
User
Committee
Cost & Schedule
Review Committee
Capital Constr.
department
Chief Engineer
Heads of Lab. services
Detectors
BM@N
MPD
SPD
v
v
v

## Slide 3
Fernando Ferroni (INFN, Italy) - chair;
Frederick Bordry (CERN);
Luisa Cifarelli (University of Bologna, Italy);
Joachim Mnich (DESY, Germany);
Latchezar Kostov (BNRA, Bulgaria);
Eliezer Rabinovici (Racah Institute of Physics Hebrew University of Jerusalem, Israel);
Leonid Kravchuk (INR RAS, Russia)
By the decision of
the Supervisory Board of the
megasciens project “NICA Complex”
at the IV session on December 11, 2019
Cost and Schedule Review Committee
Composition was approved

## Slide 4
First meeting of the NICA Cost and Schedule Review Committee
24 - 26 February 2020
Monday 24 February 2020 LHEP, Building 215
09.00 Visit to the NICA site Dmitry Peshekhonov
11.00 Welcome Victor Matveev
NICA Project Vladimir Kekelidze
12.00 Accelerator complex Igor Meshkov
14.30 Infrastructure: civil construction Andrey Dudarev
15.00 Infrastructure: engineering systems Nikolay Agapov
16.00 Multi Purpose Detector (MPD) Viacheslav Golovatyuk
17.00 Baryonic Matter at Nuclotron Mikhail Kapishin
Spin Physics Detector (SPD) Alexey Guskov
18.00 Computing infrastructure Andrey Dolbilov
Infrastructure for applied research Evgeny Syresin
First meeting of the NICA Cost and Schedule Review Committee
24 - 26 February 2020
Monday 24 February 2020 LHEP, Building 215
09.00 Visit to the NICA site Dmitry Peshekhonov
11.00 Welcome Victor Matveev
NICA Project Vladimir Kekelidze
12.00 Accelerator complex Igor Meshkov
14.30 Infrastructure: civil construction Andrey Dudarev
15.00 Infrastructure: engineering systems Nikolay Agapov
16.00 Multi Purpose Detector (MPD) Viacheslav Golovatyuk
17.00 Baryonic Matter at Nuclotron Mikhail Kapishin
Spin Physics Detector (SPD) Alexey Guskov
18.00 Computing infrastructure Andrey Dolbilov
Infrastructure for applied research Evgeny Syresin
First meeting of the NICA Cost and Schedule Review Committee
24 - 26 February 2020
Monday 24 February 2020
09.00 Visit to the NICA site Dmitry Peshekhonov
11.00 Welcome Victor Matveev
NICA Project Vladimir Kekelidze
12.00 Accelerator complex Igor Meshkov
14.30 Infrastructure: civil construction Andrey Dudarev
15.00 Infrastructure: engineering systems Nikolay Agapov
16.00 Multi Purpose Detector (MPD)) Viacheslav Golovatyuk
17.00 Baryonic Matter at Nuclotron (BM@N) Mikhail Kapishin
Spin Physics Detector (SPD) Alexey Guskov
18.00 Computing infrastructure Andrey Dolbilov
Infrastructure for applied research Evgeny Syresin

## Slide 5
Tuesday 25 February 2020
9.30 Assessment of project risks by technology, financing and planning:
injection complex Andrey Butenko
the collider Evgeny Syresin
12.00 Assessment of project risks by technology, financing and schedule;
civil construction Andrey Dudarev
14.00 Assessment of project risks by technology, financing and planning:
cryogenic Vladislav Benda
power supply infrastructure Viktor Karpinsky
15.30 Assessment of project risks by technology, financing and planning:
MPD Viacheslav Golovatyuk
17.10 Assessment of project risks by technology, financing and planning:
BM@N Mikhail Kapishin
18.00 General discussion
Wednesday 26 February 2020
9.00 Closed Session

## Slide 6
Report
from the NICA Cost & Schedule Review Committee
Dubna, 26 February 2020
General comments.
NICA is a large and ambitious project which is expected to start (Phase I) in the fall of 2022. Its goal is to study the features of dense baryonic matter, the nature and properties of strong interactions between quarks and gluons, the phase transition between hadronic matter and quark-gluon plasma, together with the basic properties of the strong interaction vacuum and QCD symmetries.
The visit to the NICA complex and its many workshops on the first morning has allowed the Committee to concretely see the progress made in the last two years. The progress is impressive in several areas.
The information provided was of high quality. The Committee acknowledged how much work has gone in the preparation of this review and therefore gratefully thanks everybody involved. The total transparency of the presentations and the fruitful conversations that went along have been especially appreciated.

## Slide 7
Observations
- Despite the impressive progress over the last years a significant increase of efforts is required to meet the goal of first collisions at the end of 2022.
- There is a serious lack of experienced & skilled personnel in certain critical areas concerning for example the cryogenics and electric power installations.
- There is often a long-time delay between the appearance of a problem and the corresponding action taken.
- An increase in the volume of the construction work and corresponding engineering equipment led to the inevitable shift of the construction time as a whole by at least 21 months. This can lead to critical delays of the NICA Project.
- Not much has been presented about safety considerations. This is a very important issue and should be taken very seriously.
- The detectors MPD and BM@N, are in general well advanced and the planning includes sufficient time contingency.
-- It would be good to define more milestones and to improve the reporting on the earned value of the project.
- Comments on budget issues require further insight.

## Slide 8
Recommendations
Set up a Project Office with clearly defined personal responsibilities:
- schedule,
- logistics,
- budget,
- safety,
- quality control.
2) Produce a resource loaded global plan.
3) Define milestones to assess progresses with a periodicity of 3 months.
5) Identify critical items for NICA Phase I.
6) Develop a risk analysis and mitigation plan for the most critical items

## Slide 9
implementation of recommendations
A project office is organized with the following responsible:
planning S.A. Kostromin
logistics A.V. Slesarenko
budget V.V. Morozov
quality control H.G. Khodzhibagiyan
safety A.D. Kovalenko
The global plan has been restored and substantially improved
- S. Kostromin
a preliminary list of milestones has been prepared
- S.A. Kostromin
a plan was prepared for organizing a QC group
H.G. Khodzhibagiyan

## Slide 10
Thank you
for attention!
“The ability to raise reasonable questions
is already important and necessary sign of mind and insight.”
Kant