## Slide 1
Vadim Kolesnikov
(VBLHEP)
On behalf of the MPD team
Programme Advisory Committee for Particle Physics
46th Meeting
January 16, 2017
Within the JINR theme 02-0-1065-2007/2019
Progress towards the realization
of the MPD project

## Slide 2
Outline
Introduction
Progress in MPD project realization:
Status of the MPD TDRs & MPD DAC evaluation
Progress in preparation for mass-production
MPD Collaboration growing and role of external groups
Conclusions

## Slide 3
MPD
The general contractor STRABAG (MPD hall in 2018)
Beams – p,d(h)..197Au79+
Collision energy (collider) – 4-11 GeV
(fixed target) - 1-6A GeV
Luminosity: 1027 cm-2s-1(Au), 1032 (p)
NICA Complex
Experiments:
2 Interaction points – MPD and SPD
Fixed target experiment BM@N

## Slide 4
QCD matter at NICA :
Highest net baryon density = 4-11A GeV
Energy range brackets onset of deconfinement
Bulk properties, EOS
- particle yields & spectra, ratios, femtoscopy, flow
In-Medium modification of hadron properties
- onset of low-mass dilepton enhancement
Deconfinement (chiral) phase transition at high rB
- enhanced strangeness production
- Chiral Magnetic (Votical) effect, L polarization
QCD Critical Point
- event-by-event fluctuations & correlations
Y-N interactions in dense nuclear matter
- hypernuclei
NICA-MPD heavy-ion program
RHIC-BES
NICA
BM&N

## Slide 5
Physics targets for the exploration of the QCD phase diagram accessible to NICA & CBM and possible observables for a “mixed phase“ in the release of the “NICA White Paper” as a Topical Issue of the EPJ A (July 2016).
NICA program: new issues (White Paper)
M. Baznat, K. Gudima, A. Sorin, O.Teryaev
Phys. Rev. C 93 031902 (2016)
L-polarization as an observable for the vortticity in non-central A+A.
Spin effects in HI collisions
as a complementary probe
The modulus of the polarization for momentum vectors in the transverse, [px,py ], plane at pz = 0, for the NICA Au+Au reaction at √sNN = 9 GeV.
Y.L. Xie, M. Bleicher, H. Stocker, D.J. Wang, L.P. Csernai.
Phys. Rev. C 94 054907 (2016)

## Slide 6
Hermeticity, 2p acceptance in azimuth
3-D tracking (TPC, ECT)
High resolution vertexing (IT)
Powerful PID (TPC, TOF, ECAL)
- p/K up to 1.5 GeV/c,
- K/p up to 3 GeV/c,
- g, e : 0.1<p<3 GeV/c
Precise event characterization (FHCAL)
Fast timing and triggering (FFD)
Low material budget
High event rate (up to ~ 7 kHz)
MultiPurpose Detecor for A+A collisions @ NICA
  MPD
    the I stage – 2019
    upgraded (IT + end-cups) – 2023

## Slide 7
Status of MPD TDRs
MPD system | Date of recent evaluation | Comments
TPC | 22.06.2016 | DAC recommendations are implemented, ready for next evaluation
TOF | 16.12.2015 | Recommendations from DAC implemented, ready for green light
FFD | 22.06.2016 | Got green light (22/06/2016)
ECAL | 22.06.2016 | DAC recommendations are implemented, ready for next evaluation
FHCAL | 22.06.2016 | Recommendations from DAC implemented, ready for green light
http://indico.jinr.ru/Projects/NICA/Detectors/DetectorAdvisoryCommitee
Next MPD DAC meeting – 17/01/2017

## Slide 8
Control Dewar,
pipe lines
Cryostat
SC coil
Trim Coil
MPD superconducting solenoid
ASG superconductors
(Genova, Italy):
Cold Mass + Cryostat
Vacuum System
Trim Coils
Control System
PS
General responsibility
TPC region
weight ~ 900 t
B0=0.56 T
works – in progress
high level (~ 3x10-4) of magnetic
field homogeneity
Notes: The major part of MPD is SC solenoiodal magnet. It is a challenging project due to very high requirement for the magnetic field homogeneity – better that a permill.
After long negotiations a contract is signed with the ASG sc company – the one which produced a big solenoid for CMS. The ASG is responsible for production of coils, cryostat control system etc. In addition the company takes responsibility for the overall supervision and final characteristics.

## Slide 9: MPD magnet yoke production status
MPD conception design (Neva-magnet ,St. Peterburg) – finished
Strength calculation (Progresstech,Dubna) – finished
Yoke production (VHM, Vitkovice, Czech Republic) – in progress
Forging (support rings, poles, plates) (SPETSMASH, Kazan) – finished
Main tool for assembly, manipulator (gift from CERN) – in Dubna
Other needed tool (VHM + VBLHEP) - in progress
Control assembly technology (VBLHEP) – in progress
A conception and detailed plan of actions for MPD magnet yoke
manufacturing & test assembling is ready
Forging production
Lodgment
Support ring
Plates

## Slide 10
MPD Time Projection Chamber (progress in 2016)
TDR status: Recent evaluation 22.06, the recommendations
implemented, next revision ready for evaluation
Assembling tooling: In progress
RoC & Padplanes: Successful production and testing
FEE: Tests of SAMPA chips ongoing
Service systems (gas, cooling): In production
TPC Integration: Progressing
Clean Room Close to completion

## Slide 11
ROC test procedures:
connectivity tests of pad planes
control of wire positions
counting plateau
dark current
energy resolution (Fe-55)
uniformity of gas gain
TPC : production of ROC chambers
control of the
wire positions
setup for ROC tests
RoC chambers preparation
Works are going in accordance with the schedule

## Slide 12
TPC tooling & service (status at the end of 2016)
Tooling for TPC assembly is manufacturing (Briansk, Russia)
Will be ready in May’17,
Cost ~ 300 k$
Rack 2
Rack 1
Purification system test with TPC imitator – DONE
TPC gas system delivery to JINR – spring of 2017
clean room input gate
climate control

## Slide 13
MPD TOF : progress in 2016
TDR status: all recommendation after recent evaluation implemented, ready for further proceeding
Preparation for mass-production : material ordering (mylar, conductive paint, screws,
monofilament line, wires and connectors purchased), equipment installation, personnel
training
TOF readout electronics: in production
TOF assembling area
& cosmic tests zone : in preparation
Area for TOF cosmic tests
Full-scale mRPC stack
for MPD TOF
mRPC housing developed in cooperation with
NC PHEP BSU and “ Artmash” (Minsk, Belarus)

## Slide 14
Materials are already bought for
assembling of 50 MRPC (5 mod):
280 μm float glass – 1000
400 μm float glass – 500
Honeycomb panel – 100
PCB with strips – 100
Purchasing plans in 2017 :
280 μm float glass – 4000 (133%)
400 μm float glass – 2000 (133%)
Honeycomb panels – 500 (250 MRPCs)
PCB with strips – 500 (250 MRPCs)
Workshop staff: 3 physicists, 5 technicians, 2 electronics engineer
Productivity: 1 detectors per day (1 module/2 weeks).
~ 1 year and 2 months to assembling whole TOF system.
TOF mass-production: mRPC and FEE
All major elements (NINO and HPTDC chips) for the production
of electronics for the MPD TOF barrel (13440 channels) were
purchased with reserve (~24000 channels).
72-channels VME time-to-digital converter TDC72VHL
Updated NINO based 24-channels
preamplifier-discriminator PA24N2V2I
32 boards (2034 ch ~15% of total)
available.
Available – 50 boards; 100 boards
(2400 ch ~17% of total) – in 2017

## Slide 15
TDR FFD finished, recent recommendations of the MPD DAC
implemented, got green light on 22.06.2016
Tests of the trigger electronics & software within BM@N
Progress in FE electronics and LV system for FFD
Purchasing plans, integration & installation procedure
MPD FFD : progress in 2016
The time resolution of 44 ps was obtained
with deuteron beam in Dec. 2016

## Slide 16
Status of quartz radiators
Status of purchase of MCP-PMTs
# | Type | Date | Units | Comments
1 | XP85012/A1 | 03.2010 | 2 | used for tests
2 | XP85012/A1-Q | 09.2012 | 6 | used for tests (in reserve)
3 | XP85012/A1-Q | 09.2013 | 20 | for FFDE
4 | XP85012/A1-S | 10.2015 | 1 | used for tests (in reserve)
5 | XP85012/A1-S | 08.2016 | 20 | for FFDW
All quartz bars of FFD radiators have been produced
by Fluorite Co. in 2016
Production and delivery of MCP-PMTs
by Photonis have been finished in 2016
FFD modules
Front-End Electronics and
Tests with prototypes were finished in 2016.
Mass production will be started in 2017.
Module housings
FFD electronics
2016 – Concept
2017 - 2018 – Prototyping and tests
2018 - 2019 – Production and tests
HV power supplies
2017 - 2018 – Purchase of HV system
Cables
Prototypes of all cables were selected and tested
in 2015 - 2016. 2017 - 2018 – Purchase of cables
Laser system
2016 – New concept for 20 + 20 modular arrays of FFD
2017 – Upgrade of fiber bundles
2018 - 2019 – Production and tests
Detector Control System
2016 - 2017 – Concept
2017 - 2018 – Purchase of equipment, prototyping
2018 - 2019 – Production and tests
FFD: purchasing plans

## Slide 17
Pb+Sc “Shashlyk” with APD read-out
Segmented (4x4 cm2) to ensure rate capability , full azimuthal coverage
Energy resolution better than 5% (@ 1 GeV), arrival time measure is an advantage (st~500 ps)
MPD ECAL : progress in 2016
ECAL to perform high acceptance & purity e/g identification
In-medium modifications in dilepton spectra
Thermal radiation from QGP
Bulk properties via study of spectra, flow & correlations of photons
Challenge for electron measurements in Au+Au at NICA
Significant remaining contribution from hadrons in TPC-TOF identified sampleб correct
reconstruction of pT-spectra of dileptons in Minv above pT~0.5 GeV/c problematic
Large flux of secondary photons (for example, y-rays from capture of slow neutrons)

## Slide 18
ECAL group activities in 2016:
Progress in ECAL MC feasibility study (response & pattern recognition)
Additional R&D to improve ECAL performance (timing performance)
TDR preparation ( next evaluation – 17/01/2017)
Preparation for mass-production (technology, tooling, new participants, etc. )
Extra h-suppression
factor with EMC:
up to 30 for protons
up to 13 for pions
up to 12 for kaons
ECAL pressurization tooling

## Slide 19
MPD FHCAL : progress in 2016
TDR status : after detailed evaluation ready to get green light from DAC.
Results of realistic MC performance study are read, MEPhI group is very active
Preparation to mass-production
ongoing
Ein
Eout
FHCAL calorimeter for centrality
& event plane determination.

## Slide 20: Status of FHCAL module production
The contract on production of all 90 FHCal modules
is signed
Assembling room with the necessary equipment
(welding gear, lifting crane, mounting tables) ready
The basic components for full project (lead,
scintillators, WLS-fibers…) are ordered
First nine modules (supermodule) are already
assembled
A few Front-End-Electronic boards are produced
The tests and the calibration with cosmic muons
in process
Front-view of supermodule.
Back-view of supermodule.
According to plans, next year other 30 FHCAL modules will be assembled
and tested.

## Slide 21
Integration of TPC service
systems - progressing
ТРС
MPD Integration : service, cabling
Final design of internal support structures
Finalizing TPC, TOF & ECAL assembling plans
Integration of service systems, cabling, etc..
Drawing of tooling for (dis)assembling MPD
elements and MPD integration
EСAL

## Slide 22
CERN & JINR have signed MoU for manufacturing the STS carbon fiber space frames for NICA (BM@N & MPD) and FAIR
ITS: progress in 2016
Site for module
assembly
Automat for DSSD strip-by-strip
QA-tests was put into operation
A first stand for in-beam tests of silicon
sensors was put into operation

## Slide 23
45th meeting, PAC for Particle Physics: RECOMMENDATIONS
….The PAC emphasizes again the need to attract young professionals
and additional external groups for the realization of the MPD project.
Present activities of SINP MSU group
within the agreement between JINR and SINP MSU : 01.06.16-30.04.17
(L. Malinina, K. Mikhailov, G. Eyyubova together with JINR group)
Development of tracking for ITS MPD
Particle Identification for TPC and TOF
Femtoscopy study for NICA
Present activities of MEPhI+GSI group
agreement between JINR and MEPhI under preparation
(A. Taranenko, I. Selyuzhenkov, I. Svintcov, and P. Parfenov)
FHCAL simulation (event plane and centrality)
FHCAL TDR preparation (in cooperation with INR, Trotsk)
Development of analysis algorithms for MPD flow analysis
Visitors from Mexico – Alejandro Ayala (Univ. of Mexico) and Mario Rodriguez (Univ. of Puebla)
Visitors from China – Fuqiang Wang (Huzhou Univ.), Zebo Tang (USTC, Hefei)
Visitors from Azerbajan – Anar Rustamov (Baku Univ,)
LoIs with particular contributions to MPD under preparation

## Slide 24
Au+Au @ 5 A GeV (preliminary results at NICA energies)
Mass distributions of fragments for central and semi-peripheral collisions
Central collisions: light clusters; semi-peripheral collisions: heavy clusters – remnants from spectators
Rapidity distribution becomes more narrow with increasing the cluster size
Rapidity distributions of fragments for central collisions
PHQMD: fragment formation at NICA energies
The goal: Dynamical modeling of cluster formation by a combined model
PHQMD = (QMD & PHSD) & SACA (FRIGA)
GU & GSI & NANTES & JINR collaboration: A. Le Fèvre, Y. Leifels, J. Aichelin, V. Kireev, E. Bratkovskaya
V. Kireev, A. Le Fèvre, J. Aichelin, Y. Leifels and E. Bratkovskaya, arXiv:1509.06648 [nucl-th] , SQM’15

## Slide 25
Conclusions
Thank you for your attention!
Significant progress achieved in 2016 in MPD project realization
MPD TDR preparation is going further : DAC helps
in their evaluation
Successful preparation for mass-production of MPD elements
(TPC, TOF, FFD, FHCAL)
Integration plan for MPD is ongoing
MPD Collaboration is continuing to grow: new groups
are very active MPD simulation and analysis

## Slide 26
Extra slides

## Slide 27
 | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  | 
Injection complex |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Lu-20 upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HI Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HI Linac |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nuclotron |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
general development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
extracted channels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Booster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Collider |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
startup configuration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
design configuration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BM@N |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I stage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
II stage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MPD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
solenoid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TPC, TOF, Ecal (barrel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
upgraded end-caps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Civil engineering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MPD Hall |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SPD Hall |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
collider tunnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HEBT Nuclotron-collider |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cryogenic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
for Booster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
for Collider |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NICA schedule
running time

## Slide 28: VHM (Vitkovice) equipment for test assembling
Milling machine for plates
Boring machine for rings
Possible
Assembly place
A conception and detailed plan of actions
for MPD magnet yoke test assembling is ready

## Slide 29
15-Jan-17
29
Test of boards with SAMPA chip at Dubna
Test
set up
Cyclone-5 + NCCA board
Ready for tests
MPD TPC FEC32S board
PCB - 6 layers