## Slide 1
Milestones, plan, critical path
NICA facility construction

## Slide 2
Key milestones
2020
Booster commissioning
construction cryogenic compressor station W49
2021
Booster – Nuclotron channel commissioning W06
LHEP electrical substation commissioning W49
BM@N run W40
MPD commissioning W47
2022
NICA cryogenic system fully commissioned W24
Start of Collider Run#1 W36
…main points

## Slide 3
Key milestones list
6 milestones from 27 completed,

## Slide 4
2020
!

## Slide 5
2021

## Slide 8
Project plan – overall level
Booster
Collider
MPD
Collider building
Runs schedule
Cryogenic
infrastructure
Power infrastructure
Nuclotron
Injection chain
List of works:
Injection chain – 103 items
Booster – 230 items
Runs schedule – 7 items
Nuclotron – 157 items
Collider – 345 items
Runs schedule – 6 items
Collider building – 17 items
MPD – 21 items
Cryogenic infrastructure – 128 items
Power infrastructure – 209 items
Total: 1223 items
@2020_09_11

## Slide 9
Project plan – overall level
Ion sources, Linacs
Booster
2021, 2022 Booster + Nuclotron runs
Heavy ion source
Inj /Extr in full config
Beam diagnostics

## Slide 10
Project plan – overall level
Inj from Booster system
Nuclotron
Fast extraction system
Channels for applied research
Collider
SC-magnets testing

## Slide 11
Project plan – overall level
Collider assembling
Collider Run 1
Magnet modules – assembly & tests
Reference super period construction, production, assembly
Collider magnets electrical power supply system
RF-system
Beam diagnostics, control system
Vacuum system
Electron cooling system
Stochastic cooling system
Injection & beam dump system
Collimation system
Other collider engineering system
Injection system,
Collider infrastructure - critical

## Slide 12
Project plan – overall level
Cryogenic infractructure

## Slide 14
409 people for the moment

## Slide 15
Manpower for construction of Collider systems in man-months
in total: 5 500 man-months
106 persons involved
Project plan loading by HR

## Slide 16
Manpower for construction of Collider systems in man-months
188 persons involved
Project plan loading by HR

## Slide 17
Manpower for cryogenic infrastructure construction in person-month
in total: 500 man-months
40 persons involved
Project plan loading by HR

## Slide 18
68 persons involved
Project plan loading by HR

## Slide 19
Project plan loading by HR
lack of resource in the project
List of needed personnel compiled
35(÷ 50) people needed in to accelerator division