## Slide 1: CBM-STS Milestones and Work Packages: Sensor Production Readiness and Purchasing
Johann M. Heuser
STS Work Meeting on CBM and BM@N, JINR VB-LHEP, 22-23 May 2017

## Slide 2: CBM-STS: Production Readiness
(Major) Milestone | Date
Sensors PRR accepted [M8] | 7/2017
ASIC PRR accepted [M8] | 11/2017
FEB ready for production | 12/2017
Module assembly procedure ready | 2/2018
Ladder assembly procedure ready | 2/2018
Powering concept ready | 3/2018
Cooling concept ready | 3/2018
System assembly procedure ready | 3/2018
STS Core PRR accepted [M8] | 3/2018
ROB ready for production | 7/2018
POB ready for production | 7/2018
ROB/POB PRR accepted [M8] | 7/2018
CBM-STS PR is separated into 4 major milestones (M8)
Some are an envelope for PR of sub-components or procedures
Our task:
How do we get to PR for the different components/procedures?
Establish milestones and timelines to their PR, at the different sites/teams
add this to the official STS Project Plan
 here: for sensors

## Slide 3: Production Readiness: Sensors
Major Milestone | Date | Milestones to PR | Date | Team(s)
Sensors PRR accepted [M8] | 7/2017 |  |  | 
 | !!! | All sensor types produced with two vendors | 3/2017 5/2017 | GSI, JINR
 |  | QA prepared and documented | 1/2017 | GSI, Tübingen, JINR
 |  | Internal review | 3/2017 | GSI, Tübingen
 |  | Irradiated sensors checked | 5/2017 7/2017 | GSI
 |  | Technical specs and production timeline agreed with vendors | 5/2017 6/2017 | GSI
 |  | Sensors with microcables and STS-XYTER read-out verified | 6/2017 | GSI
 |  | PRR documentation prepared | 6/2017 | GSI, Tübingen, JINR

## Slide 4: Brief recollection of sensor development
started in 2007 CiS Forschungsinstitut für Mikrosensorik, Erfurt, Germany
CBM01 full-size sensor, double-sided, double metal
  small budget only  low priority at vendor
CBM02 (FSD, SPID) baby sensors, from a CiS research project
CBM03, CBM03’ technological wafers to address quality/performance issues
CBM04 (2010) next full-size sensor – still low priority
CBM05 (2012/13) started prototyping using additional funding (“3M”), including single-metal sensors
in 2012: second vendor – Hamamatsu, Japan
CBM05 (2013) first sensor from Hamamatsu – special BMBF budget
CBM06 (2014-2016) in several sizes and iterations;
start using STS project funds  larger orders, higher priority
12 cm sensor (2014) 6.2 x 12.4 cm sensor replacing two daisy chained 6.2 x 6.2
CBM06 (2014-2017) sensors of all sizes produced at CiS and Hamamatsu,
double-sided, double metal (GSI/FAIR and JINR funds)

## Slide 5: Current status
Full family of sensors developed with CiS and Hamamatsu:
  double-sided, double metal
  layouts established with identical features (within the design rules of the vendors)
  mask sets produced
  sensors in all four sizes produced at both vendors
CiS:
  4” technology: established
    6.2 cm x 2.2 cm – 3 sensors per wafer small series produced
    6.2 cm x 4.2 cm – 1 sensors per wafer small series produced
    6.2 cm x 6.2 cm – 1 sensors per wafer small series produced
  6” technology: being established
    6.2 cm x 12.4 cm – 1 sensors per wafer, space free for “gap” sensors small series produced
Hamamatsu:
  6” technology: established
    6.2 cm x 6.2 cm + 6.2 cm x 4.2 cm – 1 sensor of each per wafer small series produced
    6.2 cm x 12.4 cm + 6.2 cm x 2.2 cm – 1 sensor of each per wafer small series produced + one “gap” sensor 4.0 cm x 2.2 cm
Those could be the masks for the series production, if no further changes are identified.

## Slide 6: Most recent sensors
6.2 x 2.2 cm2
6.2 x 4.2 cm2
6.2 x 6.2 cm2
6.2 x 12.4 cm2
CiS
Hamamatsu

## Slide 7: Contact with vendors
CiS
  http://www.cismst.org
  main business: MEMS, radiation sensors
  established sensor provider, e.g. at CERN (ATLAS, CMS)
  double-sided microstrip sensor technology
  we have direct contact to managers, project leaders of radiation detector division, are well informed about technology, equipment, procedures; CiS investment in DSSD production process
  project meetings at GSI and CiS in regular intervals + phone meetings
  most recent major meeting on 01 March 2017, including director from CiS [and GSI/FAIR]
Hamamatsu
  http://www.hamamatsu.com
  main business: photon detectors
  established microstrip sensor provider, in particular CMS tracker
  large factory for single-sided sensors
  double-sided sensor technology offered since ca. 2010 on 6”  K. Yamamura, CERN Workshop Nov. 2011, https://indico.cern.ch/event/148944/
  good and direct contact to sales office in Germany (Herrsching), good relaying of communication to and from Sensor Division in Japan; regular meetings.
  technical meeting with Hamamatsu engineers and managers in Frankfurt (May 2012), project meeting at Hamamatsu, Hamamatsu City, Japan (Nov. 2013), next: June 2017

## Slide 8: Sensor production timeline
official STS Project Plan:
Possible production at CiS:
CiS has worked out a plausible timeline for a 2-year production, both 4” and 6” processing, for all STS sensors (896) + spares.
Possible production at Hamamatsu:
3-year old rough estimate: max. 35-40 sensors/month (420-480 sensors/year)
production readiness: 7/2017
tendering: 7/2017 (takes > ½ year)
production: 10/2017 – 10/2019
 probably needs adjustment: sensor production 1/2018 – 1/2020. Delivery due: STS ready for installation 12/2021!

## Slide 9: Joint Purchase of sensors
Tendering procedure is being prepared at FAIR GmbH
with the combined funds of GSI, JINR, JU
advantages:
  all sensors will be produced with the same technical specifications
  production within one consistent time plan
  better price due to the larger amount of sensors ordered as compared with split orders
  one point of contact for the companies
tendering can only start with the FAIR-JINR CBM-STS Collaboration Contract Addendum signed.
Status: GSI – lawyer agreed, ready for signature at GSI/FAIR. JINR – accepted by VB-LHEP director JU – accepted by work package leader
valid also for microcables

## Slide 10: Call for Tender
Two-step EU tendering procedure (“zweistufiges Verhandlungsverfahren”)
  publication of the tender with request for participation of bidders.  Selection of the bidders according to suitability and several qualitative/quantitative criteria
  request of offers from the selected bidders  screening of offers, renegotiation, award of contract to bidder(s)
  The call for tender will be issued by FAIR. Input from us:
    Accurate description of the tendered objects and conditions
    Precise list of technical and other specifications
  The tendering procedure will take about 6 months. Also, the sensor producers need an advance time to plan in the production.
  To start sensor production at the beginning of 2018, tendering has to commence in Summer 2017. Preparation in detailed progress at GSI/FAIR!

## Slide 11: To-do list on sensors for PR
must have:
S/N measurement with minimum configuration: sensor+ microcable + STS-XYTER
  sensor thickness; what is the optimum under which boundary condition (study)
full set of tests for 12cm sensor
establish production plan to ensure correct proportion of sensor sizes for smooth module assembly
acceptance criteria for sensors
  needs measurements on large sample of sensors
test effect (dark current, breakdown voltage) of glue applied onto different areas of sensor
  map out “active” areas of sensors
iterate location of alignment marks on sensors; they will be partly obscured after assembly.
marks for position of L-legs
finalize shape of innermost sensors
  beam pipe design is needed to do so
charge collection efficiency of irradiated sensors
nice to have:
measure capacitance and interstrip resistance of irradiated sensors
check bonding quality with “real” sensor; also: long term test of bonding, e.g., by thermal cycling
dark currents: check path (through bulk vs. surface) with thermal camera
more test of latest version of CBM06
what is the impact of the doping concentration onto the sensors
improve on cable mask (not multiple of 58 µm)
summary of CBM-STS Sensor Internal Review, 10 March 2017
https://indico.gsi.de/conferenceDisplay.py?confId=5808

## Slide 12
Invitation to join the work team for sensor PR!