## Slide 1
A.Butenko on behalf of the team
Sarantsev V.P. workshop, 20 of September 2022, Crimea, Alushta
Status of the
NICA accelerator complex

## Slide 2
Introduction (complex NICA)
Two LINACs & ion sources
  LU-20/LILAc (light & pol. ions)
  HILAC (heavy ions)
The Booster ring (commissioning)
The Nuclotron ring
Collider systems status

## Slide 3
NICA complex
Nuclotron ring
Nuclotron
Two Linear Injectors
& sources
Two linacs:
HILAC & LILAC
Booster & beam line
Booster
Collider ring
Collider

## Slide 4
SPP
LU-20
Nuclotron
ESIS
Booster
Transfer to the collider rings
LIS
RFQ
RFQ
IH1
IH2
HILAc
Au31+ 3.2 MeV/u
p↑, d↑, ions z/A>0.3, 5 MeV/u
Slow extraction
& transfer to BM@N
LILAc
Stripping Au31+=>Au79+
(24)×109 ions Au31+ 570 MeV/u
2×109 Au79+, 3.9 GeV/u
or
light ions, 5 GeV/u
Structure of the Injection complex

## Slide 5
p↑, d↑, ions Z/A>0,3
RFQ
Ions Z/A>0,3
LIS
SPI
p↑,d↑
10mA
HILAc
HILAc building
Booster
Injection
channel
Nuclotron
Booster
RF amplifier for LU-20
LU-20 building
Layout of the linear Injectors

## Slide 6
SPI “source of polarized ions” was transported, installed on the HV terminal and commissioned with the new fore-injector & LU-20
SPI, beams of polarized d & p
The SPI-project was started more then 10 year ago.
Main purpose is to provide the intensity of the accelerated polarized beams (D+,H+) up to 1010 p/pulse
The SPI provided by polarized d & p Nuclotron complex during two beam RUNs in 2016-17.
in spring 2016
Commissioned in 2016
two Nuclotron beam RUNs
was provided

## Slide 7
source
LEBT + Buncher
4 wane RFQ
(3 sections)
MEBT LU-20
QT + Bu +QT
Designe has been started in 2012 In collaboration with ITEPH, MEPHI, Snezhinsk.
New fore-injector for LU-20
Commissioned in 2016
4 Nuclotron beam RUNs
was provided

## Slide 8
p↑, d↑, ions Z/A>0,3
RFQ
Ions Z/A>0,3
LIS
SPI
p↑,d↑
10mA
HILAc
HILAc building
Booster
Injection
channel
Nuclotron
Booster
RF amplifier for LU-20
LU-20 hall
Layout of the linear Injectors
The new Light Ions Linac LILAC
7 MeV/u for A/q<3, 13 MeV for protons

## Slide 9
Layout of the linear Injectors
RF amplifiers
Tested at JINR
RFQ 4-rod
3Q of 2022
IH2 and MEBT
Mid of 2023
LLRF + PS
End of 2023
IH3 + debuncher
End of 2023
Under manufacturing
BEVATECH Germany

## Slide 10
p↑, d↑, ions Z/A>0,3
RFQ
Ions Z/A>0,3
LIS
SPI
p↑,d↑
10mA
HILAc
HILAc building
Booster
Injection
channel
Nuclotron
Booster
RF amplifier for LU-20
LU-20 building
Layout of the linear Injectors

## Slide 11
HILAC & Booster injection beam line
A/q (Target Ion Au31+) | 6.25
Beam current | < 10 emA
Repetition rate | < 10 Hz
Output energy | 3.2 MeV/u
Transmission of 2mA Fe14+ ions beam is about 75% from RFQ to the exit of the HILAc, 3.2 MeV/u
Heavy Ion Linear Accelerator
Stable and safe operation during Booster commissioning with He1+ and Fe 14+ beams
Commissioned in 2018
BEVATECH Germany

## Slide 12
Introduction (complex NICA)
Two LINACs & ion sources
  LU-20/LILAc (light & pol. ions)
  HILAC (heavy ions)
The Booster ring (commissioning)
Beam transfer line
The Nuclotron ring

## Slide 13
Beam losses < 10%
just on the first 5 turns.
Beam injection & circulation
26.12.2020
Fast Current Transformer (FCT)
Circulating beam
at the injection energy 3.2 MeV/u
22.12.2020
600 ms circulation of He1+
19.12.2020, 19:56 Moscow time. First beam in the ring.

## Slide 14
RUN-2
16 of September 2021
Life-time more then 10 s, equivalent pressure of residual gas
              is about 8910-9 Pa
Parametric beam current transformer signal
16.09.2021: Measurements of integral vacuum conditions by intensity decrement of circulating He1+
Beam current & vacuum conditions
Beam intensity
PCT signal
0 500 1000 1500 2000 2500 3000 3500 4000
t, ms
Circulation of 3.2 MeV/u He1+
~10 s beam lifetime
Beam Intensity, ppc
Magnetic field, Gs
RUN-1

## Slide 15
Beam acceleration
PCT signal when beam injecting into rising field, capturing (~60%), accelerating & decelerating:
no transient losses on the MF table & after.
1000 1500 2000 2500 3000 3500
Acceleration
Circulation
100 MeV/u
Deceleration
RF off
Magnetic field
Injection
Beam Intensity
Magnetic field
Cycle time, ms
Parametric beam current transformer signal (DC mode)
Beam injection with adiabatic capturing 5 harmonic (>95%),
accelerating up to 65 MeV/u,
recapturing 1 harmonic (close to 100%)
acceleration up to 578 Mev/u
with project ramp dB/dt = 1.2 T/s
Cycle 2 of commissioning
14-23 of September 2021 Fe14+
500 1000 1500 2000 2500 3000 3500
Cycle time, ms
Acceleration
Circulation
578 MeV/u
RF capturing 5 harm.
Acceleration
Magnetic field 1,2 T/s
Injection
Circulation
65 MeV/u
Re-capturing 1 harm.
Fe14+
He1+
Cycle-1 of commissioning
20 of December 2020 He1+
RUN-1
RUN-2

## Slide 16
Schottky spectrum at 4-th harmonics
Electron cooling of Fe14+ at 3.2 MeV/u during 2 s
Electron cooling section

## Slide 17
30.12.20: design magnetic field cycle
increasing of main PS current up to 9.8 kA & quench detection.
It was take just 10 hours, and 17qunches of magnets was detected.
1st quadrant
2nd quadrant
3rd quadrant
4th quadrant
The goal: B = 1.8T, dB/dt = 1.2T/s
Magnetic system training and problems

## Slide 18
Design magnetic field amplitude & ramping rate
30.12.20: design magnetic field cycle
Injection plateau
Electron cooling plateau
Project B=1.8 T
dB/dt = 1.2 T/s
3.6 s
17999.96Gs
CSRC, 16 of November 2021
RUN - 1

## Slide 19
Contract with BINP
Beam extraction & transfer line
3-rd str. sect.
To Nuclotron
Circulating beam
Beam fast extraction section
3D model of the transfer line

## Slide 20
Contract with BINP
Beam extraction & transfer line
3-rd str. sect.

## Slide 21
BINP team during beam line commissioning
Beam extraction & transfer line
3-rd str. sect.
RuPAC 2021, Crimea, Alushta, 27 of September 2021
56Fe beam “portrait” at the exit of the transfer line Booster - Nuclotron
Commissioned! Autumn 2021
RUN-2

## Slide 22
Unique devices
Lambertson magnet
4-rod kicker
Tested & mounted
End of 2021
22
Beam injection system (into the Nuclotron)
Side view
Top view
Commissioned in RUN -3
winter 2022

## Slide 23
Main results of RUN-3 (Booster + Nuclotron)
Booster and Nuclotron beam DC current transformers signals
Nucloton field
Intencity
RF capture
Acceleration
Booster field
Beam transfer with stripping С4+/С6+ transmission 75%
Beam intensity in the Booster intensity in the Nuclotron

## Slide 24
Acceleration
1-1.5*109 of С 6+
Nuclotron field
From the Booster ring
RF capture
3 GeV/amu
Spill duration 5 c,
Beam slow extr.
Nuclotron beam DC current transformers signal
Main results of RUN-3 (Booster + Nuclotron)
Beam acceleration cycle in the Nuclotron

## Slide 25
78Kr+26 beam extraction (2,8 Gev/u) RUN #55 at Nuclotron
78Kr 2*105 Tspill = 10s, kdc= 99,3%
Heavy ion beams acceleration
2018

## Slide 26
Parameter | Project | Status (2021)
Max. magn. field, T | 2 | 2 (1.6 T routine)
B-field ramp, T/s | 1 | 0.8 (0.7 routine)
Accelerated particles | p–U, d | p, d, p – Xe
Max. energy, GeV/u | 12 (p), 5.8 (d) 4.3( 197Au79+) | 5.6 (d, 12C), 3.6 (40Ar16+)
Intensity, ions/cycle | 1E11(p,d), 2E9 (A > 100) | d 4*1010 (2*1010 routine), 7Li3+ 3*109 12C6+ 2*109 40Ar16+ 1*106 78Kr26+ 2*105 124Xe42+ 1*104
26
Nuclotron status table

## Slide 27
Fast extraction from the Nuclotron
Design development is in the progress
Delays:
Due to delays of LM for injection;
Due to delays of injection Kicker;
A lack of designers of SC magnets;
LM1
Not designed
Final stage of design
LM2
Under redesign
Mitigation plan “plan B”:
Limitation of extracted beam energy by factor 1,6 (~2 GeV/u for Bi)
Doubling of injection LM with the same design and tooling for higher current;
Two sections of Kicker instead of 3 (not needed reconstruction lattice quads)
3 section kicker

## Slide 28
Magnetic element | Number | Effective length, m | Max. magnetic field (grad), T (T/m)
Long dipole | 21 | 2 | 1.5
Short dipole | 6 | 1.2 | 1.5
Quadrupole | 28 | 0.35/0,52 | 31
Steerer | 33 | 0.466 | 0.114
Nuclotron-Collider transfer line is under delivery and construction by Sigma Phi
Magnets delivered in JINR in February 2021
November 2021 – delivery of first part of PS, beam diagnostics, support stands.
January 2022 – delivery of vacuum equipment.
July 2022 – second part of power supplies, profile monitors, control system.
September 2022 – start of commissioning of the channel equipment.
December 2022 – commissioning of the channel with a beam.
Nuclotron-Collider beam transport channel
Sigma Phi

## Slide 29
Collider SC magnetic system

## Slide 30
Collider power supply system
Three main power supplies
Additional power supplies (10В х 300А)
Constructed by LM Invertor (Moscow)
Delivered to JINR
Energy evacuation keys
Prototype was constructed and tested
2 prototypes from 3 were constructed and tested
LM Invertor
(Moscow)

## Slide 31
Barrier bucket RF1 and harmonic RF2-RF3
Two RF1 cavities delivered to JINR in 2019
RF3 cavity and amplifier in BINP
16 RF3 cavities for extension configuration,
installation - end of 2022 – 2023,
beam tests – 2023/24
4 RF2 cavities for base configuration
mounted, 2 of then passes trough vacuum tests, installation in 4q of 2022
RF1 cavity in JINR
RF1 cavity in BINP
RF2 cavity in JINR
BINP

## Slide 32
32
Electron Cooling System
HV Electron Cooler for NICA Collider
Design and construction at BINP
Installation at NICA in 2022
Parameter | Value
Electron energy, MeV Energy instability, E/E | 0.2 – 2.5  110-4
Electron beam current, A | 0.1 – 1.0
Cooling section length, m | 6.0
Solenoid magnetic field, T Field inhomogeneity, B/B | 0.05 – 0.2  110-5
Beginning of mounting – October of 2022
First beam tests – Sumer 2023
Contract with BINP

## Slide 33: Synchronization and LLRF system
33
Stage 1 (T0 + 7 months) | Development of the NICA Injection complex (Booster+Nuclotron) Synchronization system, its testing on the Executive’s site, and its delivery to the Customer. Two LLRF Prototypes are provided up to this stage and testing is started during the Nuclotron-Booster run.
2.Stage 2/ (T0 + 13 months ) | Development of the first revision of NICA Injection complex LLRF system and on-site testing; Development of NICA Collider Synchronization System
3.Stage 3/ (T0 + 19 months ) | Development and testing of the final revision of synchronization and LLRF systems of the NICA complex.
4.Stage 4/ (T0 + 21 months ) | Services for mounting, final software installation and testing of the NICA Accelerator complex Synchronization and LLRF systems./
5.Stage 5 (T0 + 25 months ) | Services for SAT and commissioning of the NICA Accelerator complex Synchronization and LLRF systems.
Start of Contract with COSY Lab – November 2021
Synchronization and LLRF of Booster and Nuclotron – December 2022
Mounting and testing of NICA synchronization and LLRF – June 2023
Synchronization: 317+31+91 channels. LLRF: 30 channels
COZYLAB

## Slide 34
During last beam runs of the injection complex was demonstrated:
Stable operation of the HILAC & Booster;
Low beam losses at all stages of acceleration;
Real possibility to acceleration of different ion species
High quality of the slowly extracted beam form the NUCLOTRON -
emittances, profiles, spill structure;
Stable operation of the new PS system of the beam transfer channels to BM@N (fix target exp.)
For operation of the NICA injection complex for collider,
Summary
 Increasing of operation stability of all main systems
 Minimization of beam losses on all stages
 Development of injection and other main systems
 Development of automatization and control
 new global synchronization

## Slide 35
Thank you for attention