## Slide 1: MPD Yoke assembly September 2022
N.Topilin on behalf of the MPD team
JINR, Dubna

## Slide 2
28 plates
16 t each
2 support rings
42.5 t each
2 poles
44 t each
Total weight: 621 t
Material:
Steel 10 (AISI 1010)
forging
MPD Yoke (L=8970 mm, Ø6625 mm)
Lodgement (Yoke support) – 70 tons, ordinary steel St.3 (Fe 360)
Pole transport supports 15 tons each without ballast

## Slide 3
MPD yoke preassembly at VHM, June-August 2018

## Slide 4
Predicted very useful tool !

## Slide 5: “Final” measurements report (27 plates in assembly)
Side W – 0.55 mm out
Side E – 0.66 mm out

## Slide 6
MPD pre assembly at JINR
(13 July – 12 August 2020)
1-st stand
1-st plate: 8.5 m length, 16 tons
42 t Pole installation
Support ring lifting, Ø 6.7 m, 44 tons
13 plates and 2 rings as 1 piece
370 tons in total
Leading engineer N.Topilin VBLHEP
JINR-Pelcom plant team
JINR-Pelcom plant team

## Slide 7: Measurements by “Industrial Measurements” LLC (ООО “Промышленные измерения”) , S.Peterburg
Rails planarity (top and side surfaces) – 0.4 mm on length 30 m
12 stands height deviations – 0.1 mm max
Stands shape deviation – 0.2 mm max
7 plates in assembly – nonplanarity 0.5 mm
13 plates in assembly - nonplanarity 0.58 mm max
13-th plate installation

## Slide 8
Geometry of 13 plates in the assembly
Nonflatness of plates
## 12-13 per faces
Nonflatness of plates
## 12-13 per faces
relative to the
horizontal plane
Nonflatness of plates
##4-5 and ##8-9

## Slide 9
Capturing the position of the plate with micron accuracy
Поимка положения плиты с микронной точностью

## Slide 10
Installation top (last) plate #28

## Slide 11: December 25, 2020

## Slide 12
28 plates in assembly

## Slide 13
Poles installation

## Slide 16
Movement system assembly and test

## Slide 17
The movement system allows you to move an object weighing
up to 1000 tons with a positioning accuracy of 0.1 mm across
the beam and install it with an accuracy of 0.1 mm in height.
The accuracy of the installation of the pole axis relative to the axis
of the support ring is 0.25 mm (provided technologically).
The speed of movement of all rods is from 0 to 3 mm/s.

## Slide 18
1 - Assembly zone position
Rails shape during Yoke moving
2 - Central position
(poles installation)
3 - Beam position

## Slide 19
July 16, 2021
Power frame brackets

## Slide 20
Magnet installation: July 30, 2021
August 2020
Traverse 75 t capacity and
80 t Crane test together

## Slide 21
The position of the magnet axis relative to the axis of the Yoke

## Slide 22: Related tasks
Assembling and modification
the mobile platform
Evacuation of the ASG magnet transport container

## Slide 23
Pole transport support modification
O-Ring, 3935 mm in diameter,
Overall thickness: 300 mm
Weight: 2.7 t , 2 ps
Modification reason: Cable space increasing
by “Lider” Company, St-Peterburg
Installation: end of October 2021

## Slide 24: Worm coils installation in the poles
POINT 4
11-13 July 2022
Misalignment of the position of the pole and coil centers is 1 mm

## Slide 25: Pole with TRIM coil installation
15 July 2022

## Slide 26: Pole with TRIM1 coil installation

## Slide 27: Current status on today

## Slide 28: Carbon structure for E-Cal modules
Diameter 4.6 m
Length 8.26 m
Weight 8 t

## Slide 29: Thanks for your attention !
Conclusion
The working documentation developed in the design department of the LHEP
and the original technology of assembling the yoke of the magnetic circuit,
as well as their filigree production at the factory in Vitkovice (Czech Republic),
made it possible to repeatedly assemble and disassemble the yoke while maintaining
the high accuracy laid down on the geometry of the yoke.
Next steps:
Yoke assembly finishing (last 3 plates installation)
Top platform assembly up to end
Cryogenic equipment installation on the top platform
All of these operations will be done as soon as it will be possible