## Slide 1: MPD TPC Status (18.04.2023)
  TPC:
    vessel assembly, ROC chambers, gating grid system
  Sub-systems:
    Electronics
    LV+HV system (CAEN)
    Gas and cooling systems
    Laser calibration
  Integration TPC to MPD
    Electronics platform
    Cabling and piping
    Installation TPC to MPD
  Time schedule
Presented by S.Movchan

## Slide 2: MPD TPC main parameters
Item | Dimension
Length of the TPC | 340cm
Outer radius of vessel | 140cm
Inner radius of vessel | 27 cm
Outer radius of the drift volume | 133cm
Inner radius of the drift volume | 34cm
Length of the drift volume | 170cm (of each half)
HV electrode | Membrane at the center of the TPC
Electric field strength | ~140V/cm;
Magnetic field strength | 0.5 Tesla
Drift gas | 90% Ar+10% Methane, Atmospheric pres. + 2 mbar
Gas amplification factor | ~ 104
Drift velocity | 5.45 cm/µs;
Drift time | < 30µs;
Temperature stability | < 0.5°C
Number of readout chambers | 24 (12 per each end-plate)
Segmentation in φ | 30°
Pad size | 5x12mm2 and 5x18mm2
Number of pads | 95232
Pad raw numbers | 53
Pad numbers after zero suppression | < 10%
Maximal event rate | < 7 kHz ( Lum. 1027 )
Electronics shaping time | ~180 ns (FWHM)
Signal-to-noise ratio | 30:1
Signal dynamical range | 10 bits
Sampling rate | 10 MHz
Sampling depth | 310 time buckets

## Slide 3: TPC vessel assembly
  C1-C2 and C3-C4 cylinder – assembled
  TPC service wheels (2pc) - assembled
  HV membrane – tested
  TPC field cage assembly - July 2023
  TPC vessel ready – August 2023
TPC vessel assembly – in progress (see next slide)
ISO-6
Service wheel with thermal panels (12pc)
Both service wheels - assembled
Rods D=40 mm (24 pc) reassembled - ready
Rods D=60 mm (24 pc) – assembling in progress, ready - June 2023
Bld. 217

## Slide 4: TPC vessel assembling
TPC body assembled with test rods for check TPC geometry by laser tracker
AT-402 (reflector type -TBR (R=6.35 mm), reflector center offset L== 12.00 mm):
2 flanges, HV electrode and C1-C2 cylinder - misalignment is about 1 mm
Goal – improve misalignment by factor х2

## Slide 5: TPC vessel assembling
Flanges and HV electrode unflatness
Flanges unflatness – about 0.5 mm
HV electrode unflatness – about 0.7 mm
Flange to flange distance
L=(3300.5 +/-0.5) mm
(nominal – 3300.0 mm)

## Slide 6: ROC chambers and gating grid system (GGS): status
24 pc serial ROCs + 4 spare – READY!
Test set up for ROC certification
Test set up for pads calibration
Leica MS60 - 1 second resolution
Leica AT960 +/-10 mkm +5 mkm/m
Leica AT403 +/-15 mkm +6 mkm/m
Scanner AS1+AT960 +/-50 mkm
+/- 30 mkm
Pad plane unflatness: example
Check pads geometry
systematic - up to 150 mkm
Full set of ROC alignment marks
Summary:
- measurements to do for all ROCs
- calibration of ROC marks and
3968 pads respect to ROC
“reference hole” - in progress
ROC gating grid system: test set up
Pulse rise time
- 500 ns, OK!
Mass-production – in progress
Delivery to JINR – Sept 2023
24 pc ROCs – tested

## Slide 7: TPC Sub-systems: electronics
Production version of the FE card:
DAQ prototype:
62 FE cards, RCU prototypes,
ROC, 2pc LVDBs, server interface
board - tests ongoing
Chart: TPC FE cards production status
| FECs manufactured | FECs to be manufactured in 2022 | FECs to be ordered
 | 467 | 260 | 761
N=967 pc
(65%)
15 ROCs chambers can be completed
(from 24 ROCs)
967 FECs of 1500 were produced.
Tests of the FEC basic functionality were shown the target characteristics (noise and stability).
Testing of the readout system for one ROC is ongoing.
60 pc LVN9 were send back to Minsk:
- modification connection of power cables to LVN9 - in progress
- modification of LVN9 output voltages to FECs - in progress
- test of LVN9 with cooling radiator under full load (analog – 70 A, digital – 50 A) – in progress
LVN9 stabilizer
FE radiators (water cooling)
RCU-64 controller:
testing with FEE

## Slide 8: TPC Sub-systems: LV+HV (CAEN)
LV&HV system based on CAEN rad. hard design:
(up to 2000 Gauss and 15 kRad)
- power converters A3486 AC/DC (380 V -> 48 V) – 15+3 pc
- EASY3000 crates - 14+2 pc
- LV module - A3100B (8V/100A) - 48+8 pc
- LV module - A3100HBP (14V/50A) - 6 +2 pc
- HV modules –A3540P (+4kV/1mA) - 8+3 pc
- HV modules –A3540N (- 4kV/1mA) - 2+2 pc
Status:
LV+HV system: JINR-CAEN contract signed
Expected delivery date to JINR: August 2023
test system – tests ongoing
LV cables (halogen free, low smoke):
S=50 mm2 – delivered
HV cables - ordered

## Slide 9: TPC Sub-systems: gas and cooling
Gas supply
Racks
Tests - in progress
(H20 and Q2 sensors are replaced)
TPC volume
imitator
Full set of panels – delivered
contract JINR-INP BSU (Minsk) – in progress
delivery – 30 September 2023
operation under manual control – during beam test 2024
fully automatic control – 30 September 2024
Gas system (Ar/CH4, 90:10)
Water cooling system
S=4x5 m2
h=2.5 m
MPD hall
S=1.2x3.6 m2
h=2.2 m
MPD
S.Movchan TPC assembling, XI collab. meeting, April 18-20 2023, Dubna, Russia

## Slide 10: Cooling prototype
Bottom cooling plates
Set of top cooling plates
Cu tube Din - 3.16 mm
Plates thickness - (4+4) мм
7 sensors
7 sensors
T sensor based on Pt100
Electronics water:
T=19 C
ROC water: T=22 C
Air: T=23 C
Cooling simulation (Autodesk inventor Nastran)
Experimental and simulation
results are compatible

## Slide 11: Cooling prototype: results
Chiller
LV power
Set up
Water FECs T (C) | Water ROC T(C) | SAMPAs dT (C) | FPGAs dT (C) | Pads dT (C) | ROC dT (C) | T Min (C) | T Max (C) | Comments
17 | 25 | 3÷5 | 7 | 0.27 | 0.6 | 18 | 33 | 
19 | 22 | 3÷5 | 7 | < 0.2 | 0.2 | 20 | 35 | optimum
ROC + pad sensors
FE card sensors
Air: T=23 degree (C)

## Slide 12: Serial Cooling system (INP BSU, Minsk): STATUS
Hydrodynamic pressure drop
for ROC chambers
dP ≤ 0.5 atm
Water velocity: (1.5-2.5) m/s
Systems parameters optimization by
calculations – in progress
NEW cooling system position –> 2-nd floor of a
additional platform – design and optimization in progress

## Slide 13: Serial Cooling system: optimization
in progress …

## Slide 14: Serial Cooling system: stAtus
in progress …

## Slide 15: TPC Sub-systems: laser calibration
Scheme for ½ TPC
Laser “planes” - 4
Micro-mirrors bundles per plane - 4
Beams from micro-mirrors bundle - 7
Laser “tracks” (N =112х2) - 224
micro-mirror
bundles
TPC
laser
laser
Laser beam monitor
Laser beam splitter

## Slide 16: NICA-MPD-Platform (NMP)
Common view
TPC + ECAL
cooling
Design and integration –
in progress …
TPC equipment

## Slide 17: MPD electronic platform
TPC equipment in racks on the 4th floor
16

## Slide 18
W side: cooling and gas pipes scheme
TPC cabling and piping
TPC list of cables and pipes

## Slide 19: TPC cabling and piping
Structures for
cables and pipes
fixation
Prototype for cabling and piping
Structure design - in progress
TPC+TOF+ECAL cabling – in progress
Piping – not started yet
TPC
Beam pipe
Integration …

## Slide 20: Tooling for Installation TPC to MPD
24 tons,
max=0.41 mm
Bld. 217
Bld. 217 (MPD)
4 units for adjustment X, Y, Z
Design under optimization,
Prototype 1:5 – June 2023
Tooling manufacture –
July 2023-Feb 2024
Delivery to JINR –
Spring 2024

## Slide 21: Planning (draft)
in progress …

## Slide 22: Time schedule
Status:
TPC assembling:
  Field cage assembly - July 2023
  HV tests - August 10 2023
  TPC vessel ready (glue by epoxy) - August 30 2023
  Laser beams position measurements - Sept 2023
  TPC vessel tightness measurements - Oct 2023
  24 ROC chambers installation - Nov-Dec 2023
  TPC tests: laser tracks and cosmic test - Jan-Sept 2024
  Integration TPC to MPD:
  TPC racks (8pc) + cabling - autumn 2023-2024
  TPC rails (2pc manufacture and delivery) - Oct 30 2023 on critical path !!!
  Rails installation to ECAL support structure - Nov 2023
  Tooling for installation TPC to MPD:
  Design optimization + prototype 1:5 - June 2023
  Tooling manufacture - July 2023 – Feb 2024 (8 month)
  Delivery to JINR - Spring 2024
  TPC+ECAL cooling systems: FE cooling - Nov 2023
  commissioning - Sept 30 2024
  TPC installation to MPD - Oct 1-Nov 30 2024
  MPD commissioning - Jan 10 - Feb 2025
Thank you !