## Slide 1
X Collaboration Meeting of the MPD Experiment at the NICA Facility
JINR, Dubna, April 18-20, 2023
A.Sidorin, on behalf of the AD
Construction and commissioning
of the NICA complex

## Slide 2
Contents
Stages of the accelerator complex commissioning
Plans of the collider commissioning

## Slide 3
Fixed Target Area
Nuclotron (38.5 Tm)
injection of one bunch
of  1×109 ions,
acceleration up to
1 - 3.85 GeV/u
Linac LU-20 (5MeV/u)
Ion sources
Booster (25 Tm)
1(2-3) single-turn injection,
storage of 2 ×109 ions,
acceleration up to 65 MeV/u,
electron cooling, acceleration
up to 587 MeV/u
Linac HILac (3.2MeV/u)
ESIS KRION
Stripping (80%) 197Au31+ => 197Au79+
Two SC rings of the collider
NICA – Stage II
~ 2 x 22 injection cycles
22 bunches per ring
L ≥ 1027 см-2с-1
Heavy ions: ESIS + HILac + Booster + Nuclotron
NICA accelerator complex

## Slide 4
Stages of the accelerator complex commissioning
HILAC + transfer line to Booster
HILAC + Booster
HILAC + Booster + transfer line to Nuclotron
HILAC + Booster + Nuclotron + transfer line to BM@N
ESIS + HILAC + Booster + modified Nuclotron + transfer line to BM@N

## Slide 5
ESIS + HILAC + Booster +
modified Nuclotron + transfer line to BM@N
Forth commissioning run:
from 20.09.2022 to 03.02.2023 Ar, Xe ions
Acceleration of Ar ions in the Booster, test of SOCHI
Tuning of Xe acceleration
ESIS Krion-6T installed and tuned at HILAC
- Nuclotron structure was modified for installation of fast extraction

## Slide 6
The timetable of the run (135.5 days)
repairment
experiments
Unexpected losses
cooling
Commissioning works

## Slide 7
Beam acceleration in the Nuclotron up to 1.65 T magnetic field plateau (about 3.6GeV/u).
Intensity of the accelerated beam up to about 2107 ions.
Extracted beam spill duration up to 2 s (cycle period 12 s).
Beam acceleration and slow extraction
Time, s
Intensity,
elementary charges
Field, Gs

## Slide 9
Plans of the collider commissioning
End of 2023 (may be beginning of 2024): technological run
Main limitations:
- completion of engineering infrastructure bld. 17
- Assembly of cryomagnetic system

## Slide 10
Preliminary program of first technological collider run
- Insulating volume and beam pipe vacuum tests
Test of cryogenic system
Start of the collider control system
Test of the main power supply and cycle control system on equivalent load
Commissioning of thermometry system
Cooling of the rings
Commissioning of quench detection system
Commissioning of energy evacuation system
Test of the main power supply on superconducting load

## Slide 11
Status of the collider construction
In June all the collider dipole magnets were installed
and mechanically adjusted in the collider tunnel, connected by pairs each to other.
The assembly of the collider is postponed until completion
of the engineering infrastructure mounting that is expected to the end of May 2023.
The collider ark dipole magnets in the tunnel
A.Galimov

## Slide 12
Collider power supply system
Each collider ring has its own power supply system based on 3 main current sources:
PIT11-50, PIT01-40, PIT0.6-30.
2 sets of sources for both collider rings are manufactured by NPP "LM Inverter"
and transferred to VBLHEP.
V.Karpinsky
PIT 11-50 power supplies
Busbar model in rooms No. 240 and 109/1
12 electromechanical energy evacuation switches
are manufactured and located at VBLHEP

## Slide 13
Test assembly of the collider electron cooling system was performed in October at Budker INP
Electron cooling system

## Slide 14
Electron cooling system
22 November – start of transportation of the cooler elements to JINR
HV vessel
Toroidal solenoid
I.Meshkov
A.Sergeev

## Slide 15
2024: first beam run
Fast extraction from the Nuclotron
Assembly of the Nuclotron-Collider beam line
Injection into Collider
Synchronization, beam storage