## Slide 1: Status of Yoke production
N.Topilin
The first collaboration meeting
of the MPD and BM@N experiments at the NICA Facility
April 11-13, 2018, JINR, Dubna

## Slide 2: MPD Yoke (L=8970 mm, Ø6625 mm)
28 plates
16 t each
2 support rings
43.7 t each
2 poles
47 t each
Total: 630 t
Material:
Steel 10 (AISI 1010)
forging
Cradle (Yoke support) – 74 tons, ordinary steel St.3 (Fe 360)
2 Pole transport supports – 15 tons each

## Slide 3: JINR-VHM (Ostrava, Czech Republic) Contract (Dec. 2015)

## Slide 4: Plates production on NKMZ (Kramatorsk, Ukraine)
Mechanical properties:
Sigma 0.2 = 225 - 354 N/mm²
Average = 241 N/mm²
Technical Order = 210 N/mm²
Carbon C
GOST on steel 10 0.07 - 0.14 %
Technical Order 0.08 - 0.10 %
Forging (really) 0.08 - 0.10 %
All other elements are inside tolerances
Ultrasonic control: good

## Slide 5
Forging transportation from NKMZ (Kramatorsk, Ukraine) to VHM (Vitkovice, Czech Republic) -1700 km, 29 trucks

## Slide 6: Support rings (Forgiatura Morandini)
4 May 2016
14 June 2016

## Slide 7: Poles
4 May 2016
14 June 2016
Carbon C
GOST on steel 10 0.07 - 0.14 %
Technical Order 0.08 - 0.10 %
Forging (really) 0.08 - 0.09 %
All other elements are inside tolerances
Mechanical properties:
Sigma 0.2 = 231-292 N/mm²
Average = 255 N/mm²
Technical Order = 210 N/mm²
Ultrasonic control: good

## Slide 8
Forging transportation from Italy to VHM (Vitkovice, Czech Republic)
1130 km

## Slide 9: Support rings: Ø 6.63 m, 43.7 tons each need to have holes machining, sandblasting, painting
Vitkovice Heavy Machinery, Ostrava

## Slide 10: 2 Poles: Ø 4.5 m, 47 tons each
28, February 2018

## Slide 11: Yoke plates: 0.35x0.74x8.47, m3; 16 tons each 25 from 28 are ready
13 bottom plates have nominal length 8470 mm
All top one have length on 9 mm shorter
Length tolerances: 0…-0.1 mm for all the plates
We plan the slots machining

## Slide 12: Cradles 2 main parts are in progress: 1.47x4.15x7.68, m; 34 tons in total VHM inserts pins and weld brackets

## Slide 13: Cradle bottom parts
6 cradle support
Spacer plates between bottom surface
of cradle and Roller Skates

## Slide 14: Poles transport supports
Front stand
Back stand

## Slide 15: Poles transport supports
Rings billets
Bottom base parts

## Slide 16: Technological tool
Top beam
Lifting beams
Base plate for face surface

## Slide 17: Technological tool
Lifting beam for plugs inserting-removing in vertical plates
Plugs

## Slide 18
Restart to work – 20 March 2018
Cradle installation – 17 April
Floor measurement – 13 April
Cradle measurement – 23 April
13 plates installation – 03-08 May
13 plates measurement – 08 May
Support rings
installation – 10-13 May
14-28 plates installation – 15-21 May
1-28 plates measurement – 21 May
700 Pins installation – 23 May- 22 June
Yoke test 22 June
Plan of work at VHM

## Slide 19
Work finish – 31 July
Transport by “AET Trans” – S-Petersburg in the period August - September

## Slide 20
Pole turn-over device (by Sergei Gerasimov)
Full contact
between pole and
Frame
Squeezing
(pressing) bolt
Bolts have
tension stresses only
Trim coil installation
Frame fixing
Appendix 1

## Slide 21: Two 80/20 tons Cranes by “URALKRAN” are ready
Appendix 2

## Slide 22
Appendix 3
E. Belyaeva (DD LHEP)
Yoke assembly 1 – Control assembly at VHM - May 2018 and test of ridging at VHM – June 2018 2 – Final assembly at Dubna – 2018 - 2019
Δ estimation, mm |  |  | Test result
Neva-Magnet | Progresstekh- Dubna | LHEP DD | VHM
5,6 | 4,5 | 0,1 | 

## Slide 23: MPD Hall layout
Appendix 4

## Slide 24: Thanks for your attention
MPD Trench 10 April 2018

## Slide 25: cosmonautics day and international day of human space flight