## Slide 1: Collider NICA complex status
NICA: Nuclotron based Ion Collider fAcility
E. Syresin and V. Lebedev on behalf of Accelerator division

## Slide 2: NICA Layout
1. Вывод из
Нуклотрона
2. Каналы в
коллайдер
3. Инжекция в
коллайдер
3. Инжекция в
коллайдер
4. Магнитная система коллайдера
5. MPD

## Slide 3
Ion source KRION-6Т
Achieved values:
Аr16+ - 5·108 ions per pulse
Xe28+ - 2·108 ions per pulse
Bi35+ - 2·108 ions per pulse
First Collider beam runs are
planed with Xe28+ & later Bi35+ ions
Project ion intensity 2·109 Bi35+ per pulse
Chart: 
| 40.1 | 40.200000000000003 | 40.299999999999997 | 40.4 | 40.5 | 40.6 | 40.700000000000003 | 40.799999999999997 | 40.9 | 41 | 41.1 | 41.2 | 41.3 | 41.4 | 41.5 | 41.6 | 41.7 | 41.8 | 41.9 | 42 | 42.1 | 42.2 | 42.3 | 42.4 | 42.5 | 42.6 | 42.7 | 42.8 | 42.9 | 43 | 43.1 | 43.2 | 43.300000000000097 | 43.4 | 43.5 | 43.600000000000101 | 43.700000000000102 | 43.800000000000097 | 43.9 | 44.000000000000099 | 44.100000000000101 | 44.200000000000102 | 44.300000000000097 | 44.400000000000098 | 44.500000000000099 | 44.600000000000101 | 44.700000000000102 | 44.800000000000097 | 44.900000000000098 | 45.000000000000099 | 45.100000000000101 | 45.200000000000102 | 45.300000000000097 | 45.400000000000098 | 45.500000000000099 | 45.600000000000101 | 45.700000000000102 | 45.800000000000097 | 45.900000000000098 | 46.000000000000099 | 46.100000000000101 | 46.200000000000102 | 46.300000000000097 | 46.400000000000098 | 46.500000000000099 | 46.600000000000101 | 46.700000000000102 | 46.800000000000097 | 46.900000000000098 | 47.000000000000099 | 47.100000000000101 | 47.200000000000102 | 47.300000000000097 | 47.400000000000098 | 47.500000000000099 | 47.600000000000101 | 47.700000000000102 | 47.800000000000097 | 47.900000000000098 | 48.000000000000099 | 48.100000000000101 | 48.200000000000102 | 48.300000000000097 | 48.400000000000098 | 48.500000000000099 | 48.600000000000101 | 48.700000000000102 | 48.800000000000097 | 48.900000000000098 | 49.000000000000099 | 49.100000000000101 | 49.200000000000102 | 49.300000000000097 | 49.400000000000098 | 49.500000000000099 | 49.600000000000101 | 49.700000000000102 | 49.800000000000097 | 49.900000000000098 | 50.000000000000099 | 50.100000000000101 | 50.200000000000102 | 50.300000000000097 | 50.400000000000098 | 50.500000000000099 | 50.600000000000101 | 50.700000000000202 | 50.800000000000203 | 50.900000000000198 | 51.000000000000199 | 51.1000000000002 | 51.200000000000202 | 51.300000000000203 | 51.400000000000198 | 51.500000000000199 | 51.6000000000002 | 51.700000000000202 | 51.800000000000203 | 51.900000000000198 | 52.000000000000199 | 52.1000000000002 | 52.200000000000202 | 52.300000000000203 | 52.400000000000198 | 52.500000000000199 | 52.6000000000002 | 52.700000000000202 | 52.800000000000203 | 52.900000000000198 | 53.000000000000199 | 53.1000000000002 | 53.200000000000202 | 53.300000000000203 | 53.400000000000198 | 53.500000000000199 | 53.6000000000002 | 53.700000000000202 | 53.800000000000203 | 53.900000000000198 | 54.000000000000199 | 54.1000000000002 | 54.200000000000202 | 54.300000000000203 | 54.400000000000198 | 54.500000000000199 | 54.6000000000002 | 54.700000000000202 | 54.800000000000203 | 54.900000000000198 | 55.000000000000199 | 55.1000000000002 | 55.200000000000202 | 55.300000000000203 | 55.400000000000198 | 55.500000000000199 | 55.6000000000002 | 55.700000000000202 | 55.800000000000203 | 55.900000000000198 | 56.000000000000199 | 56.1000000000002 | 56.200000000000202 | 56.300000000000203 | 56.400000000000198 | 56.500000000000199 | 56.6000000000002 | 56.700000000000202 | 56.800000000000203 | 56.900000000000198 | 57.000000000000199 | 57.1000000000002 | 57.200000000000202 | 57.300000000000203 | 57.400000000000198 | 57.500000000000199 | 57.6000000000002 | 57.700000000000301 | 57.800000000000303 | 57.900000000000297 | 58.000000000000298 | 58.1000000000003 | 58.200000000000301 | 58.300000000000303 | 58.400000000000297 | 58.500000000000298 | 58.6000000000003 | 58.700000000000301 | 58.800000000000303 | 58.900000000000297 | 59.000000000000298 | 59.1000000000003 | 59.200000000000301 | 59.300000000000303



28+ | 0 | 296
29+ | 0 | 264
27+ | 0 | 140
30+ | 0 | 108
26+ | 0 | 22
31+ | 0 | 50


Xe ion charge distribution at KRION exit
Further development and upgrade of KRION-6T during Apr.-May and Sep.-Oct. 2024 beam runs with D, N, Kr, Xe ions at injection rate of 10 Hz and pulse duration approaching required 4ms.
I [A]

## Slide 4
Bunch length
measured with FCT
Without cooling .
With cooling .
Longitudinal electron cooling
Electron cooling of Xe beam
124Хе 28+ at injection energy
Electron energy 1,93 keV
Electron current 150 mА
Signals from Ionization profile monitors during beam circulation
Transverse cooling
MCP monitor

## Slide 5
Priorities for the Accelerator Complex
1. Most of NICA commissioning will proceed in heavy ion mode
  “Real” luminosity is expected in 2.5 – 3 years - after we will get cooling systems operational
Operation with slow extracted beams
  All modes of operations are anticipated
    Heavy ion mode is straightforward – it will not require significant efforts (Xe is at the beginning)
    Light unpolarized ions will be a backup for heavy ion mode in the case of problems with KRION (Acceleration in Booster)
    Polarized ions (Acceleration in Nuclotron, LU-20 has to be operational)
    Medium mass ions from laser source are anticipated They will require additional ion source (laser source?)
        Operation in 2-4 years

## Slide 6
Plans for Acceleration of Polarized Ions
Delivery of LILAC (Light ions linac) is postponed to unknown time
  LU-20 is the only available possibility for near future
    LU-20 “switching-on” slowly proceeds
        Looks like the problem with beam loss is found
        Consequences of recent accident are addressed
        I expect LU-20 operations to be resumed by the year end
Increase of LU-20 acceleration efficiency from ~10% to ~30% will trigger displacement of the polarized ion source to LU-20
  Nuclotron injection energy - 5 MeV/n
  Particle number will be limited by betatron tune shift at Einj to ~2.5∙1010 for H and ~5∙1010 for D (eRMS=3 mm, 2.5smax=16 mm, Dn=0.2)
I would not exclude short runs with acceleration of polarized D in the 2nd half of 2025
  2026 looks more realistic
If LU-20 will be out of operation we still can inject polarized D through HILAC and Booster – such operation was recently tested
  It will require new line connecting the Ion source and HILAC

## Slide 7
Acceleration of Protons in Nuclotron
We plan to install SC solenoid into Nuclotron to support proton beam acceleration without loss of polarization
Presently, two Nuclotron straights are taken by RF cavities
In the future we want to replace these cavities by SC solenoid and new RF cavities which are identical to the Booster RF
  The SC solenoid of ~2*12 T m is in advanced stage of design
  BINP will be ready to start work on new RF system in the 2nd half of 2025
Solenoid
  Current – 6.9 kA
  Bmax - 5 T
  Stored energy - 640 kJ

## Slide 8: Commissioning plan Presented at coordination committee meeting Oct. 24, 2024
Starts: 25.12.2024
 | 2024 Дек. | Январь | Февр. | Март | Апрель | Май | Июнь | Июль | Август | Сент.
Комплексные испытания систем коллайдера: |  |  |  |  |  |  |  |  |  | 
Охл. западной арки |  |  |  |  |  |  |  |  |  | 
Охл. восточной арки |  |  |  |  |  |  |  |  |  | 
Охлаждение Бустера |  |  |  |  |  |  |  |  |  | 
Пучки в Бустере |  |  |  |  |  |  |  |  |  | 
Охлаждение Нуклотрона |  |  |  |  |  |  |  |  |  | 
Пучки в Нуклотроне |  |  |  |  |  |  |  |  |  | 
Настройка каналов в Колл. |  |  |  |  |  |  |  |  |  | 
Инжекция в Колл. (CCW) |  |  |  |  |  |  |  |  |  | 
Ускорение в Колл. |  |  |  |  |  |  |  |  |  | 
Начало работы MPD мишень |  |  |  |  |  |  |  |  |  | 

## Slide 9
Booster Run – January 2025
E-cooling system
Reference magnets section
Nuclotron ring
Injection system
Power supply & energy evacuation
RF system
Fast Extraction system
Synchrophasotron iron yoke
Parameter | Value
Circumference, m | 210.96
Lattice type | DFO
Injection energy, MeV/u | 3.2
Maximum energy, MeV/u | 578
Magnetic rigidity at injection, Т∙m | 1.6
Maximum magnetic rigidity, Т∙m | 25.0
Ions species (project) | 124Xe28+

## Slide 10
Beam Accumulation with Electron Cooling
An increase of ion accumulation intensity by a factor of 5 is planned. However, the intensity is restricted by ion bunch space charge at the level of (1-2)109 ions of Bi35+
Beam accumulation happens in the longitudinal plane at Booster injection
  4 ms bunch – 8 ms revolution time
Each new injection happens after the previous one is cooled to the core
  Expected injection rate – 10 Hz
  10 – 15 injections will be required
  Total cycle duration ~5 s
The permanently present 1st RF harmonic weakly affects large amplitude particles
For small amplitude particles the cooling force will be intentionally reduced to avoid overcooling
To avoid anti-coolig we need to match well the injection magnetic field and e-beam energy
  It happens since for large Dp/p, dF/dt changes sign after reaching the peak
The run of KRION-6T - HILAC - Booster will be with Xe ions with the goal of commissioning of multi cycle injection and accumulation supported by electron cooling. The run will proceed in Jan.-Apr. of 2025

## Slide 11
Start configuration (magnetic rigidity up to 29 T·m)
Full configuration (magnetic rigidity up to 38.5 T·m)
Nuclotron Extraction System
Application of one extraction Lambertson magnet permits to reach the maximal kinetic ion energy 2.5 GeV/n in first Collider beam runs
Nuclotron run –April 2025

## Slide 12
Commissioning start - Winter 2025
Technological run at cryomagnetic system testing
West arc W– February 2025
East arc E- March 2025
First beam run – Summer of 2025
Collider equipped with
RF-1 (barrier voltage system) for ion storage
RF-2 : 4 cavities per ring instead (100 kV RF amplitude)
Longitudinal S-cooling - 1 out of 4 channels for each ring
Result: 22 bunches of the length   2 m per collider ring that 2e25 cm-2s-1, ion kinetic energy E=2.5 GeV/n
NICA Stage II-A (basic configuration)

## Slide 13: The Magnetic System: Regular Period
13
13
Dipole unit
Quadrupole unit
Parameter | Dipole | Lens
Number of magnets (units) | 80 | 46
Max. magnetic field (gradient) | 1.8 T | 23.1 T/m
Effective magnetic length, m | 1.94 | 0.47
Beam pipe aperture (h/v), mm | 120 / 70 | 
Distance between beams, mm | 320 | 
Overall weight, kg | 1670 | 240
Dipole unit
Comissioning W arc-December 2024, commisiong of E arc –February 2025

## Slide 14: NICA Commissioning. The magnetic system: magnets
14
Final focusing quadrupoles
BI vertical 1х dipole units
Quadrupole units
4х Quadrupole units

## Slide 15: Straight Sections: Magnets
15
Straight section
Q1
Q2
Q3
Straight sections and MPD final focus
BV1
BV2
ВВК Y
Straight section lenses
Final focuse lense
Vertical magnets

## Slide 16: RF system: status RF1 and RF2
16
RF1
RF2
RF2
RF2
All RF1 and RF2 cavity in JINR.
Two RF1 and eight RF2 cavities were installed.
Commissioning of E-arc- February 2025
RF1 and RF2 in tunnel

## Slide 17
17
Collider Beam Injection Septa
Septum cryostat module
Septum’s internal chamber with feedthrough
Effective length, m | 2.5
Max. magnetic field, T | 0.42
Bending angle, mrad | 24
Gap, mm | 30
Septum thickness, mm | 3
Current, кA | 50
Pulse duration, µs | 10
Commissioning of Collider injection system –February 2025

## Slide 18
Collider Power Supply System
68 Additional power supplies (10В х 300А)
12 energy evacuation keys
were built and tested
Each collider ring has its own power supply system based on 3 main current sources
2 sets of main PS for both collider rings are manufactured by NPP "LM Inverter"
and delivered to JINR.
Busbars system model in b.17
First operation of PS and magnets- February 2025

## Slide 19: Technological run of cryomagnetic system testing West arc W– February 2025 East arc E- March 2025
I. Collider cryo-magnetic tests:
Tests of Power supplies on an equivalent load
Tests of energy evacuation switchers
Vacuum of isolation volume
High vacuum of beam chamber
Operation of control system
Magnet system cryogenic cooling
Thermometry tests
Operation of quench protection and evacuation system
Formation of magnetic cycle, power supplies tuning
Corrector system tuning
Serious situation with infrastructure of Bld.17: Power distribution, Water cooling, Ventilation and air-conditioning

## Slide 20: Status of cryogenic compressor station
Commissioning and tests of nitrogen centrifugal compressor Aerocom - 2 179/18 and two nitrogen centrifugal compressors Hanwha Techwin SM5000 were done. Compressors passed through tests in air medium and ready for testing in NICA cryogenic nitrogen system.
Аerocom - 2 179/18
Hanwha Techwin SM5000
Spiral helium compressor
Commissioning and tests of two spiral helium compressors «Каskad- 110/30» was performed by Heliomash company which will provide repairs of this system.

## Slide 21
Parameters of pulsed magnet elements
Nuclotron-Collider Beam Transport Channel
Magnetic element | Number | Effective length, m | Max. magnetic field (gradient), T (T/m)
Long dipole | 21 | 2 | 1.5
Short dipole | 6 | 1.2 | 1.5
Quadrupole Q10 | 22 | 0.353 | 31
Quadrupole Q15 | 6 | 0.519 | 31
Dipole correctors (BINP) | 33 | 0.466 | 0.114
Nuclotron-Collider transfer line was contracted with French company Sigma Phi
Magnets delivery in JINR in February 2021
JINR could not receive some parts of already built equipment: power supplies, beam diagnostics, dipole correctors, vacuum chambers and support stands.
JINR restarted design and production of this equipment in Summer 2023. We plan to produce and install this equipment before Summer 2025.
First beam tests – July 2025
Critical point is the construction of pulsed power supplies for magnets.

## Slide 22: The first Collider Run with Beam
22
1. Injector chain: KRION => Booster => BTL BN => Nuclotron
2. BTL Nuclotron => Collider
3. Collider equipped with
RF-1 - (barrier voltage system) for ion storage
RF-2 - 4 cavities per ring (100 kV RF amplitude)
4. Date for MPD roll-in is not set (earliest the end of summer 2025)
NICA Stage II-a (basic configuration): starts at April 2025
Result: 22 bunches of the length   2 m per collider ring that 2e25 cm-2s-1. Maximum kinetic ion energy 2.5 GeV/n
 | Booster |  | Nuclotron |  | Collider
 | Injection | Extraction | Injection | Extraction | 
E | 3,2 МeV/u | 530 МeV/u | 523 МeV/u | 1,5-2,5 GeV/u | 1,5-2,5 GeV/u
N | 5108 | 3.5*108 | 2.5*108 | 2*108 | Injection - 2*108 Accumulation in RF1 - 4*109 Formation of 22 bunches by RF2)
Вd, Тл | 0,1 | 1,6 | 0,4 | <1,2 | <1.2
Dependence of luminosity on number ions per bunch
at different energies (1) 4.5 GeV/u (2) 3GeV/u, (3) 2 GeV/u, (4) 1 GeV/u.
Collision of bunch to bunch
N=2E8

## Slide 23
Thank you for your attention

## Slide 24: Backup slides

## Slide 25
25
Area of Fixed Target Experiments
Nuclotron
(38.5 Tm, 251.5 m)
injection of one bunch
of 0.8∙109 ions,
acceleration up to
1 - 3.85 GeV/u
Linac LU-20 (5MeV/u)
Ion sources
Booster (2021)
(25 Tm, 211 m)
~10 one-turn injections Xe28+ ,
storage up to 1×109 ions
with electron cooling,
Acceleration to 550 MeV/u
Later transition to 209Bi35+
Linac HILac (3.2MeV/u)
ESIS KRION
NICA – collisions for Heavy ion mode
Two SC rings of the collider by 503 m
NICA – Stage II, E=1 - 4.5 GeV/u
~ 2 x 22 injection cycles
22 bunches per ring
Baryonic Matter @ Nuclotron
BM@N: NICA – Stage I
(was realized in 2023)
s = 2.3 – 3.6 GeV/u (Au  Au)
MPD
Operation 2016.
2018
2020
2025
Stripping (80%) 209Bi35+ =>209Bi83+
L ≥ 1027см-2с-1 @ ~4.5 GeV/n

## Slide 26: HILac status
HILAc status
Stable and safe HILAC operation during with Ar13+ and Xe 28+ beams
Yellow line - at RFQ exit I=100 mA (). Redish line - at HILAC exit I=65 mA.
Ion pulse duration 22 ms, about 70% at this pulse of target ions 124Xe28+.
Number of ions accelerated in HILAC at energy 3,2 МeV/n is about 1108.
Project HILAC intensity 209Bi35+ at energy 3,2 МeV/n is about 1.8109 per pulse.
=> Further development
I.e. realization of multi cycle injection with electron cooling and upgrade of KRION-6T
4