## Slide 1
Viacheslav Golovatyuk
(JINR)
Status of the MPD integration

## Slide 2
MPD - stage I
MPD - Stage II
Momentum resolution with TPC
8970
6583
Momentum resolution in the forward direction
Particle identification capability

## Slide 3
The Magnet of MPD
Konstantin Mukhin (JINR)
Short list of Activities;
Liquid He an N2 lines have been constructed and mounted
The Solenoid Cold mass was cooled down to the working temperature
Superconducting regime inside of the of the Solenoid Cold mass has been achieved
Power Supplies were included into the Solenoid Control and Monitoring system.
Training procedure of supplying current to the Solenoid is going on
At the moment Magnetic field monitoring system based on Hall probes shows the field
We have managed to gather a strong team of cool specialists working under the leadership of Konstantin Mukhin able to solve the most difficult engineering tasks.
The magnet platform with cryostat, satellite refrigerator, MFS, heaters, control system, power supply and many other systems

## Slide 4
B-field Mapper
Evgeny Antokhin, INP Novosibirsk
Concept of Novosibirsk INP mapper:
One - 3D Hall probe moves in 3 directions: z , R and ϕ
Accuracy: 0.3 Gs
Range of fields: 0.3 - 0.57 T
Reference system - 40 stationary sensors of Magnetic Field
 | Along radius (R) | Along azimuth angle (φ) | Along the axes of Solenoid (Z)
Step size, см | 5 | 21 | 10
Total length, см | 220 | 360О (1380 см on max. R) | 700
Number of measurements | 44 | 64 | 70
The total number of measurements: 44 х 64 х 70 = 197120 (200000)
Total time of one cycle of measurements: 1,5 сек
Fields to measure : 0.57Т; 0.53Т; 0.5T; 0.45T; 0.4T; 0.3T – In total - 6 nominals of field.
For each field one need about 5 adjustments of current in correction coils
In total: 6 fields х 5 adjustments = 30 cycles.
Total time of field measurement run is about 3 months

## Slide 5
Monitoring Hall Probes
Регулировочные винты
Прижимные болты
Cube with Hall Probes
Приварной кронштейн
Линейка
Планка
290
1830
1830
In total there are 40 pcs of 2D Hall probes in the monitoring system

## Slide 6
24 pc. of serial ROCs + 4 spare are READY
MPD Time Projection Chamber
Sergey Movchan
4 planes with laser beams
For TPC calibration
Laser beams scheme for ½ TPC
Many thanks to Arkady Taranenko!
A team of laser experts -2 seniors (Star-Aliсe experience) + 2 young engineers from MIPHI (Laser Institute) start participation in the TPC laser calibration system
Their contribution is already have been seen.
Beams
FE electronics 100% manufactured (1488 FECs)

## Slide 7: Status and Time schedule
TPC sub-systems status:
TPC vessel assembling in progress
ROC chambers (24+6 spare) ready
FE electronics 100% manufactured (1488 FECs)
R/O controller v1.2 start of manufacturing
Gating grid system ready, long term test at Minsk in progress
HV+LV systems (CAEN) ready for start installation to MPD TPC racks on ”Electronics” platform
Gas system ready, wait of gas piping at MPD building
Cooling system in progress (start of Still and Cu collectors manufacturing)
Laser system in progress (calibration of 8pc TPC rods with micro-mirrors, installation to TPC skeleton)
Slow control system in progress (LV+HV sub-systems based on MasterScada 4D ready, for rest sub-systems – started)
TPC schedule:
TPC:
TPC vessel will be assembled and tested June 15 2025.
ROC chambers installation July – August 2025.
  TPC tests (with laser tracks and cosmic ray) Sept - Oct 2025
  TPC rails and TPC installation tooling:
  Rails installation to ECAL support structure done
  Tooling for installation TPC to MPD delivered to JINR
  TPC+ECAL cooling systems (INP BSU, Minsk):
  Systems assembling and start up done (3 water vessels and 3 pump modules are assembled and tested at MPD)
  TPC installation to MPD Nov 23 2025
  Cabling and piping June 22 - Nov 2025
  MPD commissioning Dec 2025

## Slide 8
Status of the TOF MPD
V.Babkin

## Slide 9
ECal consist of 50 baskets (2400 modules)
The last bunch of 400 modules will be produced till the June 2025,
though some of them without light wave shifter (fibers)
The company which provides fibers (light shifter) is busy and cannot produce shifters for this last bunch of 400 modules as soon as we need them.
Officially they have declared the productivity – 6 km per month ( February 2026 – whole bunch of fiber should be produced.
However promised to deliver all shifters before December this year
As soon as readout fibers arrive we will insert them into produced modules before assembling half sectors.
We will have 45 baskets till the middle of August, the rest 5 baskets could be produced till the end of November.
In some circumstances we also consider their installation in the MPD after TPC in December.
Still a lot of work to be done with cooling system.
Electromagnetic Calorimeter (ECal)
Igor Tyapkin (JINR), Yi Wang (Tsinghua University)
ECal – Tsinghua University., Yi Wang
Shandong University
Fudan University
South China University
Huzhou University
JINR – production in IHEP (Protvino) and Tenzor (Dubna)

## Slide 10
FHCal
Two arms of hadron calorimeter at opposite sides in forward regions.
At the distance 3.2 meters from the interaction point.
Available acceptance corresponds to pseudorapidity 2.0< <5.0
FHCAL consists of 2x44 modules.
~1x1 m2 each part.
Beam hole 15x15 cm2.
Lead/scintillator sampling calorimeter.
Longitudinal segmentation;
Light readout- WLS-fibers;
7 sections/photodetectors in each module.
FHCal in MPD
Aleksandr Ivashkin (INR, Russian Academy of Science)
Test of procedure of installation of the assembled FHCal inside of the Pole

## Slide 11
Control of luminosity at the interaction points in the collider NICA
JINR working group
SiPM
SiPM
Detector circuit
one shoulder front view
The detector consists of plastic
scintillator strips viewed from both sides with silicon photomultipliers (SiPM)
) |  |  |  | 
Tasks which have to be solved by the detector
Assistance in controlling the transverse sizes of the bunches
Assistance in setting up transvers convergence of bunches
Assistance in setting up longitudinal convergence of bunches
Control of the distribution of vertices in the longitudinal direction.

## Slide 12
Tooling for subsystems integration
Tools for installation of Ecal, TOF are ready. For TPC – will be ready soon.
Our plan is to test Ecal half sector installation into Support Frame.
There is a plan to have two identical platforms from both sides of the Solenoid. The first one is ready, the second is produced and waiting for assembling.

## Slide 13
Test of the Support Frame installation
Within the program of testing installation procedure of MPD subsystem, we also have tested insertion the Support Frame inside of Magnet.

## Slide 14
1 | January 13th- 30th | Solenoid and Correction Coils Power Supplies control system tests
2 | January 25th – February 21st | Solenoid Safety regimes of emergent energy evacuation working out Development of algorithms of cooling on base of experience with manual regime
3 | February 1st – February 27th | Solenoid Power cable temperature isolation inside of the Chimney
4 | March 3d – April 7th | Cooling down of the Solenoid to the working temperature 4K
5 | April 7th -April 30th | Development procedure of current supplying to the Solenoid, training
6 | April 20th – 30th | Installation stationary Hall probes (both INP Novosibirsk and Belorussia)
7 | April 1st - April 20th | Final test of the Field Mapper at Novosibirsk
8 | April 28 | Delivery Mapper to the JINR
9 | May 10th – May 18th | Installation Magnetic Field Mapper, Calibration, preparation for measurements of Field
10 | May 20th - July 30th | Magnetic field measurements on nominals: 0.2Т, 0.3Т, 0.4Т, 0.45Т, 0.5Т, 0.55Т
11 | June 15th | TPC mechanical body is assembled, leak test and HV test are finished
12 | August 4th – August 22d | Installation FHCal into poles
13 | August 6th – September 25th | Ecal installation
14 | August 20th – September 30th | Installation TOF modules (access from both sides )
15 | November 1st – December 20th | TPC installation and test
16 | June 22d – November 30th | Cabling
17 | December 4th – December 14th | Beam pipe installation
18 | December 22d | Moving to the beam line
19 | December 30th | Readiness for Data taking
Milestones of MPD assembling in the year 2025

## Slide 15
Summary
All components of the 1st stage detector are advancing in production.
We start activities on the integration subsystem into MPD.
The efforts of the MPD groups are put on the execution of the schedule plan with minimal delays.

## Slide 16
Thank you for the attention

## Slide 17
Detector upgrade ideas
Forward tracker 𝜼 < 2,5
Decreasing of the TPC material budget in the forward direction (cables, electronics reorganization)
Replacement of proportional chambers (ROC TPC) by other gas detectors (GEM, MicroMegas, TMWPC)
Replacement of the TPC by new tracker based on contemporary technology
Forward TOF (up to 10000 channels). Using a picoTDC allows to get time resolution around 40 ps
Modification of Ecal electronics to provide trigger signal and time resolution better then 50 ps. (maybe specialized chip)
Development of forward fast detector for triggering with time resolution < 200ps and
space resolution < 200mkm
8. Construction of the ITS system (Stage 2)

## Slide 18
А new platform on the South side of MPD and other infrastructure
A platform on the south side of MPD is ready.
Besides Cooling system of TPC second floor of this platform is planned for ITS electronics which is the second stage of detector (basic configuration).
This picture shows the position of the MPD on the collider beam line.

## Slide 19
Fast Trigger L0 for MPD
Vladimir Yurevich (JINR)
The vertex resolution for Au-Au collisions at √s=5GeV/n for three distances from interaction point
Beam crossing fast signal from Collider is needed in trigger for determination of FFD efficiency for peripheral collisions
FFD provides information on
- interaction rate ( luminosity adjustment )
- bunch crossing region position
- as part of TOF – gives T0 signal
15 mm quartz radiator
10 mm Lead converter
The FFD sub-detector consists of
20 modules based on
Planacon MCP-PMTs
80 independent channels plus
The position of the FFD in the MPD