## Slide 1: Status of the solenoid start-up
Speaker: K. Mukhin
JINR, LHEP 2025
XVI Collaboration Meeting of the MPD Experiment at NICA
28/10/2025
From drawing
to detector

## Slide 2: Plan of talk
Magnet construction and some parameters
Chimney area and determination a problem after cooling
-Power supply system
-Power supply at CS coil
-Current leads problem
Feld mapper
Timeline

## Slide 3: Chapter 1 Magnet construction and parameters

## Slide 4: MPD in NICA complex
SPD
BM@N
Booster
Nuclotron
N I C A
MPD

## Slide 5: MPD magnet construction and surprise from ASG
Parameters of the magnet | 
Magnetic field | 0,57 T
Cryostat weight and size (diameter/length) mm | 66 tons 5443/7910
Yoke weight and size (diameter/length) mm | 630 tons 6583/8970
Current Voltage | 1790 A 10V
Each pole weight | 45 tons
Total weight with support equipment | 800 tons

## Slide 6: Superconductor cable
Original SC cables for MPD
Winding and tests of SC cable in ASG
SC cables parameters
SC Materials – NbTi/Cu.
Cable composition is pure aluminum matrix (4,1 x 20 mm) and inside string of Cu/SC ratio 0,9/1 (d – 1,5 mm).
Insulation – kapton tape, glass tape and epoxy resin.
Critical current (1,2 T, 4,5 K) – 6,9 kA
Cable length - 27 km.
Cable weight – 6,3 tons
LHC 27 km

## Slide 7: CS coil winding
-
+

## Slide 8: Chapter 2 Chimney area and determination a problem after cooling -Power supply system -Power supply at CS coil -Current leads problem

## Slide 9: Power supply system

## Slide 10: Stability test of power supplies
Power supply of solenoid I = 2500A V= 10V
Power supply of TRIM1
I = 3000A V= 70V
Power supply of TRIM2
I = 1300A V= 45V

## Slide 11: Cryogenic infrastructure
Control Dewar
Refrigerator
NTCS (Nitrogen temperature correction system)
LN2 and LHe heaters
LHe pipe
Cryogenic flexible connection pipes
LN2 Tanks (2 pc)
LHe Tanks (2 pc)
LN2 transfer pipe 120 m
Warm pipes for He, N2 and instrumentation Air
Flexible warm pipes
Support system for flexible pipes

## Slide 12: Cooling process scheduled
Total cooling time – 28 days
Nitrogen mode – 14 days
Transient mode – 6 days
Helium mode – 8 days

## Slide 13: 10/04/2025 current 750A (0,2 T)

## Slide 14: Superconductor cable, Dewar, chimney area
LHC 27 km
Chimney area assembling

## Slide 15: Chimney area
CS cable
No thermal contact to LH pipe
LH pipe have square cross-section for maximum contact with the CS

## Slide 16: New chimney area

## Slide 17: Additional temperature sensors in Dewar and chimney area

## Slide 18: Additional temperature sensors 29/05/2025
Additional temperature sensors in chimney area
15, 14, 1, 18 – cernox temperature sensors
A, E – voltage taps sensors
- Positions of new temperature sensors

## Slide 19
Chimney area
Touching SC cable of LHe manifold circle pipes on cold mass
It was lucky that the electrical insulation was not broken!
Available area
There are NO any supports
Mechanically fixation cable into control Dewar

## Slide 20: Current 1050 A – 0,3 T (13/10/2025)
Current 0
Current 1050A
0,3T

## Slide 21: SC cables connect to current leads into control Dewar
LHe pipe
Sky view
SC cables
Installation box
Copper stationary plate
Copper clamp plate
SC cable
Insulation plate

## Slide 22: Current leads
Project by TS Neva magnet
Actual CL by ASG
Current lead test (ASG)
Electrical and thermal contact by 2 screw m6

## Slide 23: Chapter 3 Field mapper

## Slide 24: Stationary magnetic field monitors
Current 1050A

## Slide 25: Field mapper in solenoid
04/09/2025 mapper was delivered to MPD hall
16/07/2025 test mapper in Novosibirsk
From 06/10/2025 assembling and test in MPD solenoid
26-27/10/2025
Measuring in one stationary point (730,6 A)

## Slide 26: Timeline
For present day we ready to mapping magnetic field to 1050 A (0,3 T)
27/10/25 – 31/10/25 – test measurement 0,2 T
0,3 – 0,7/11/2025 – processing of results and determination of magnetic axis
10 – 12/11/2025 – mapping by correction current 0,2 T
12 – 24/11/2025 – processing of results and confirmation of homogeneity (3*10-4) by 0,2 T
0,1 – 12/12/2025 – mapping, processing of results and confirmation of homogeneity (3*10-4) by 0,3 T
15 – 19/12/2025 – calculations and presents of results a number of current to 0,25 T (homogeneity (3*10-4))
19-25/12/2025 – checking calculations and mapping the 0.25T field
25/12/2025 – 10/01/2026 – warming and open Dewar
10 – 25/01/2026 – modernization of current leads
26/01 – 12/02/2026 – cooling and current up
13/02 – 20/02/2026 – mapping 0,4 T (1400A) field by calculations from Novosibirsk group
20/02 – 28/02/2026 – mapping, processing of results and confirmation of homogeneity (3*10-4) by 0,5 T

## Slide 27: Thank you for attention