## Sheet 1
STRAW BARREL |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
prototyping - prototypes of individual elements | StrawMassProd
prototyping - small tracker prototypes and mockups | DetectorProd
longevity tests | DetectorProd
sixtant prototype construction | DetectorProd
sixtant prototype testing (mech+readout) | DetectorProd
prototyping of the tracker frame ()
Development of the straw mass production lines | StrawMassProd
straw mass production | StrawMassProd
quality control of the produced straws | StrawMassProd
Production of first sixtant | DetectorProd
Production of the first traker frame | DetectorProd
5 sixtant production 2 team | DetectorProd
production of tracker frames | DetectorProd
sixtant quality control and final assembly 2 teams | DetectorProd
tracker installation | DetectorProd
gas supply system R&D | gas
gas supply system prototyping | gas
gas system protype testing | gas
gas system production, maintenance and testing | gas
gas system integration and commissioning | gas
readout electronics R&D | readiout
readout electronics production, maintenance and testing | readiout
installation, integration and commissioning | readiout
LV and HV prototyping | LV+HV
LV and HV production/procurement, maintenance and testing | LV+HV
installation, integration and commissioning | LV+HV

## StrawMassProduction
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
preparation of the production hole JINR
preparation of the production hole INP
preparation of the storage area JINP
preparation of the storage area INP
development of new welding line
design
procurement JINR
procurement INP
assembling JINR
assembling INP
commissioning JINR
commissioning INP
start of mass production with new line JINR
start of mass production with new line INP
development of the quality control procedure
development of the pressure test
development of the express-test
qc data-base
longevity studies
evaluation of the maximal accumulated charge
irradiation test
choice of glue
straw design
choice of the foil
choice of pin
choice of endplug
procurement
mass production

## DetectorCostruction
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments

## gas
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments

## readoutelectronics&DAQintegr
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments

## LV+HV
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments

## Infrastructure
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments

## alignment
| 2024 | 2025 | 2026 | 2027 | 2028 | 2029
geometry optimization
simulation studies
mockup production
interface developments