## Slide 1: CBM STS tracking system for BM@N
Johann M. Heuser, GSI Darmstadt for the CBM-STS team 2nd Collaboration Meeting of the MPD and BM@N experiments at NICA 29 – 30 October 2018, JINR-VBLHEP, Dubna
Progress with CBM-STS
System definition of BM@N-STS
CBM-STS timeline, links to BM@N planning

## Slide 2: I. Progress with CBM-STS

## Slide 3: STS in CBM Experiment at FAIR
Beam
Dipole Magnet
RICH
Ring Imaging Cherenkov
TRD
Transition Radiation Detector
TOF
Resistive Plate Chambers
MVD
Micro Vertex Detector
STS
Silicon Tracking System
MUCH
Muon Detection System (parking pos.)
ECAL
Electro- Magnetic Calorimeter
PSD
Projectile Spectator Detector
Tracking acceptance:
lab
2o <  < 25o
Free streaming DAQ
Rint = 10 MHz (Au+Au)
with
Rint (MVD) = 0.1 MHz
Software based event selection
Target

## Slide 4: Silicon Tracking System
Central CBM detector: charged-particle tracking + momentum measurement
Challenges:
up to ~ 700 charged particles per heavy-ion collision  high granularity
105  107 heavy-ion collisions per second  fast, radiation tolerant
Technical solutions:
8 tracking stations,  4 m2 total area, 896 detector modules, 106 ladders
double-sided silicon microstrip sensors
  hit spatial resolution  25 µm
  material budget per tracking station:  0.3% – 2% X0
  radiation tolerance up to 1 × 1014 n/cm2 (1 MeV equivalent)
self-triggering electronics, time-stamp resolution  5 ns
low-mass detector modules/ladders
Construction: 2019 – 2023 Install in CBM: 2024 Physics: 2025 …

## Slide 5: Silicon Tracking System

## Slide 6: Silicon Tracking System

## Slide 7: System Engineering
Global system aspects:
STS services, mechanic supports and details
  Cabling
  Cooling
  Positioning
  Safety / emergency systems
  Integration upstream and downstream
  vibrations / structural analysis
Thermal enclosure:
Sealing
Panel connections
Material budget rear panel
Overall stiffness
C-Frame positioning / measurement / adjustment concept
Service / support mechanics
Overall assembly procedure is an idea
Mechanical frames:
Sensor cooling
Cooling plate shape / technology
Cabling not tested
Material
Rail system
Positioning / Adjustment
Consistent design being worked on. Current issues:

## Slide 8: Updated Performance Studies
detector model with passive materials
track reco efficiency
momentum resolution
physics observables
data rates
delta electrons
...

## Slide 9: STS – exploded view
(18 variants)
(17 variants)

## Slide 10: Silicon Microstrip Sensors
6.2 x 2.2 cm2
6.2 x 4.2 cm2
6.2 x 6.2 cm2
6.2 x 12.4 cm2
double-sided
1024 strips of 58 µm pitch
4 variants/strip lengths
final prototypes realized with two vendors:
  CiS, Germany
  Hamamatsu, Japan
Internal Sensor Review: April 2018
Tendering: August – September 2018 Offers received, negotiations ahead
Aim: Production 2019 – 2020

## Slide 11: Front-end ASIC and read-out electronics
current prototype STS-XYTER v2.0
STS-XYTER v2.1 submitted
Front-end electronics board FEB-8
Common Read-out Board test chain with GBT chipset
(not applicable to BM@N)
128 channels
self-triggering
5 bit ADC, time resolution < 5 ns

## Slide 12: Micro-cables
cable stack: thickness ~ 800 µm / 0.23% X0
meshed spacer layer
signal layer: 64 Al lines of 116 µm pitch, 14 µm thick on 10 µm polyimide
64 traces per signal layer
2 signal layers per cable
8 cables per sensor side
trace lengths 5 - 55 cm
trace capacitance 0.45 pF/cm
N-side read-out
P-side read-out
tab-bonding of 2 signal layers to Al pads on ASIC and sensor
Alternative Cu cable under test.
(foam spacers also)

## Slide 13: STS assembly centers: GSI and JINR
GSI Detector Laboratory
STS Lab at JINR-VBLHEP
realized in GSI + JINR cooperation
with BMBF-JINR funding (2015) and EU-H2020 CREMLIN grants
150 m2 clean rooms, Solid State Section
600 m2 clean rooms (2nd floor), 600 m2 gray rooms + workshops (1st floor)

## Slide 14: Module assembly satellite to GSI: KIT
Institute for Process Electronics Laboratory
Karlsruhe Institute of Technology, Germany

## Slide 15: Module assembly at GSI
First full-size module for mSTS

## Slide 16: Module assembly at GSI

## Slide 17: Module assembly at JINR-VBLHEP
first fully read-out module

## Slide 18: Module test stand at GSI
FEB-8 mounted on cooling fins
sensor
90Sr
microcables and shield
longest in STS (50 cm)
FEB-8
connections to power supplies and read-out system, DAQ

## Slide 19: First STS module with full 2-side r/o
-source spot
noise
detailed study ongoing
sensor
90Sr
microcables and shield
longest in STS (50 cm)
FEB-8
2 x 1024 channels (front/back side)
gain uniformity

## Slide 20: Ladder assembly at GSI
module #0 installed on ladder;
module #1 on transfer tool
application of glue onto L-legs
transfer of module #1 to ladder
module #1 tansferred, fixed during curing of glue
ladder #0 for mSTS

## Slide 21: mSTS in mCBM at SIS18
mSTS
https://fair-center.eu/for-users/experiments/nuclear-matter-physics/cbm/projects/mcbm.html
Demonstrator experiment for data transport and online event finding from prototype detector systems to the Green IT Cube
  mSTS
  mMUCH
  mTRD
  mTOF
  ...
  2018 – 2020/21/22

## Slide 22: mSTS system
station #0: C-frames #0 and #1
station #0 area 12 x 12 cm2
2 tracking stations: #0: 2 ladders à 2 modules (2018) #1: 3 ladders à 3 modules (add 2019)
mSTS box with C-frames
 installation into mCBM: 11/2018
assembly of ladder #0

## Slide 23: II. System definition of BM@N-STS

## Slide 24: STS in BM@N-2 experiment at Nuclotron
STS

## Slide 25: Workshop on DSSD-GEM Tracking System for BM@N-2
JINR News 10 July 2018: http://www.jinr.ru/posts/joint-plans-for-the-nearest-future/
 Indico agenda
5-6 July 2018
at JINR LHEP
BM@N upgrade for high intensity Au beams
BM@N simulations
BM@N-STS layout
R/o electronics, DAQ
CBM-STS status and project plan, link to BM@N-STS

## Slide 26: Tentative layout of the STS for BM@N2
8 x 294 mm
pin to pin ladders
8 x 414 mm
pin to pin ladders
12 x 414 mm
pin to pin ladders
12 x 414 mm
pin to pin ladders
Num. of modules | Size of the sensor
24 | 62*62 mm
8 | 42*62 mm
4 | 42*62c mm
Num. of modules | Size of the sensor
28 | 62*62 mm
4 | 42*62 mm
4 | 42*62c mm
12 | 22*62 mm
Num. of modules | Size of the sensor
44 | 62*62 mm
4 | 42*62 mm
4 | 42*62c mm
20 | 22*62 mm
Num. of modules | Size of the sensor
68 | 62*62 mm
4 | 42*62 mm
4 | 42*62 mm
20 | 22*62 mm
36 modules
48 modules
72 modules
Total numbers: 252 modules, 40 ladders
96 modules

## Slide 27
Geometries
bmn_v18a
10 cm
bmn_v18b
15 cm
bmn_v18c
20 cm
implemented for simulations (E. Lavrik, Univ. Tübingen)

## Slide 28: Simulation studies
E. Lavrik, Univ. Tübingen:
geometry studies
hit occupancies
tracking efficiency
momentum resolution
physics observables

## Slide 29: III. CBM-STS timeline, links to BM@N planning

## Slide 30: CBM-STS Project Plan
technology + procedure freeze
Official planning document at GSI-FAIR, together with other planning documents from CBM, civil construction and accelerator.
General timeline: 2018 – 2024
Pre-production phase: until Q3/2019 (mSTS completed with 2 tracking stations)
    development of final components and prototypes, as well as assembly methods
Production readiness: reviews/milestones - including:
  STS module/ladder assembly procedure: 9/2018
  STS sensors ready for order 10/2018
  STS Core Preliminary Design Review: 11/2018
Production phase: 2019 until 2024 2/2024 STS ready for installation

## Slide 31: CBM-STS Project Plan summary
Task Name | Start | Finish
STS ready for installation | 22-02-24 | 22-02-24
STS assembly and commissioning in lab | 25-02-21 | 25-01-24
Ladder assembly (GSI) | 21-05-20 | 18-05-23
Ladder assembly (JINR) | 18-06-20 | 18-05-23
Module assembly (GSI) | 30-01-20 | 15-09-22
Module assembly (KIT) | 30-01-20 | 15-09-22
Module assembly (JINR) | 27-02-20 | 15-09-22
STS-XYTER ASIC production | 07-06-19 | 02-07-20
Microcable production | 06-04-19 | 12-04-21
FEB-8 production | 19-03-19 | 17-02-20
Sensor production | 10-01-19 | 07-12-20
STS-XYTER ASIC production readiness review | 06-06-19 | 06-06-19
Sensor tendering completed, orders placed | 27-02-18 | 10-12-18
STS core readiness | 30-10-18 | 30-10-18
Module/ladder assembly readiness [internal] | 15-09-18 | 15-09-18
Sensor readiness | 23-04-18 | 10-10-18

## Slide 32: Upcoming CBM-STS milestones
Sensor Readiness completed ............................................... (10/2018)
  Reviews held in 3/2017 and 4/2018
  Summary report – Technical Note close to finalization
Sensor tendering:
  Deadline for reception of offers .............................................. (28/9/ 2018)
  Negotiations with vendors, orders placed .............................. (10 - 12/2018)
Module/ladder assembly readiness [internal] .................... (15/9/2018)
STS core readiness ............................................................... (11/2018)
mSTS with tracking station 0 installed in mCBM ................. (11/2018)
Start of sensor production ................................................... (1/2019)
Start of FEB-8 production ..................................................... (3/2019)
Start of microcable production ............................................ (4/2019)
STS-XYTER ASIC production readiness review ...................... (6/2019)
Start of STS-XYTER ASIC production ...................................... (7/2019)
mSTS with tracking stations 0 and 1 installed in mCBM ...... (Q3/2019)

## Slide 33: Links to BM@N-2 STS planning
CBM-STS construction model fully detailed
  modules and ladders exactly defined: 11/2018
  available for BM@N-STS construction model
CBM-STS front-end electronics and read-out chain demonstrated
  start adaptation for BM@N: in the course of mCBM preparation and running: 11/2018
  including prior definitions of BM@N r/o needs, e.g. at this meeting
CBM-STS modules – first of series available
  lessons learned from mSTS: 11/2018, Q3/2019
  start producing modules for BM@N-STS: 2/2020
CBM-STS ladders – first of series available
  lessons learned from mSTS: 11/2018
  start producing ladders for BM@N-STS: 6/2020
  In order to use the same module and ladder make in BM@N as later in CBM:
modules available in larger numbers for BM@N earliest from mid 2020 on
ladders available in larger numbers for BM@N-STS earliest from end 2020 on
a few prototypes may be available already earlier (in 2019 - 2020)
plan BM@N-STS system and component availability accordingly, detector completed in 2021?

## Slide 34: Estimated module production time
Mockups modules assembled at JINR
JINR team:
module assembly – most time consuming assembly step
2.5 years
BM@N-STS modules:

## Slide 35: Module + Ladder production volume
CBM-STS |  | 
JINR assembly: | 400 modules, 46 ladders | + 15% spares
GSI (+KIT) assembly: | 496 modules, 60 ladders | 
BM@N-STS |  | 
JINR assembly: | 252 modules, 40 ladders | + 15% spares
consider a further satellite lab for at least the module assembly