## Slide 1
MPD TOF status
Vadim Babkin on behalf of the ToF group of the MPD collaboration

## Slide 2
640x12.5 mm strip: 280х24 = 6720 strips → 13440 el.ch
Advantages of the design:
~94% estimated geometrical efficiency
Convience of integration (28 sec. ECal)
Design of the time-of-flight (TOF) system
Z-direction detectors layout
 | Number of detectors | Number of readout strips | Sensitive area, m2 | Number of FEE cards | Number of FEE channels
MRPC | 1 | 24 | 0.192 | 2 | 48
Module | 10 | 240 | 1.848 | 20 | 480
Barrel | 280 | 6720 | 51.8 | 560 | 13440 (1680 NINO)
φ-direction TOF modules layout
For TPC rail
Notes: At the beginning, let me remind you about the current design of the barrel part of the TOF system.
It looks like a cylinder composed of 14 sectors. It is convenient for integration with ECal since it consists of 28 sectors.
The radius of the TOF cylinder is about one and half meters. The radius of the TOF cylinder is about one and half meters.
Detectors are arranged inside module with small angle to the beam line for better registration and geometrical efficiency.
In this table I present the numbers of the main parts of the barrel TOF.
Total the TOF contents 280 detectors and covers the area of 52 square meters. The total number of the electronics channels is 13440

## Slide 3
MRPC for the MPD TOF
Inner readout board with strips
Triple-stack MRPC cut view
Efficiency and time resolution of the MRPC versus HV
Notes: The triple stack MRPC…

## Slide 4
Cabling and readout electronics location
Total cabling:
14 VME crates
196 TDC72VHL => 14 per crate
560 cables Molex CXP => 40/crate
Cable lengths: 4 - 8 m
About 70 cm2 in each technical
hole for cables and tubes.
Low heat dissipation
inside the barrel! ~10 W/m2
NINO preamp
Molex InfiniBand cables
HV cable
VMEx64 crate
Air cooling
Trigger out
Signal cables
Gas connectors
LV distribution
Slow control
HV connectors
Notes: A very important part of creating the TOF system is the correct cabling.
This is single module with all communications that should be placed inside it.
The readout electronics must be as close as possible to the detector for achieving best time resolution.
But each crate radiates heat up to 300 W. Therefore we decided to fix them directly on the yoke.
Cables taking the signals from the FEE, LV cables, gas tubes and slow control buses will be routed through the center of the module to its outer ends.
Then they will come out from the external sides of the sector and pass through special holes in the yoke.
The space about 70 cm2 (<1% of total size) is enough in each hole in the yoke for all TOF system cables, tubes.

## Slide 5
TOF gas and front-end electronics box (“Artmash”(Minsk) )
Notes: One of the part is the module…. It is finalized. We have in our laboratory several such TOF module. But most serial modules are in Minsk for the improvement

## Slide 6
TOF integration
“Artmash”(Minsk) guides with rollers

## Slide 7
Assembly and transport device (being developed)
“Artmash”(Minsk)

## Slide 8
Assembly and transport device (being developed)
“Artmash”(Minsk)

## Slide 9
Gas system of the TOF MPD
Mixer
Distributor
Purification
Closed loop pump

## Slide 10
Gas system of the TOF MPD

## Slide 11
Building 42 modernization (TOF workshop)
New clear ventilation system.
Photo
Filters & pumps

## Slide 12
Mass production
Painting
MRPC assembling
Optical quality control
Cables and connectors soldering
Detectors installation to the TOF box
Painting of the HV conductive layer
Ultrasonic wave glass cleaning
Mass production staff: 2 physicists, 3 technicians, 2 electronics engineers
Productivity: ~ 1 detector per day (1 module/2 weeks)
During continuous operation, all modules can be assembled in 1 year and 2 months

## Slide 13
Current status of production and equipment purchasing
Task | Current status | Readiness
TOF modules and detectors |  | 
Materials for detectors | Purchased >90% of materials and components. The beginning of the production was delayed due to repair activity in the building 42. | 90%
TOF module box | TOF modules are being reworked and finalized. As a result of these works, the tightness of the gas volume will be improved. Carriages for moving the modules are installed on the boxes. Added the basket for protection of signal cables. Delivery of the finalized boxes is scheduled for November-December. | 70%
TOF cosmic test stand | The mechanical structure of the test stand is ready. More than 80% of the equipment is purchased. Completion of the assembly and commissioning is planned after the finishing of repair of the building 42. | 80%
TOF front-end electronics production | We have 180 amplifiers in stock. The contract for the production of another 560 units signed. Total will be 130%. Delivery is scheduled for the 2019. | 35%
DAQ sysytem |  | 
Signal cables | Done | 100%
VME64x VXS crates | In stock – 6 pcs (14 needed) + 6 in production. | 43%
TDC72VHL modules | In stock – 21 pcs (196 needed) + 51 in production. | 10%
Gas system | All work is performed by a group of WUT (Poland). Purchased more than 90% of the equipment. 80%. assembled in the building 42. | 80%
TOF integration | Part of the equipment is ready (rails, carriages). A tender has been announced for the design and manufacture of an assembly and transportation device. | 35%
HV & LV systems |  | 
LV | In stock – 16 pcs (14 needed). Done. | 100%
НV | In stock – 24 modules (28 needed) | 85%

## Slide 14
Actual time schedule of the MPD TOF assembling (with new conditions)

## Slide 15
  Conclusions
Technical design of the MPD TOF system is complete.
Most materials for the TOF production is purchased by 90% for the entire system which corresponds to the procurement plan.
Everything is ready to start mass-production of detectors.
Development of the readout electronics is complete now. Mass production began last year. At the moment we already have 30% of preamplifier boards. The contract for the production of another 560 units signed.
Service systems are in development and purchase state.
Setup for testing TOF modules with cosmic rays should be commissioned at the end of this year.
  Thank you for the attention!

## Slide 16
  Extra slides

## Slide 17
BM@N TOF-400 system
For the BM@N 26 detectors (20 at the experiment and 6 are reserved) was assembled
103 ps – time resolution of
the BM@N TOF system
(for protons)
Details in the M. Rumyantsev presentation “Particle ID in recent runs” in the BM@N section