## Slide 1: Manufacture, pre-assembly and testing of MPD magnet yoke on VHM Vitkovice, Czech Republic 2016 - 2018
N.Topilin, E.Belyaeva, E.Gerasimov
Международное совещание
«Ускорительный комплекс NICA: проблемы и решения — 2018»,
08 - 15 сентября 2018 г., г. Созополь, Болгария

## Slide 2: MPD Yoke (L=8970 mm, Ø6625 mm)
28 plates
16 t each
2 support rings
42.5 t each
2 poles
44 t each
Total: 621 t
Material:
Steel 10 (AISI 1010)
forging
Lodgement (Yoke support) – 70 tons, ordinary steel St.3 (Fe 360)

## Slide 3: Support rings: need to have holes machining, sandblasting, painting
Yoke production status, March - 2018
Yoke plates: 25 from 28 are ready
Pole machining

## Slide 4: Cradles parts are in progress:
6 cradle support
Spacer plates between bottom surface
of cradle and Roller Skates

## Slide 5: Poles transport supports (2 ps)
Front stand
Back stand
Bottom base parts
Bottom base parts
Rings billets

## Slide 6: Technological tool
Top beam
Lifting beams and Base plate for face surface
Lifting beam for plugs inserting-removing in vertical plates

## Slide 7
Restart to work – 20 March
Floor measurement – 21 May
Cradle installation – 23 May
Cradle measurement – 24 May
13 plates installation – 05-09 June
13 plates measurement – 11 June
Support rings installation – 12-13 June
14-28 plates installation – 14-21 June
1-27 plates measurement – 21 June
700 Pins installation – 6 June - 23 July
Yoke test – 24 July
Disassembly, manufacture, packing – 1-Aug-30 Sept.
Transport to JINR – 1 October – 30 November
Plan of work at VHM (Feb_2018):
Machining
Control assembly
Yoke rigid test

## Slide 8
Floor flatness on area 7x7 m²
0
+0.2
-0.1
+0.1
Common non-flatness is 0.3 mm

## Slide 9: Stands shape

## Slide 10: Measurement Protocol (page 1/5) of Stand #1
Main deviations are
“zero” !
Drawing tolerances are +/- 0.05 mm
on the R=3655 mm and others

## Slide 11: Plate #1 installation (5 June 2018)

## Slide 12: Plate #1 installation (5 June 2018)
Position pins Ø 50 mm

## Slide 13: Plate #1 installation (5 June 2018)

## Slide 14: Plate #2 installation (5 June 2018)
Manipulator from
Tile Calorimeter
(ATLAS, CERN)
It was used in 2002-2006
Second life in 2018-2019
(NICA-MPD, VHM-JINR)

## Slide 15: Plate #2 installation
Surface control tool

## Slide 16: 2 plates in place

## Slide 17: Shims calculation
S=1.73 + (Δ1+Δ2)/2
S=1.8 mm as usual
Δ1, Δ2 – plate passport data

## Slide 18: Shims preparing

## Slide 19: Plates preparing for assembly

## Slide 20: Plates preparing for assembly

## Slide 21: Plate #5 installation (7 June 2018)

## Slide 22: Top points flatness measurement of 7 plates

## Slide 23: 7 plates in assembly
0
0.5

## Slide 24: Assembly step

## Slide 25: Plate #13 installation (9 June 2018)

## Slide 26: 13 plates in place

## Slide 27: 13 plates in assembly
00
0
+0.3
-0.2
+0.2
L=5888 (+1 mm)

## Slide 28: Scaffolding erection
Complementary supports
from both sides

## Slide 29: Support ring manipulation

## Slide 30: Support ring #1 installation (12 June 2018)

## Slide 31: Support ring #1 on side W
Gap 0.4 mm
Gap 0.6 mm
Gap 0 mm
#1
#3
#6
#12
#13
Non-symmetry 0.1 mm
#4
#2

## Slide 32: Support ring #2 installation (13 June 2018)
Gap for plate #12 – 0.1 mm
Gap for plate #13 – 0.1 mm
Non symmetry 0 mm
Full contact on all bottom 11 plates

## Slide 33
Measurement Protocol (page 1/5)
of Support ring
5887 -0.1 , really it is < 0.05 mm

## Slide 34: Support rings on both sides

## Slide 35: Technology beam (8470 mm) installation

## Slide 36: Plate installation

## Slide 37: 2 support ring in assembly
0.53 mm out
0.66 mm out
Limit 0.5 mm

## Slide 38: Plates position on support rings (the similar situation for all bottom ones)
W side (base)
E side
W side (base)
9 mm gaps for 8.5 mm shims

## Slide 39: Plates position on support rings (the similar situation for all bottom ones)
W side (base)
E side
W side (base)

## Slide 40: Plate #26 installation

## Slide 41: 27 plates in place (20 June 2018)

## Slide 42: “Final” measurements report (27 plates in assembly)
Side W – 0.55 mm out
Side E – 0.66 mm out

## Slide 43: Plate #28

## Slide 44: Top plates positions
Gap between #27 and @28
Is 0.5 mm (fixed by steel shims)
Gap is zero
Gap is 0.2 mm
Diameters have nominal dimensions
6583 mm in vertical and horizontal directions
on both sides

## Slide 45: JINR technicians
Ivan
Sergei

## Slide 46
It is half way of preassembly.
Next step is drilling of 544 holes
33H7 for pins 33p6.

## Slide 47: 712 Holes drilling (in 5 steps):
279 from 712 are ready (on 23 June)
1 – drill 28 mm
2 – mill 30 mm, h = 90 mm
3 – mill 32 mm, h = 90 mm
4 – mill 32.6 mm, h = 90 mm
5 – rimmer 33H7 (0+0.025), h = 80-85 mm

## Slide 48
Useless parts
VHM promised steps
Unforeseen problem:

## Slide 49
Predicted very useful tool !

## Slide 50
5. Выдвинуть шток домкрата А так, чтобы можно было убрать
одну дополнительную опору 1 из под стойки ложемента.
Убрать одну дополнительную опору 1 из под стойки ложемента
магнитопровода MPD.
Для удобства все дополнительные опоры можно сделать
составными из двух одинаковых пластин разной толщины.
В ходе испытаний убирать только тонкую пластину, как самую
легкую.
6. Плавно опустить шток домкрата А до образования зазора
1-2 мм между стойкой ложемента и верхней плоскостью
поршня домкрата, либо до падения давления в домкрате до нуля.
В результате этих действий магнитопровод MPD
будет опираться на 3 дополнительные опоры 2,3,4.
Измерить величину получившегося зазора В
между крайней точкой стойки ложемента и опорной
поверхностью цеха.
Вычислить величину отклонения крайней точки стойки
ложемента от своего первоначального положения.
Δ = Н доп.опоры – В, мм
Расчетная оценка величины Δ, мм |  |  | По результатам испытания
Нева-магнит | Прогресстех-Дубна | ЛФВЭ КО | VHM
5,6 | 4,5 | 0,1 | 
В
Опорная поверхность цеха
TEST on 24 July 2018 at VHM
?

## Slide 51
Расчетная оценка величины Δ, мм |  |  | По результатам испытания
Нева-магнит | Прогресстех-Дубна | ЛФВЭ КО | VHM
5,6 | 4,5 | 0,1 | 
TEST on 24 July 2018 at VHM
?
https://www.google.ru/search?q=magnet+vitkovice&newwindow=1&source=lnms&sa=X&ved=0ahUKEwjXq86_09jcAhUpP5oKHQysCIwQ_AUICSgA&biw=1920&bih=974&dpr=1

## Slide 52
Расчетная оценка величины Δ, мм |  |  | По результатам испытания
Нева-магнит | Прогресстех-Дубна | ЛФВЭ КО | VHM
5,6 | 4,5 | 0,1 | 
TEST on 24 July 2018 at VHM
?

## Slide 53
Расчетная оценка величины Δ, мм |  |  | По результатам испытания
Нева-магнит | Прогресстех-Дубна | ЛФВЭ КО | VHM
5,6 | 4,5 | 0,1 | 
TEST on 24 July 2018 at VHM
10.4

## Slide 54: Conclusions
We are on the right way:
1 - there is no mechanical hysteresis
2 - All 4 support trolleys accept half of the standard load
3 - Local load on the concrete is 50% of the design: increases the
durability of the foundation and reduces the chance of
subsidence of rail tracks in the process of exploitation
(локальные нагрузки на бетон составляют 50% от расчетных:
повышается долговечность фундамента и уменьшается шанс
просадки рельсовых путей в процессе эксплуатации)

## Slide 55: Next steps: VHM:
- Manufacture finishing
- Checking
- Packing
- Transportation
- Customs procedure
JINR:
- Local store preparations
- Cranes installation and work permit receiving
- Foundation plates, underrails plates, rails installation
- Pre-assemble of magnet at JINR (Spring 2019)

## Slide 56: MPD Hall today

## Slide 57
Thank you for your attention

## Slide 58: 7 plates in place, top edges horizontality checking

## Slide 59: Relative height of top edges of plates #6 and #7
E side
Point 7E + 0.0
Point 7W + 0.0
Point 6W + 0.0
Point 6E + 0.5
W side is base
Non-flatness of
Faces of 7 plates =
= 0.1 mm