## Slide 1
Progress in the NICA project realization
V. Kekelidze
JINR Scientific Council, session 125,
Dubna, February 21, 2019
“You need to manage not the work - it never ends, but time,
because it is of course.” Richelieu

## Slide 2
basic facility
SPD
MPD
Center NICA
Nuclotron ring (c=251,5 m)
Collider ring (c=503 m)
major milestones
BM@N
the first
physics run
Booster commissioning
Notes: This is a view of major NICA facilities. The Nuclotron – supercoducting synchrotron with circumference of 250 meters was put in operation 24 years ago. The beams from Nuclotron are extracted to the experimental hall, where the first experiment of NICA program BM@N is located. The plan is to put in operation a booster in 2019, and collider - in 2020 simultaneously with the MPD.

## Slide 3
RF Government Disposal
Agreement between
the RF Government
and
the Joint Institute for
Nuclear Research
has been signed
on June 2-nd, 2016

## Slide 4
Major Mailstones
Agreement
Addendum №1
Chapter III
Start of BM@N experiment - 2017
Start-up configuration
of accelerator complex - Booster - 2019
Put in operation MPD - 2020
Start of MPD experiment - 2021
Center NICA & computer complex - 2021
Наstart of SPD construction - 2020
Infrastructure for applied research - 2020

## Slide 5
ECal
Baryonic Matter at Nuclotron (BM@N)
BM@N schematic view
Fulfillment: 60% (of basic configuration)
Start-up configuration is put in operation:
December 2017 Readiness for
data taking
9 objects with a total sum of 492 396 455, 53 Rub
id #: 706970, 706976, 706979, 706980, 706982,
706983, 706984, 706986, 706987
Notes: Several milestones are foreseen to put in operation the fully equipped detector. There major tracker is based on the GEM chambers installed inside the gap of dipole magnet. Fully equipped set-up contains as well TOF system, Ecal, zero degree calorimeter and silicon tracker, which will be installed just downstream the target.

## Slide 6
162 м
Nuclotron
experimental hall
LU-20
12C BM@N SRC
40Ar 84Kr BM@N
03.04
0,5
1,0
1,5
2,0
2,5
3,0
Kr26+
30/03/2018
s
Run №55: March-April 2018
the first physics run of BM@N
start of experiment
BM@N SRC
Notes: Several milestones are foreseen to put in operation the fully equipped detector. There major tracker is based on the GEM chambers installed inside the gap of dipole magnet. Fully equipped set-up contains as well TOF system, Ecal, zero degree calorimeter and silicon tracker, which will be installed just downstream the target.

## Slide 7
Baryonic Matter at Nuclotron (BM@N)
time resolution: T0 ~43 ps
• ToF-700 ~65 ps
• ToF-400 ~53 ps
momentum resolution
GEM: 163 x 45 cm2
milestone I (stage 0 of BM@N) :
the first run: March 22 – April 3, 2018:
targets: C, Al, Cu, Sn, Pb;
beams statistics
      12C6+ 4,0 -4,5 AGeV 20 M events
      40Ar16+ 3,2 AGeV 130 M events
      84Kr26+ 2,3 AGeV 50 M events
L p + p- decay
reconstruction
p-
p
year | 2017 | 2020 | 2021 +
beam | C, Ar/Kr | Au | Au, p
intensity, Hz | 0,5M | 1M | 10M
trig. rate, Hz | 10k | 20k | 50k
central tracker | 10 GEM half pl. | 8 GEM full pl. | 12 GEM or 8+2Si
stage | 0 | 1 | 2
First results in preparation:
Ratio of K+/π+ in Ar - nucleus interactions at beam kinetic energy of 3.2 AGeV
Ratio of K+/π+ in Kr - nucleus interactions at beam kinetic energy of 2.4 AGeV
Yields of Λ hyperon in C – nucleus (C,Al,Cu) interactions at beam kinetic energy of 4 - 4.5 AGeV
Notes: Several milestones are foreseen to put in operation the fully equipped detector. There major tracker is based on the GEM chambers installed inside the gap of dipole magnet. Fully equipped set-up contains as well TOF system, Ecal, zero degree calorimeter and silicon tracker, which will be installed just downstream the target.

## Slide 9
Major Mailstones
Agreement
Addendum №1
Chapter III
Start of BM@N experiment - 2017 - 2018 March
Start-up configuration
of accelerator complex - Booster - 2019
Put in operation MPD - 2020
Start of MPD experiment - 2021
Center NICA & computer complex - 2021
Наstart of SPD construction - 2020
Infrastructure for applied research - 2020

## Slide 10
Ecool
RF
Booster
PS
ref. mag. sec.
Booster
Nuclotron
parameter | value
Ion types | A/Z < 3
injection energy, MeV/u | 3.2
maximum energy, MeV/u | 600
magnetic rigidity, T m | 1.6 – 25.0
circumference, m | 210.96
vacuum, Torr | 10-11
intensity, Au ions/pulse | 1.5 109
RF range, MHz | 0.5 -2.53
Booster assembly - started in 2018

## Slide 11
Elements of HILac – Booster beam channel
.
The gap for beam channel:
Booster - Nuclotron
dipole magnets in
the first quadrant of Booster
Booster assembly

## Slide 12
14/02/2019
dipoles in the third quadrat
Bridge for allocation of equipment
for measuring period
power supply systems for Booster
the head part of injection channel

## Slide 13
Time table
Booster assembly |  | 2018 |  |  |  |  |  |  |  | 2019 |  |  |  |  |  |  |  |  |  | 
 |  | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI
“Cold” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Quadrant 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | bypasses and ends |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | reference magnets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | “Warm” sections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | E-cooling |  |  |  | commissioned |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | injection section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | beam extraction section |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | RF system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | vacuum system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | power supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | cryogenic system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | thermometry system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
technological commissioning
Commissioning with beam

## Slide 14
Major Mailstones
Agreement
Addendum №1
Chapter III
Start of BM@N experiment - 2017 - 2018 March
Start-up configuration
of accelerator complex - Booster - 2019 - 2019
Put in operation MPD - 2020
Start of MPD experiment - 2021
Center NICA & computer complex - 2021
Наstart of SPD construction - 2020
Infrastructure for applied research - 2020

## Slide 15
Control Dewar,
pipe lines
Cryostat
SC coil
Trim Coil
Superconducting Solenoid
ASG superconductors, Genova
- General responsibility
TPC region
weight ~ 900 t
B0=0.5 T
field homogeneity (~ 3x10-4)
HM Vitkovice, Czech Republic:
Yoke + supports
nominal current: 1790 A
stored energy: 14.6 MJ
Notes: The major part of MPD is SC solenoiodal magnet. It is a challenging project due to very high requirement for the magnetic field homogeneity – better that a permill.
After long negotiations a contract is signed with the ASG sc company – the one which produced a big solenoid for CMS. The ASG is responsible for production of coils, cryostat control system etc. In addition the company takes responsibility for the overall supervision and final characteristics.

## Slide 16
The Yoke
control assembly at HM Vitkovice:
the tolerances ~ 0,5 mm
Vitkovice, February 6
plan of arrival to Dubna on March 12
Notes: 8 contracts have been signed for the construction of large superconducting solenoid. All works are well progressing. The yoke production is going on at Vitkovice heavy machinery in Czech Republic. The cold mass is under production in other European enter[prizes.

## Slide 17
winding of the 3-d module of coil - in progress
vacuum cryostat
vacuum test
Cold mass, cryostat ….
module assembling
all basic parts are produced
assembly procedure - in progress;
power supplies - produced by Sigma-Phi
control Dewar - produced at ILK Dresden
Final assembly in the MPD hall
– September 2019
trim coil
Cold mass assembled

## Slide 18
TPC (basic tracker) & TOF
assembly tools
length | 340 см
outer R | 140 см
inner R | 27 см
gas | 90%Ar +10%CH4
drift time | < 30 ms;
# R-O ch. | 12 + 12
# pads/ch. | 95 232
max rate | < 7kGz
pad structure:
- raws – 53
- l pads 5×18 mm2
- s pads 5×12 mm2
momentum resolution
outer cylinder
FE electronics:
FEC64SAM –
dual SAMPA card
(ALICE techn.)
280 MPRC’s
13 440 ch.
TPC
TOF
R= 170cm
efficiency,
time resolution
electronics:
NINO
& HPTDC

## Slide 19
Pb+Sc “Shashlyk”
read-out: WLS fibers + MAPD
L ~35 cm (~ 14 X0)
Segmentation (4x4 cm2),
s(E) better than 5% @ 1 GeV;
time resolution ~500 ps
Barrel ECAL ~ 43 000 modules
projective geometry
Electromagnetic calorimeter: ECAL
module prototype
block of modules
Notes: One of the unique high-tech projects within the framework of the MPD experiment is the large scale electromagnetic calorimeter of the shashlik type with projection geometry. This is a joint project with Tsinghua University (Beijing). It is required to produce more than 40 thousand modules and assemble them into a single cylindrical system, calibrate and put into operation.

## Slide 20
MPD support
construction
20
Sets of modules
Beijing
IHEP
p0 gg
Module production plans
JINR, IHEP, Tensor + .. - 25%
China - 75%

## Slide 21
Western
semiring
SPD
hall
tunnel
adjustment
~ 100 mu
MPD
hall
Civil Construction, bld.17
February 18, 2019
Readiness of MPD Hall to start MPD magnet assembly - 2019

## Slide 22
assembly of RF-1 station and preparation for tests
test of prototype of pikup/kicker for stochastic cooling system
Collider parts (Budker INP)
prototype of
cooling system
for ECS-2,5 MeV
water pressure
test of ECS

## Slide 23
Off-line cluster at LHEP
Data storage at LIT
Development of computing
Super fast disk storage
For off-line cluster at LIT

## Slide 24
Polarizaed beams:
pp at spp = 12 – 27 GeV, Lav ≈ 1032 cм-2с-1
dd at sNN = 4 – 13 GeV
longitudinally and transversally polarized
tasks:
Nucleon spin structure
spin dependent effects in elastic scattering of pp, pd & dd;
Spin effects in hadron production at high pT
SPD will provide unique conditions to measure the whole set of PDF’s (eight) in one experiment to obtain comprehensive information of nucleon spin structure with minimum statistical errors and systematics
SPD (Spin Physics Detector): Study of nucleon spin structure and polarization phenomena
SPD Collaboration - 2019
SPD CDR – 2019
SPD TDR - 2020
Drell-Yan pairs Direct photons J/ψ production
SPD
Notes: Study of nucleon spin structure must prove the sum rule and to solve a puzzle of “spin deficit”. NICA collider will provide collisions of protons and deuterons with all combinations of polarization – transversal and longitudinal. It will allow to measure all 8 intrinsic-transverse-momentum PDFs at leading twists in one experiment. MMTDY mechanism and SIDIS processes are good tools for these measurements.

## Slide 25
MPD and BM@N Collaborations
2-nd meeting, Dubna, October 29-30, 2018.
https://indico.jinr.ru/conferenceTimeTable.pyconfId=610#20181029

## Slide 26
University of Plovdiv, Bulgaria;
Institute of High Energy Physics, China;
Shanghai Institute of Nuclear and Applied Physics, CFS, China;
Tsinghua University, Beijing, China;
Nuclear Physics Institute CAS, Czech Republic;
Tubingen University, Germany;
Tel Aviv University, Israel;
Joint Institute for Nuclear Research;
Almaty Institute of Physics & Technology, Kazakhstan;
Institute of Applied Physics, Chisinev, Moldova;
Warsaw University of Technology, Poland;
Baryonic Matter at Nuclotron
(BM@N) Collaboration:
University of Wroclaw, Poland;
Institute of Nuclear Research RAS, Moscow, Russia;
NRC Kurchatov Institute, Moscow, Russia;
Institute of Theoretical & Experimental Physics, NRC KI, Moscow, Russia;
Moscow Engineer and Physics Institute, Russia;
Skobeltsin Institute of Nuclear Physics, MSU, Russia;
Moscow Institute of Physics and Technics, Moscow, Russia;
Massachusetts Institute of Technology, Cambridge, USA.
10 Countries, 19 Institutions, 222 participants

## Slide 27
Tagir Aushev
Mircea Baznat
David Blaschke
Dmitry Blau
Fedor Guber
Or Hen
Mei Huang
Adam Kisiel
Andrej Kugler
Albert Loktionov
Yugang Ma
Eli Piasetzky
Mikhail Merkin
Yury Potrebenikov
Hans Rudolf Schmidt
Valery Sosnovtsev
Alexey Stavinskiy
Vanio Tcholakov
Yi Wang
Mikhail Kapishin
Anna Maksymchuk
Election results:
IB Chair - Hans Rudolf Schmidt, Tubingen University, Germany
Spokesperson – Michail Kapishin, JINR
Deputy Spokesperson - Peter Senger, GSI
Project manager – Anna Maksimchuk, JINR
IB of BM@N:

## Slide 28
The BM@N Executive Council
Ex-officio members:
Mikhail Kapishin – Spokesperson (2018 - 2021)
Peter Senger – Deputy Spokesperson (2019 - 2021)
Anna Maksymchuk – Project Manager (2018 – 2021)
Elected members:
Konstantin Gertsenberger (2019 – 2022)
Or Hen (2019 – 2021)
Vyacheslav Slepnev (2019 – 2021)
Arkadiy Taranenko (2019 – 2022)
Yi Wang (2019 – 2020)
Alexander Zinchenko (2019 – 2020)

## Slide 29
Baku State University, NNRC, Azerbaijan;
University of Plovdiv, Bulgaria;
University Tecnica Federico Santa Maria, Valparaiso, Chili;
Tsinghua University, Beijing, China;
USTC, Hefei, China;
Huizhou University, Huizhou, China;
Institute of Nuclear and Applied Physics, CAS, Shanghai, China;
Central China Normal University, China;
Shandong University, Shandong, China;
Institute of Modern Physics of CAS, Lanzhou, China;
IHEP, Beijing, China;
University of South China, China;
Three Gorges University, China;
Palacky University, Olomouc, Czech Republic;
NPI CAS, Rez, Czech Republic;
Tbilisi State University, Tbilisi, Georgia;
Joint Institute for Nuclear Research;
MultiPurpose Detector (MPD)
Collaboration:
10 Countries, 32 Institutes, 465 participants

## Slide 30
UNAM, Mexico City, Mexico;
Institute of Applied Physics, Chisinev, Moldova;
WUT, Warsaw, Poland;
NCN, Otwock – Swierk, Poland;
Jan Kochanowski University, Kielce, Poland;
UW, Wroclaw, Poland;
INR RAS, Moscow, Russia;
MEPhI, Moscow, Russia;
PNPI, Gatchina, Russia;
INP MSU, Moscow, Russia;
SPSU - Dept. of NP, Russia;
St. Petersburg, Russia;
SPSU – Dept. of HEP, St. Petersburg, Russia;
KI NRS, Moscow, Russia;
North Ossetia State University, Vladikavkaz, Russia;

## Slide 31
Election results:
IB Chair - Fuqiang Wang, Huzhou University, China;
Spokesperson – Adam Kisiel, Warsaw University of Technology, Poland;
Deputy Spokesperson - Victor Riabov, PNPI St. Petersburg, Russia;
Deputy Spokesperson - Zebo Tang, USTC in Hefei, China;
Project manager– Vyacheslav Golovatyuk, JINR.
Tagir Aushev
Alejandro Ayala
Mircea Baznat
Marcin Bielewicz
David Blaschke
Dmitry Blau
Deging Fang
Oleg Fedin
Deqing Feng
Grigory Feofilov
Viacheslav Golovatyuk
Mei Huang
Alexander Ivashkin
Adam Kisiel
Andrej Kugler
Sergey Kuleshov
Viacheslav Kulikov
Feng Liu
Miroslav Maslan
Mikhail Merkin
Nalli Pukhaeva
Anar Rustamov
Maciej Rybczynski
Revaz Shanidze
Zebo Tang
Arkadiy Taranenko
Vanio Tcholakov
Kristina Vokhmyanina
Fuqiang Wang
Yi Wang
Xiaodong Wang
Qinghua Xu
Chengxin Zhao
IB of MPD:

## Slide 32
Involvement of researches from Russian scientific centers to the NICA project is done in 2018 with the support of
Russian Fund for Basic Research (RFBR)
The result of application for the grants dedicated to the theme
«Basic features and phase transition of hadronic and quark-gluon matter: mega-sciense class set-ups - «NICA Complex»:
received – 97 applications;
36 projects are supported based on the results of expertize,
281 researches

## Slide 33
Progress in the works on the NICA project in 2014 – 2018 (EVM diagram)

## Slide 34
“There is never a big deal without big difficulties.” Voltaire
Thank you